## Sheet1
Activity_ID | Activity_Status | WBS_CD | Activity_Type | Activity_Name | Planned_Start_DT | Planned_Finish_DT | Actual_Start_DT | Actual_Finish_DT | ML_Planned_DT | ML_Actual_DT | Activity_Complete_PCNT | Actual_Dur | Remaining_Dur | Original_Dur | Total_Float | Remaining_Float | Primary_Constraint | Primary_Constraint_DT | Sec_Constraint | Sec_Constraint_DT | Pred_DTL | Sec_DTL | Resources | Budgeted_Labor_Units | Budgeted_Nonlabor_Units
MDC1.M1000 | Completed | MDC1-BL.1 | Start Milestone | Project Start | 2020-04-27 07:00 |  |  |  | 2020-04-27 07:00 |  | 100 | 0 | 0 | 0 |  |  | As Late As Possible |  |  |  |  | A1170: FS, MDC1-2029: FS, MDC1-2527: FS |  | 0 | 0
A1170 | Completed | MDC1-BL.4.9.2 | Start Milestone | Phase 1A - Funding Release | 2020-02-24 07:00 |  | 2020-02-24 07:00 |  | 2020-02-24 07:00 | 2020-02-24 07:00 | 100 | 0 | 0 | 0 |  |  | Start On or After |  |  |  | MDC1.M1000: FS | MDC1-1383: FS, MDC1-1977: FS, MDC1.C2.E1300: FS, MDC1.C2.E1310: FS, MDC1.C2.E1360: FS, MDC1.C2.E1410: FS, MDC1.C3.E1340: FS, MDC1.C3.E1360: FS, MDC1.C3.E1350: FS, MDC1.C3.E1370: FS, MDC1.C4.E1360: FS, MDC1.C4.E1380: FS, MDC1.C4.E1370: FS, MDC1.C4.E1390: FS, MDC1.C1.CS1110: FS, MDC1.C2.CS1090: FS, MDC1.C4.CS1090: FS, MDC1-2001: FS, MDC1-2002: FS, MDC1-2002: SS |  | 0 | 0
MDC1.C1.E1320 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 1 | 2020-11-06 08:00 |  |  |  | 2020-11-06 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | MDC1-2527: FS | MDC1.C1.C1250: FS |  | 0 | 0
MDC1.P1010 | Completed | MDC1-BL.3.1 | Start Milestone | Mobilize on Site | 2020-04-27 07:00 |  |  |  | 2020-04-27 07:00 |  | 100 | 0 | 0 | 0 | [6 empty] | MDC1.S.1000: SS -1 | MDC1-P1020: FS |  | 0 | 0
MDC1-P1020 | Completed | MDC1-BL.3.1 | Start Milestone | Break Ground | 2020-04-27 07:00 |  |  |  | 2020-04-27 07:00 |  | 100 | 0 | 0 | 0 |  |  | Start On or After |  |  |  | MDC1.P1010: FS | MDC1.AD.CS1000: FS, MDC1-C1.P1000: FS |  | 0 | 0
MDC1-C1.P1000 | Completed | MDC1-BL.3.2 | Start Milestone | Foundation Start - Admin/COLO 1 | 2020-04-27 07:00 |  |  |  | 2020-04-27 07:00 |  | 100 | 0 | 0 | 0 | [6 empty] | MDC1-P1020: FS, MDC1-2002: FS | MDC1.C1.CS1010: FS, MDC1.AD.CS1000: FS |  | 0 | 0
MDC1-C1.P1100 | Completed | MDC1-BL.3.2 | Start Milestone | Steel Erection - Admin/COLO 1 | 2020-07-27 07:00 |  |  |  | 2020-07-27 07:00 |  | 100 | 0 | 0 | 0 | [6 empty] | MDC1.S.1010: FS, MDC1.AD.CS1030: SS | MDC1.C1.CS1030: FS |  | 0 | 0
MDC1-C1.P1500 | Not Started | MDC1-BL.3.2 | Start Milestone | Fit out Start - Admin/COLO 1 | 2020-09-02 07:00 |  |  |  | 2020-09-02 07:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.AD.CS1100: FS | MDC1.C1.C1120: FS, MDC1.C1.C1030: FS, MDC1.C1.C3010: FS, MDC1.C1.C2030: FS, MDC1.C1.C4010: FS, MDC1.C1.C1170: FS, MDC1AD-1017: FS |  | 0 | 0
MDC1-C1.P1400 | Not Started | MDC1-BL.3.2 | Start Milestone | SOG- ADMIN/ COLO1 Start | 2020-08-14 07:00 |  |  |  | 2020-08-14 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | MDC1.AD.CS1080: FS, MDC1.AD.CS1060: FS | MDC1.AD.CS1100: FS, MDC1.AD.CS1090: FS |  | 0 | 0
MDC1-C2.P1000 | Completed | MDC1-BL.3.3 | Start Milestone | Foundation Start - COLO 2 | 2020-06-12 07:00 |  |  |  | 2020-06-12 07:00 |  | 100 | 0 | 0 | 0 | [6 empty] | MDC1.C1.CS1000: FS, MDC1.C1.CS1020: FS | MDC1.C2.CS1010: FS, MDC1.C2.CS1000: FS |  | 0 | 0
MDC1-C2.P1100 | Not Started | MDC1-BL.3.3 | Start Milestone | Steel Erection - COLO 2 | 2020-07-07 07:00 |  |  |  | 2020-07-07 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C1.CS1030: FS | MDC1.C2.CS1020: FS |  | 0 | 0
MDC1-C2.P1500 | Not Started | MDC1-BL.3.3 | Start Milestone | Fit out Start - COLO 2 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 16 | 16 |  |  |  |  | MDC1.C2.CS1090: FS | MDC1.C2.C1050: FS |  | 0 | 0
MDC1-C2.P1400 | Not Started | MDC1-BL.3.3 | Start Milestone | SOG- COLO 2 Start | 2020-09-22 07:00 |  |  |  | 2020-09-22 07:00 |  | 0 | 0 | 0 | 0 | 14 | 14 |  |  |  |  | MDC1.C2.CS1070: FS, MDC1.C2.CS1050: FS, MDC1.C2.CS1020: FS | MDC1.C2.CS1090: FS, MDC1.C2.CS1080: FS |  | 0 | 0
MDC1-C3.P1000 | Completed | MDC1-BL.3.4 | Start Milestone | Foundation Start - COLO 3 | 2020-06-22 07:00 |  |  |  | 2020-06-22 07:00 |  | 100 | 0 | 0 | 0 | [6 empty] | MDC1.C2.CS1000: FS | MDC1.C3.CS1000: FS |  | 0 | 0
MDC1-C3.P1100 | Not Started | MDC1-BL.3.4 | Start Milestone | Steel Erection -COLO 3 | 2020-07-23 07:00 |  |  |  | 2020-07-23 07:00 |  | 0 | 0 | 0 | 0 | 7 | 7 |  |  |  |  | MDC1.C2.CS1020: FS | MDC1.C3.CS1020: FS |  | 0 | 0
MDC1-C3.P1500 | Not Started | MDC1-BL.3.4 | Start Milestone | Fit out Start - COLO 3 | 2020-10-22 07:00 |  |  |  | 2020-10-22 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C3.CS1090: FS | MDC1.C3.C1090: FS |  | 0 | 0
MDC1-C3.P1400 | Not Started | MDC1-BL.3.4 | Start Milestone | SOG- COLO 3 Start | 2020-10-10 07:00 |  |  |  | 2020-10-10 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C3.CS1070: FS | MDC1.C3.CS1090: FS, MDC1.C3.CS1080: FS |  | 0 | 0
MDC1-C4.P1000 | Not Started | MDC1-BL.3.5 | Start Milestone | Foundation Start - COLO 4 | 2020-07-20 07:00 |  |  |  | 2020-07-20 07:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C3.CS1010: FS | MDC1.C4.CS1010: FS, MDC1.C4.CS1000: FS |  | 0 | 0
MDC1-C4.P1100 | Not Started | MDC1-BL.3.5 | Start Milestone | Steel Erection - COLO 4 | 2020-08-08 07:00 |  |  |  | 2020-08-08 07:00 |  | 0 | 0 | 0 | 0 | 10 | 10 |  |  |  |  | MDC1.C3.CS1020: FS | MDC1.C4.CS1020: FS |  | 0 | 0
MDC1-C4.P1500 | Not Started | MDC1-BL.3.5 | Start Milestone | Fit out Start - COLO 4 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 68 | 68 |  |  |  |  | MDC1.C4.CS1090: FS | MDC1.C4.C1140: FS |  | 0 | 0
MDC1-C4.P1400 | Not Started | MDC1-BL.3.5 | Start Milestone | SOG- COLO 4 Start | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 68 | 68 |  |  |  |  | MDC1.C4.CS1070: FS | MDC1.C4.CS1090: FS |  | 0 | 0
MDC1-C1.P1200 | Not Started | MDC1-BL.3.2 | Start Milestone | Insulated Metal Panel Start- Admin/COLO 1 | 2020-07-07 07:00 |  |  |  | 2020-07-07 07:00 |  | 0 | 0 | 0 | 0 | 9 | 9 |  |  |  |  | MDC1.AD.CS1030: SS 12 | MDC1.C1.CS1050: FS, MDC1AD-1010: FS, MDC1.AD.CS1060: FF, MDC1.AD.CS1070: FS, MDC1.C1.CS1060: FS, MDC1-1965: FS, MDC1-1972: FS, MDC1-C1.P1300: FS |  | 0 | 0
MDC1-C1.P1300 | Not Started | MDC1-BL.3.2 | Start Milestone | Roof Panel Start -Admin/COLO 1 | 2020-07-15 07:00 |  |  |  | 2020-07-15 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 |  |  |  |  | MDC1.AD.CS1040: FS, MDC1.AD.CS1050: SS 2, MDC1-C1.P1200: FS | MDC1.AD.CS1060: FS |  | 0 | 0
MDC1-C2.P1200 | Not Started | MDC1-BL.3.3 | Start Milestone | Insulated Metal Panel Start- COLO 2 | 2020-07-20 07:00 |  |  |  | 2020-07-20 07:00 |  | 0 | 0 | 0 | 0 | 18 | 18 |  |  |  |  | MDC1.C1.CS1050: FS | MDC1.C2.CS1040: FS |  | 0 | 0
MDC1-C2.P1300 | Not Started | MDC1-BL.3.3 | Start Milestone | Roof Panel Start -COLO 2 | 2020-07-27 07:00 |  |  |  | 2020-07-27 07:00 |  | 0 | 0 | 0 | 0 | 10 | 10 |  |  |  |  | MDC1.C1.CS1070: FS | MDC1.C2.CS1050: FS |  | 0 | 0
MDC1-C3.P1200 | Not Started | MDC1-BL.3.4 | Start Milestone | Insulated Metal Panel Start- COLO 3 | 2020-08-15 07:00 |  |  |  | 2020-08-15 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C2.CS1040: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS | MDC1.C3.CS1040: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FF, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF |  | 0 | 0
MDC1-C3.P1300 | Not Started | MDC1-BL.3.4 | Start Milestone | Roof Panel Start -COLO 3 | 2020-08-18 07:00 |  |  |  | 2020-08-18 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C2.CS1050: FS | MDC1.C3.CS1050: FS |  | 0 | 0
MDC1-C4.P1200 | Not Started | MDC1-BL.3.5 | Start Milestone | Insulated Metal Panel Start- COLO 4 | 2020-09-01 07:00 |  |  |  | 2020-09-01 07:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C3.CS1040: FS, MDC1.C3.CS1040: SS, MDC1-C3.P1200: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS | MDC1.C4.CS1040: FS |  | 0 | 0
MDC1-C4.P1300 | Not Started | MDC1-BL.3.5 | Start Milestone | Roof Panel Start - COLO 4 | 2020-09-04 07:00 |  |  |  | 2020-09-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C3.CS1050: FS | MDC1.C4.CS1050: FS |  | 0 | 0
MDC1-C1.P1800 | Not Started | MDC1-BL.3.2 | Start Milestone | Cx - Level 2 Start COLO 1 | 2021-01-25 08:00 |  |  |  | 2021-01-25 08:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C1.C1040: FS, MDC1-P1050: FS, MDC1.C1.C1130: FS, MDC1.C1.C1420: FS, MDC1.C1.C1460: FS, MDC1.C1.C1400: FS, MDC1.C1.C1330: FS, MDC1.C1.C1440: FS, MDC1.C1.C1320: FS, MDC1.C1.C1340: FS, MDC1.C1.C1290: FS, MDC1.C1.C3340: FS, MDC1.C1.C1320: SS, MDC1.C1.C2260: FS, MDC1.C1.C4320: FS, MDC1-2529: FS | MDC1.C1.Cx2020: FS |  | 0 | 0
MDC1-C2.P1900 | Not Started | MDC1-BL.3.3 | Start Milestone | Cx - Level 2 Start COLO 2 | 2021-03-19 07:00 |  |  |  | 2021-03-19 07:00 |  | 0 | 0 | 0 | 0 | 112 | 112 |  |  |  |  | MDC1.C2.C1450: FS, MDC1.C2.C3440: FS, MDC1.C2.C2230: FS, MDC1.C2.C2430: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.C1220: FS, MDC1.C2.C1320: FS, MDC1.C2.C2210: FS, MDC1.C2.C2320: FS, MDC1.C2.C3200: FS, MDC1.C2.C3300: FS, MDC1.C2.C4160: FS, MDC1.C2.C4260: FS, MDC1.C2.C1240: FS, MDC1.C2.C1400: FS, MDC1.C2.C2240: FS, MDC1.C2.C2390: FS, MDC1.C2.C4200: FS, MDC1.C2.C4330: FS | MDC1.M3010: FS |  | 0 | 0
MDC1-C3.P1800 | Not Started | MDC1-BL.3.4 | Start Milestone | Cx - Level 2 Start COLO 3 | 2021-04-14 07:00 |  |  |  | 2021-04-14 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | MDC1.C3.Cx2000: SS, MDC1.C3.C1200: FS, MDC1.C3.C1400: FS, MDC1.C3.C1150: FS, MDC1.C3.C1190: FS, MDC1.C3.C1340: FS, MDC1.C3.C1440: FS, MDC1.C3.C1260: FS, MDC1.C3.C2270: FS | MDC1.C3.Cx2030: FS, MDC1.C3.Cx2010: FS, MDC1.C3.Cx2050: FS |  | 0 | 0
MDC1-C4.P1800 | Not Started | MDC1-BL.3.5 | Start Milestone | Cx - Level 2 Start COLO 4 | 2021-05-21 07:00 |  |  |  | 2021-05-21 07:00 |  | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | MDC1.C4.Cx2000: SS, MDC1.C4.C1390: FS, MDC1.C4.C1410: FS, MDC1.C4.C1090: FS, MDC1.C4.C1210: FS, MDC1.C4.C1330: FS, MDC1.C4.C1430: FS | MDC1.C4.Cx2030: FS, MDC1.C4.Cx2010: FS, MDC1.C4.Cx2050: FS |  | 0 | 0
MDC1-C1.P1600 | Not Started | MDC1-BL.3.2 | Start Milestone | Ready to Set Exterior MER | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 43 | 43 |  |  |  |  | MDC1.C1.C1050: FS | MDC1.C1.C1250: FS |  | 0 | 0
MDC1-C1.P1700 | Not Started | MDC1-BL.3.2 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C1.C1060: FS | MDC1.C1.C1110: FS |  | 0 | 0
MDC1-C2.P1600 | Not Started | MDC1-BL.3.3 | Start Milestone | Ready to Set MER | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 47 | 47 |  |  |  |  | MDC1.C2.C1040: FS | MDC1.C2.C1250: FS |  | 0 | 0
MDC1-C2.P1700 | Not Started | MDC1-BL.3.3 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 |  |  |  |  | MDC1.C2.C1060: FS | MDC1.C2.C1120: FS |  | 0 | 0
MDC1-C3.P1600 | Not Started | MDC1-BL.3.4 | Start Milestone | Ready to Set Exterior MER | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C3.C1050: FS | MDC1.C3.C1230: FS |  | 0 | 0
MDC1-C3.P1700 | Not Started | MDC1-BL.3.4 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 58 | 58 |  |  |  |  | MDC1.C3.C1060: FS | MDC1.C3.C1160: FS |  | 0 | 0
MDC1-C4.P1600 | Not Started | MDC1-BL.3.5 | Start Milestone | Ready to Set Exterior MER | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 67 | 67 |  |  |  |  | MDC1.C4.C1060: FS | MDC1.C4.C1230: FS |  | 0 | 0
MDC1-C4.P1700 | Not Started | MDC1-BL.3.5 | Start Milestone | Ready to Set Exterior Mechanical Equipment | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C4.C1070: FS | MDC1.C4.C1110: FS |  | 0 | 0
MDC1.C1.E1380 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 3 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | MDC1-2029: FS, MDC1-2527: FS | MDC1.C1.C3210: FS |  | 0 | 0
MDC1.C1.E1330 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 2 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | MDC1-2527: FS | MDC1.C1.C2270: FS |  | 0 | 0
MDC1.C1.E1470 | Not Started | MDC1-BL.4.10.3.1.1 | Start Milestone | MDC1 Deliery -MER ROJ COLO 1 CELL 4 | 2020-12-04 07:00 |  |  |  | 2020-12-04 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | MDC1-2029: FS, MDC1-2527: FS | MDC1.C1.C4270: FS |  | 0 | 0
MDC1.C2.E1300 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 1 | 2020-12-15 08:00 |  |  |  | 2020-12-15 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C1250: FS |  | 0 | 0
MDC1.C2.E1310 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 2 | 2020-12-22 07:00 |  |  |  | 2020-12-22 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C2290: FS |  | 0 | 0
MDC1.C2.E1360 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 3 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C3230: FS |  | 0 | 0
MDC1.C2.E1410 | Not Started | MDC1-BL.4.10.3.1.6 | Start Milestone | MDC1 Deliery -MER ROJ COLO 2 CELL 4 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 5 | 5 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C2.C4220: FS |  | 0 | 0
MDC1.C3.E1340 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 1 | 2021-01-29 07:00 |  |  |  | 2021-01-29 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C1230: FS |  | 0 | 0
MDC1.C3.E1360 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 3 | 2021-02-12 07:00 |  |  |  | 2021-02-12 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C3200: FS |  | 0 | 0
MDC1.C3.E1350 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 2 | 2021-02-05 07:00 |  |  |  | 2021-02-05 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C2260: FS |  | 0 | 0
MDC1.C3.E1370 | Not Started | MDC1-BL.4.10.3.1.7 | Start Milestone | MDC1 Deliery -MER ROJ COLO 3 CELL 4 | 2021-02-19 07:00 |  |  |  | 2021-02-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C3.C4270: FS |  | 0 | 0
MDC1.C4.E1360 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 1 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C1230: FS |  | 0 | 0
MDC1.C4.E1380 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 3 | 2021-03-26 07:00 |  |  |  | 2021-03-26 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C3210: FS |  | 0 | 0
MDC1.C4.E1370 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 2 | 2021-03-19 07:00 |  |  |  | 2021-03-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C2270: FS |  | 0 | 0
MDC1.C4.E1390 | Not Started | MDC1-BL.4.10.3.1.5 | Start Milestone | MDC1 Deliery -MER ROJ COLO 4 CELL 4 | 2021-04-02 07:00 |  |  |  | 2021-04-02 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After |  |  |  | A1170: FS, MDC1-2527: FS | MDC1.C4.C4250: FS |  | 0 | 0
MDC1-2001 | Completed | MDC1-BL.4.9.2 | Start Milestone | PEMB Release | 2020-02-24 07:00 |  | 2020-02-24 07:00 |  | 2020-02-24 07:00 | 2020-02-24 07:00 | 100 | 0 | 0 | 0 |  |  | Start On or After |  |  |  | A1170: FS | MDC1-1383: FS |  | 0 | 0
MDC1-2002 | Completed | MDC1-BL.4.9.2 | Start Milestone | Phase 1B - Funding Release | 2020-03-30 07:00 |  | 2020-03-30 07:00 |  | 2020-03-30 07:00 | 2020-03-30 07:00 | 100 | 0 | 0 | 0 |  |  | Start On or After |  |  |  | A1170: FS, A1170: SS | MDC1-1977: FS, MDC1-1998: FS 7, MDC1.AD.CS1030: FS, MDC1.AD.CS1000: FS, MDC1.AD.CS1020: FS, MDC1-2011: FS 7, MDC1-2013: FS 7, MDC1-1994: FS, MDC1.S.1000: FS, MDC1-2016: FS 7, MDC1-1997: FS 7, MDC1-2003: FS, MDC1-C1.P1000: FS, MDC1-2000: FS, MDC1-2111: FS, MDC1-1996: FS, MDC1-2140.1: FS |  | 0 | 0
MDC1-2003 | Not Started | MDC1-BL.4.9.2 | Start Milestone | Phase 1C - Funding Release | 2020-06-30 08:00 |  |  |  | 2020-06-30 08:00 |  | 0 | 0 | 0 | 0 | 11 | 11 | Start On or After | 2020-06-30 08:00 |  |  | MDC1-2002: FS | MDC1-2008: FS, MDC1.AD.CS1090: FS, MDC1-2010: FS, MDC1-2012: FS, MDC1.C1.CS1050: FS, MDC1.AD.CS1050: FS, MDC1-1995: FS, MDC1-2101: FS, MDC1-2102: FS, MDC1-2103: FS, MDC1-2104: FS, MDC1-2105: FS, MDC1-2106: FS, MDC1.AD.CS1050: FF |  | 0 | 0
MDC1-2029 | Completed | MDC1-BL.4.9.2 | Start Milestone | Schneider Electric ROJ Received from MDC1 | 2020-04-27 07:00 |  |  |  | 2020-04-27 07:00 |  | 100 | 0 | 0 | 0 |  |  | Start On or After |  |  |  | MDC1.M1000: FS | MDC1.C1.E1380: FS, MDC1.C1.E1470: FS |  | 0 | 0
MDC1.C1.E1280 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 1 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C1.C1170: FS | MDC1.C1.C1230: FS |  | 0 | 0
MDC1.C1.E1390 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 3 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C1.C3200: FS | MDC1.C1.C3290: FS |  | 0 | 0
MDC1.C1.E1290 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 2 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C1.C2160: FS | MDC1.C1.C2210: FS |  | 0 | 0
MDC1.C1.E1400 | Not Started | MDC1-BL.4.10.2.5.1 | Start Milestone | AHU - ROJ COLO-1 Cell- 4 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C1.C4190: FS | MDC1.C1.C4250: FS |  | 0 | 0
MDC1.C2.E1260 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 1 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C2.C1160: FS | MDC1.C2.C1210: FS |  | 0 | 0
MDC1.C2.E1320 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 3 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 | Start On or After | 2020-12-23 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3250: FS |  | 0 | 0
MDC1.C2.E1270 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 2 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C2.C2140: FS | MDC1.C2.C2200: FS |  | 0 | 0
MDC1.C2.E1330 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 4 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C2.C4150: FS | MDC1.C2.C4190: FS |  | 0 | 0
MDC1.C3.E1140 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 1 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 |  |  |  |  | MDC1.C3.C1070: FS | MDC1.C3.C1140: FS |  | 0 | 0
MDC1.C3.E1300 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 3 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C3.C3090: FS | MDC1.C3.C3140: FS |  | 0 | 0
MDC1.C3.E1150 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 2 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 |  |  |  |  | MDC1.C3.C2070: FS | MDC1.C3.C2140: FS |  | 0 | 0
MDC1.C3.E1310 | Not Started | MDC1-BL.4.10.2.5.3 | Start Milestone | AHU - ROJ COLO-3 Cell- 4 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C3.C4110: FS | MDC1.C3.C4170: FS |  | 0 | 0
MDC1.C4.E1280 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 1 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2021-01-28 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1170: FS |  | 0 | 0
MDC1.C4.E1320 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 3 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 |  |  |  |  | MDC1.C4.C3140: FS | MDC1.C4.C3170: FS |  | 0 | 0
MDC1.C4.E1290 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 2 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C4.C2130: FS | MDC1.C4.C2170: FS |  | 0 | 0
MDC1.C4.E1330 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 4 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 |  |  |  |  | MDC1.C4.C4140: FS | MDC1.C4.C4170: FS |  | 0 | 0
MDC1.C1.E1300 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 1 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 | Start On or After | 2020-10-21 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1230: FS |  | 0 | 0
MDC1.C1.E1410 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 3 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3290: FS |  | 0 | 0
MDC1.C1.E1310 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 2 | 2020-10-21 07:00 |  |  |  | 2020-10-21 07:00 |  | 0 | 0 | 0 | 0 | 57 | 57 | Start On or After | 2020-10-21 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2210: FS |  | 0 | 0
MDC1.C1.E1420 | Not Started | MDC1-BL.4.10.3.2.1 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-1 Cell- 4 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4250: FS |  | 0 | 0
MDC1.C2.E1280 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 1 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1210: FS |  | 0 | 0
MDC1.C2.E1340 | Not Started | MDC1-BL.4.10.2.5.2 | Start Milestone | AHU - ROJ COLO-2 Cell- 3 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C2.C3090: FS, MDC1.C2.C3190: FS | MDC1.C2.C3250: FS |  | 0 | 0
MDC1.C2.E1290 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 2 | 2020-11-20 07:00 |  |  |  | 2020-11-20 07:00 |  | 0 | 0 | 0 | 0 | 66 | 66 | Start On or After | 2020-11-20 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2200: FS |  | 0 | 0
MDC1.C2.E1350 | Not Started | MDC1-BL.4.10.3.2.2 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-2 Cell- 4 | 2020-12-23 07:00 |  |  |  | 2020-12-23 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 | Start On or After | 2020-12-23 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4190: FS |  | 0 | 0
MDC1.C3.E1160 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 1 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 | Start On or After | 2020-11-21 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1140: FS |  | 0 | 0
MDC1.C3.E1320 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 3 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3140: FS |  | 0 | 0
MDC1.C3.E1170 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 2 | 2020-11-21 07:00 |  |  |  | 2020-11-21 07:00 |  | 0 | 0 | 0 | 0 | 97 | 97 | Start On or After | 2020-11-21 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2140: FS |  | 0 | 0
MDC1.C3.E1330 | Not Started | MDC1-BL.4.10.3.2.3 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-3 Cell- 4 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4170: FS |  | 0 | 0
MDC1.C4.E1300 | Not Started | MDC1-BL.4.10.2.5.4 | Start Milestone | AHU - ROJ COLO-4 Cell- 1 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 |  |  |  |  | MDC1.C4.C1130: FS | MDC1.C4.C1170: FS |  | 0 | 0
MDC1.C4.E1340 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 3 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 | Start On or After | 2021-02-26 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3170: FS |  | 0 | 0
MDC1.C4.E1310 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 2 | 2021-01-28 07:00 |  |  |  | 2021-01-28 07:00 |  | 0 | 0 | 0 | 0 | 83 | 83 | Start On or After | 2021-01-28 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2170: FS |  | 0 | 0
MDC1.C4.E1350 | Not Started | MDC1-BL.4.10.3.2.4 | Start Milestone | MDC1 Deliery -AHU - ROJ COLO-4 Cell- 4 | 2021-02-26 07:00 |  |  |  | 2021-02-26 07:00 |  | 0 | 0 | 0 | 0 | 69 | 69 | Start On or After | 2021-02-26 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4170: FS |  | 0 | 0
MDC1.C1.E1000 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-1 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | MDC1.C1.C1010: FS | MDC1.C1.C1040: FS |  | 0 | 0
MDC1.C1.E1010 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-1 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2020-09-03 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1040: FS |  | 0 | 0
MDC1.C1.E1080 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-3 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C1.C3020: FS | MDC1.C1.C3040: FS |  | 0 | 0
MDC1.C1.E1090 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-3 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-09-19 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3040: FS |  | 0 | 0
MDC1.C1.E1020 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-2 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 55 | 55 | Start On or After | 2020-09-03 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2040: FS |  | 0 | 0
MDC1.C1.E1030 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-2 | 2020-09-03 07:00 |  |  |  | 2020-09-03 07:00 |  | 0 | 0 | 0 | 0 | 55 | 55 |  |  |  |  | MDC1.C1.C2010: FS | MDC1.C1.C2040: FS |  | 0 | 0
MDC1.C1.E1100 | Not Started | MDC1-BL.4.10.2.2.1 | Start Milestone | UPM ROJ COLO-1 Cell-4 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 39 | 39 |  |  |  |  | MDC1.C1.C4020: FS | MDC1.C1.C4040: FS |  | 0 | 0
MDC1.C1.E1110 | Not Started | MDC1-BL.4.10.3.3.1 | Start Milestone | MDC1 Deliery -UPM ROJ COLO-1 Cell-4 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 39 | 39 | Start On or After | 2020-09-19 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4040: FS |  | 0 | 0
MDC1.C2.E1000 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-1 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C2.C1020: FS | MDC1.C2.C1030: FS |  | 0 | 0
MDC1.C2.E1010 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-1 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 33 | 33 | Start On or After | 2020-10-05 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1030: FS |  | 0 | 0
MDC1.C2.E1080 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-3 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 |  |  |  |  | MDC1.C2.C3020: FS | MDC1.C2.C3040: FS |  | 0 | 0
MDC1.C2.E1090 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-3 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 | Start On or After | 2020-10-19 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3040: FS |  | 0 | 0
MDC1.C2.E1020 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-2 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 37 | 37 | Start On or After | 2020-10-05 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2020: FS |  | 0 | 0
MDC1.C2.E1030 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-2 | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 37 | 37 |  |  |  |  | MDC1.C2.C2010: FS | MDC1.C2.C2020: FS |  | 0 | 0
MDC1.C2.E1100 | Not Started | MDC1-BL.4.10.2.2.2 | Start Milestone | UPM - ROJ - COLO2- Cell-4 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 |  |  |  |  | MDC1.C2.C4010: FS | MDC1.C2.C4030: FS |  | 0 | 0
MDC1.C2.E1110 | Not Started | MDC1-BL.4.10.3.3.2 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO2- Cell-4 | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 | Start On or After | 2020-10-19 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4030: FS |  | 0 | 0
MDC1.C3.E1000 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-1 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C3.C1020: FS | MDC1.C3.C1040: FS |  | 0 | 0
MDC1.C3.E1010 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-1 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 | Start On or After | 2020-11-03 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1040: FS |  | 0 | 0
MDC1.C3.E1080 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-3 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | MDC1.C3.C3020: FS | MDC1.C3.C3040: FS |  | 0 | 0
MDC1.C3.E1090 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-3 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 1 | 1 | Start On or After | 2020-11-18 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3040: FS |  | 0 | 0
MDC1.C3.E1020 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-2 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 19 | 19 |  |  |  |  | MDC1.C3.C2010: FS | MDC1.C3.C2040: FS |  | 0 | 0
MDC1.C3.E1030 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-2 | 2020-11-03 07:00 |  |  |  | 2020-11-03 07:00 |  | 0 | 0 | 0 | 0 | 19 | 19 | Start On or After | 2020-11-03 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2040: FS |  | 0 | 0
MDC1.C3.E1100 | Not Started | MDC1-BL.4.10.2.2.3 | Start Milestone | UPM - ROJ - COLO3- Cell-4 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 |  |  |  |  | MDC1.C3.C4010: FS | MDC1.C3.C4040: FS |  | 0 | 0
MDC1.C3.E1110 | Not Started | MDC1-BL.4.10.3.3.3 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO3- Cell-4 | 2020-11-18 07:00 |  |  |  | 2020-11-18 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 | Start On or After | 2020-11-18 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4040: FS |  | 0 | 0
MDC1.C4.E1000 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 1 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C4.C1030: FS | MDC1.C4.C1040: FS |  | 0 | 0
MDC1.C4.E1010 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 1 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 | Start On or After | 2020-12-07 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1040: FS |  | 0 | 0
MDC1.C4.E1080 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 3 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.C3030: FS | MDC1.C4.C3040: FS |  | 0 | 0
MDC1.C4.E1090 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 3 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-12-21 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3040: FS |  | 0 | 0
MDC1.C4.E1020 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 2 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 | Start On or After | 2020-12-07 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2040: FS |  | 0 | 0
MDC1.C4.E1030 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 2 | 2020-12-07 07:00 |  |  |  | 2020-12-07 07:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C4.C2030: FS | MDC1.C4.C2040: FS |  | 0 | 0
MDC1.C4.E1100 | Not Started | MDC1-BL.4.10.2.2.4 | Start Milestone | UPM - ROJ - COLO-4 Cell- 4 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.C4030: FS | MDC1.C4.C4040: FS |  | 0 | 0
MDC1.C4.E1110 | Not Started | MDC1-BL.4.10.3.3.4 | Start Milestone | MDC1 Deliery -UPM - ROJ - COLO-4 Cell- 4 | 2020-12-21 07:00 |  |  |  | 2020-12-21 07:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Start On or After | 2020-12-21 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4040: FS |  | 0 | 0
MDC1.C1.E1120 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 1 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 |  |  |  |  | MDC1.C1.C1070: FS | MDC1.C1.C1110: FS |  | 0 | 0
MDC1.C1.E1130 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 1 | 2020-09-19 07:00 |  |  |  | 2020-09-19 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 | Start On or After | 2020-09-19 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1110: FS |  | 0 | 0
MDC1.C1.E1260 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 3 | 2020-10-15 07:00 |  |  |  | 2020-10-15 07:00 |  | 0 | 0 | 0 | 0 | 38 | 38 |  |  |  |  | MDC1.C1.C3100: FS | MDC1.C1.C3130: FS |  | 0 | 0
MDC1.C1.E1270 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 3 | 2020-10-15 07:00 |  |  |  | 2020-10-15 07:00 |  | 0 | 0 | 0 | 0 | 38 | 38 | Start On or After | 2020-10-15 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3130: FS |  | 0 | 0
MDC1.C1.E1160 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 2 | 2020-09-26 07:00 |  |  |  | 2020-09-26 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C1.C2070: FS | MDC1.C1.C2120: FS |  | 0 | 0
MDC1.C1.E1170 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 2 | 2020-09-26 07:00 |  |  |  | 2020-09-26 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 | Start On or After | 2020-09-26 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2120: FS |  | 0 | 0
MDC1.C1.E1240 | Not Started | MDC1-BL.4.10.2.3.1 | Start Milestone | Fluid Cooler - ROJ COLO -1 Cell- 4 | 2020-10-12 07:00 |  |  |  | 2020-10-12 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 |  |  |  |  | MDC1.C1.C4080: FS | MDC1.C1.C4120: FS |  | 0 | 0
MDC1.C1.E1250 | Not Started | MDC1-BL.4.10.3.4.1 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -1 Cell- 4 | 2020-10-12 07:00 |  |  |  | 2020-10-12 07:00 |  | 0 | 0 | 0 | 0 | 48 | 48 | Start On or After | 2020-10-12 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4120: FS |  | 0 | 0
MDC1.C2.E1140 | Not Started | MDC1-BL.4.10.2.3.2 | Start Milestone | Fluid Cooler - ROJ COLO -2 Cell-1 | 2020-10-27 07:00 |  |  |  | 2020-10-27 07:00 |  | 0 | 0 | 0 | 0 | 50 | 50 |  |  |  |  | MDC1.C2.C1070: FS | MDC1.C2.C1120: FS |  | 0 | 0
MDC1.C2.E1150 | Not Started | MDC1-BL.4.10.3.4.2 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -2 Cell-1 | 2020-10-27 07:00 |  |  |  | 2020-10-27 07:00 |  | 0 | 0 | 0 | 0 | 50 | 50 | Start On or After | 2020-10-27 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1120: FS |  | 0 | 0
MDC1.C2.E1220 | Not Started | MDC1-BL.4.10.2.3.2 | Start Milestone | Fluid Cooler - ROJ COLO -2 Cell-3 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.C2.C3070: FS | MDC1.C2.C3120: FS |  | 0 | 0
MDC1.C2.E1230 | Not Started | MDC1-BL.4.10.3.4.2 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -2 Cell-3 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 | Start On or After | 2020-11-10 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3120: FS |  | 0 | 0
MDC1.C2.E1240 | Not Started | MDC1-BL.4.10.2.3.2 | Start Milestone | Fluid Cooler - ROJ COLO -2 Cell-2 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 34 | 34 |  |  |  |  | MDC1.C2.C2110: FS | MDC1.C2.C2170: FS |  | 0 | 0
MDC1.C2.E1250 | Not Started | MDC1-BL.4.10.3.4.2 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -2 Cell-2 | 2020-11-10 07:00 |  |  |  | 2020-11-10 07:00 |  | 0 | 0 | 0 | 0 | 34 | 34 | Start On or After | 2020-11-10 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2170: FS |  | 0 | 0
MDC1.C3.E1180 | Not Started | MDC1-BL.4.10.2.3.3 | Start Milestone | Fluid Cooler - ROJ COLO -3 Cell-1 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 |  |  |  |  | MDC1.C3.C1100: FS | MDC1.C3.C1160: FS |  | 0 | 0
MDC1.C3.E1190 | Not Started | MDC1-BL.4.10.3.4.3 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -3 Cell-1 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 | Start On or After | 2020-11-25 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1160: FS |  | 0 | 0
MDC1.C3.E1200 | Not Started | MDC1-BL.4.10.2.3.3 | Start Milestone | Fluid Cooler - ROJ COLO -3 Cell-2 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 |  |  |  |  | MDC1.C3.C2100: FS | MDC1.C3.C2160: FS |  | 0 | 0
MDC1.C3.E1210 | Not Started | MDC1-BL.4.10.3.4.3 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -3 Cell-2 | 2020-11-25 07:00 |  |  |  | 2020-11-25 07:00 |  | 0 | 0 | 0 | 0 | 54 | 54 | Start On or After | 2020-11-25 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2160: FS |  | 0 | 0
MDC1.C3.E1280 | Not Started | MDC1-BL.4.10.3.4.3 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -3 Cell-4 | 2020-12-14 07:00 |  |  |  | 2020-12-14 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 | Start On or After | 2020-12-14 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4130: FS |  | 0 | 0
MDC1.C3.E1290 | Not Started | MDC1-BL.4.10.2.3.3 | Start Milestone | Fluid Cooler - ROJ COLO -3 Cell-4 | 2020-12-14 07:00 |  |  |  | 2020-12-14 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C3.C4090: FS | MDC1.C3.C4130: FS |  | 0 | 0
MDC1.C4.E1140 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-1 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C1080: FS | MDC1.C4.C1110: FS |  | 0 | 0
MDC1.C4.E1150 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-1 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 | Start On or After | 2021-01-02 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1110: FS |  | 0 | 0
MDC1.C4.E1240 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-3 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 |  |  |  |  | MDC1.C4.C3080: FS | MDC1.C4.C3110: FS |  | 0 | 0
MDC1.C4.E1250 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-3 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 | Start On or After | 2021-01-18 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3110: FS |  | 0 | 0
MDC1.C4.E1160 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-2 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C2080: FS | MDC1.C4.C2110: FS |  | 0 | 0
MDC1.C4.E1170 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-2 | 2021-01-02 07:00 |  |  |  | 2021-01-02 07:00 |  | 0 | 0 | 0 | 0 | 62 | 62 | Start On or After | 2021-01-02 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2110: FS |  | 0 | 0
MDC1.C4.E1260 | Not Started | MDC1-BL.4.10.2.3.4 | Start Milestone | Fluid Cooler - ROJ COLO -4 Cell-4 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 |  |  |  |  | MDC1.C4.C4080: FS | MDC1.C4.C4110: FS |  | 0 | 0
MDC1.C4.E1270 | Not Started | MDC1-BL.4.10.3.4.4 | Start Milestone | MDC1 Deliery -Fluid Cooler - ROJ COLO -4 Cell-4 | 2021-01-18 07:00 |  |  |  | 2021-01-18 07:00 |  | 0 | 0 | 0 | 0 | 75 | 75 | Start On or After | 2021-01-18 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4110: FS |  | 0 | 0
MDC1.C1.E1040 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-1 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C1.C1050: FS | MDC1.C1.C1090: FS |  | 0 | 0
MDC1.C1.E1050 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-1 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 52 | 52 | Start On or After | 2020-09-15 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1090: FS |  | 0 | 0
MDC1.C1.E1180 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-3 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 41 | 41 |  |  |  |  | MDC1.C1.C3050: FS | MDC1.C1.C3080: FS |  | 0 | 0
MDC1.C1.E1190 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-3 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 41 | 41 | Start On or After | 2020-09-29 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3080: FS |  | 0 | 0
MDC1.C1.E1060 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-2 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 |  |  |  |  | MDC1.C1.C2050: FS | MDC1.C1.C2090: FS |  | 0 | 0
MDC1.C1.E1070 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-2 | 2020-09-15 07:00 |  |  |  | 2020-09-15 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 | Start On or After | 2020-09-15 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2090: FS |  | 0 | 0
MDC1.C1.E1200 | Not Started | MDC1-BL.4.10.2.4.1 | Start Milestone | Generator ROJ COLO 1- Cell-4 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 58 | 58 |  |  |  |  | MDC1.C1.C4050: FS | MDC1.C1.C4090: FS |  | 0 | 0
MDC1.C1.E1210 | Not Started | MDC1-BL.4.10.3.5.1 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 1- Cell-4 | 2020-09-29 07:00 |  |  |  | 2020-09-29 07:00 |  | 0 | 0 | 0 | 0 | 58 | 58 | Start On or After | 2020-09-29 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4090: FS |  | 0 | 0
MDC1.C2.E1040 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 1 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 60 | 60 | Start On or After | 2020-10-14 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1080: FS |  | 0 | 0
MDC1.C2.E1050 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 1 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 60 | 60 |  |  |  |  | MDC1.C2.C1040: FS | MDC1.C2.C1080: FS |  | 0 | 0
MDC1.C2.E1160 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 3 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 |  |  |  |  | MDC1.C2.C3050: FS | MDC1.C2.C3080: FS |  | 0 | 0
MDC1.C2.E1170 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 3 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 59 | 59 | Start On or After | 2020-10-29 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3080: FS |  | 0 | 0
MDC1.C2.E1060 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 2 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 56 | 56 |  |  |  |  | MDC1.C2.C2030: FS | MDC1.C2.C2060: FS |  | 0 | 0
MDC1.C2.E1070 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 2 | 2020-10-14 07:00 |  |  |  | 2020-10-14 07:00 |  | 0 | 0 | 0 | 0 | 56 | 56 | Start On or After | 2020-10-14 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2060: FS |  | 0 | 0
MDC1.C2.E1180 | Not Started | MDC1-BL.4.10.2.4.2 | Start Milestone | Generator ROJ COLO 2- Cell - 4 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 |  |  |  |  | MDC1.C2.C4040: FS | MDC1.C2.C4060: FS |  | 0 | 0
MDC1.C2.E1190 | Not Started | MDC1-BL.4.10.3.5.2 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 2- Cell - 4 | 2020-10-29 07:00 |  |  |  | 2020-10-29 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 | Start On or After | 2020-10-29 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4060: FS |  | 0 | 0
MDC1.C3.E1040 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 1 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 |  |  |  |  | MDC1.C3.C1050: FS | MDC1.C3.C1110: FS |  | 0 | 0
MDC1.C3.E1050 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 1 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 | Start On or After | 2020-11-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1110: FS |  | 0 | 0
MDC1.C3.E1220 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 3 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C3.C3050: FS | MDC1.C3.C3080: FS |  | 0 | 0
MDC1.C3.E1230 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 3 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-01 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3080: FS |  | 0 | 0
MDC1.C3.E1060 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 2 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 |  |  |  |  | MDC1.C3.C2050: FS | MDC1.C3.C2110: FS |  | 0 | 0
MDC1.C3.E1070 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 2 | 2020-11-12 07:00 |  |  |  | 2020-11-12 07:00 |  | 0 | 0 | 0 | 0 | 64 | 64 | Start On or After | 2020-11-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2110: FS |  | 0 | 0
MDC1.C3.E1240 | Not Started | MDC1-BL.4.10.2.4.3 | Start Milestone | Generator ROJ COLO 3- Cell - 4 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C3.C4050: FS | MDC1.C3.C4100: FS |  | 0 | 0
MDC1.C3.E1250 | Not Started | MDC1-BL.4.10.3.5.3 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 3- Cell - 4 | 2020-12-01 07:00 |  |  |  | 2020-12-01 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-01 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4100: FS |  | 0 | 0
MDC1.C4.E1180 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 3 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 82 | 82 |  |  |  |  | MDC1.C4.C3060: FS | MDC1.C4.C3100: FS |  | 0 | 0
MDC1.C4.E1190 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 3 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 82 | 82 | Start On or After | 2021-01-05 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3100: FS |  | 0 | 0
MDC1.C4.E1040 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 2 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C4.C2060: FS | MDC1.C4.C2100: FS |  | 0 | 0
MDC1.C4.E1050 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 2 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-16 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2100: FS |  | 0 | 0
MDC1.C4.E1200 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 4 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 84 | 84 |  |  |  |  | MDC1.C4.C4060: FS | MDC1.C4.C4100: FS |  | 0 | 0
MDC1.C4.E1210 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 4 | 2021-01-05 07:00 |  |  |  | 2021-01-05 07:00 |  | 0 | 0 | 0 | 0 | 84 | 84 | Start On or After | 2021-01-05 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4100: FS |  | 0 | 0
MDC1.C4.E1060 | Not Started | MDC1-BL.4.10.2.4.4 | Start Milestone | Generator ROJ COLO 4- Cell - 1 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 |  |  |  |  | MDC1.C4.C1060: FS | MDC1.C4.C1100: FS |  | 0 | 0
MDC1.C4.E1070 | Not Started | MDC1-BL.4.10.3.5.4 | Start Milestone | MDC1 Deliery -Generator ROJ COLO 4- Cell - 1 | 2020-12-16 07:00 |  |  |  | 2020-12-16 07:00 |  | 0 | 0 | 0 | 0 | 72 | 72 | Start On or After | 2020-12-16 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1100: FS |  | 0 | 0
MDC1.C1.E1340 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-1 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 27 | 27 |  |  |  |  | MDC1.C1.C1260: FS | MDC1.C1.C1270: FS |  | 0 | 0
MDC1.C1.E1350 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-1 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 27 | 27 | Start On or After | 2020-11-13 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C1270: FS |  | 0 | 0
MDC1.C1.E1430 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-3 | 2020-11-30 07:00 |  |  |  | 2020-11-30 07:00 |  | 0 | 0 | 0 | 0 | 28 | 28 |  |  |  |  | MDC1.C1.C3220: FS | MDC1.C1.C3240: FS |  | 0 | 0
MDC1.C1.E1440 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-3 | 2020-11-30 07:00 |  |  |  | 2020-11-30 07:00 |  | 0 | 0 | 0 | 0 | 28 | 28 | Start On or After | 2020-11-30 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C3240: FS |  | 0 | 0
MDC1.C1.E1360 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-2 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 32 | 32 |  |  |  |  | MDC1.C1.C2240: FS | MDC1.C1.C2250: FS |  | 0 | 0
MDC1.C1.E1370 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-2 | 2020-11-13 07:00 |  |  |  | 2020-11-13 07:00 |  | 0 | 0 | 0 | 0 | 32 | 32 | Start On or After | 2020-11-13 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C2250: FS |  | 0 | 0
MDC1.C1.E1450 | Not Started | MDC1-BL.4.10.2.6.1 | Start Milestone | PDU ROJ COLO-1 Cell-4 | 2020-12-02 07:00 |  |  |  | 2020-12-02 07:00 |  | 0 | 0 | 0 | 0 | 30 | 30 |  |  |  |  | MDC1.C1.C4210: FS | MDC1.C1.C4220: FS |  | 0 | 0
MDC1.C1.E1460 | Not Started | MDC1-BL.4.10.3.6.1 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-1 Cell-4 | 2020-12-02 07:00 |  |  |  | 2020-12-02 07:00 |  | 0 | 0 | 0 | 0 | 30 | 30 | Start On or After | 2020-12-02 07:00 |  |  | MDC1-2527: FS | MDC1.C1.C4220: FS |  | 0 | 0
MDC1.C2.E1370 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-1 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 31 | 31 |  |  |  |  | MDC1.C2.C1270: FS | MDC1.C2.C1300: FS |  | 0 | 0
MDC1.C2.E1380 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-1 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 31 | 31 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C1300: FS |  | 0 | 0
MDC1.C2.E1420 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-3 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C2.C3260: FS | MDC1.C2.C3290: FS |  | 0 | 0
MDC1.C2.E1430 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-3 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 | Start On or After | 2021-01-13 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C3290: FS |  | 0 | 0
MDC1.C2.E1390 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-2 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 |  |  |  |  | MDC1.C2.C2260: FS | MDC1.C2.C2280: FS |  | 0 | 0
MDC1.C2.E1400 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-2 | 2020-12-28 07:00 |  |  |  | 2020-12-28 07:00 |  | 0 | 0 | 0 | 0 | 25 | 25 | Start On or After | 2020-12-28 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C2280: FS |  | 0 | 0
MDC1.C2.E1440 | Not Started | MDC1-BL.4.10.2.6.2 | Start Milestone | PDU ROJ COLO-2 Cell-4 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C2.C4210: FS | MDC1.C2.C4240: FS |  | 0 | 0
MDC1.C2.E1450 | Not Started | MDC1-BL.4.10.3.6.2 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-2 Cell-4 | 2021-01-13 07:00 |  |  |  | 2021-01-13 07:00 |  | 0 | 0 | 0 | 0 | 13 | 13 | Start On or After | 2021-01-13 07:00 |  |  | MDC1-2527: FS | MDC1.C2.C4240: FS |  | 0 | 0
MDC1.C3.E1380 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-1 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | MDC1.C3.C1350: FS | MDC1.C3.C1390: FS |  | 0 | 0
MDC1.C3.E1390 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-1 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 | Start On or After | 2021-03-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C1390: FS |  | 0 | 0
MDC1.C3.E1420 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-3 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | MDC1.C3.C3310: FS | MDC1.C3.C3340: FS |  | 0 | 0
MDC1.C3.E1430 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-3 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 | Start On or After | 2021-03-27 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C3340: FS |  | 0 | 0
MDC1.C3.E1400 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-2 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  |  | MDC1.C3.C2340: FS | MDC1.C3.C2370: FS |  | 0 | 0
MDC1.C3.E1410 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-2 | 2021-03-12 07:00 |  |  |  | 2021-03-12 07:00 |  | 0 | 0 | 0 | 0 | 4 | 4 | Start On or After | 2021-03-12 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C2370: FS |  | 0 | 0
MDC1.C3.E1440 | Not Started | MDC1-BL.4.10.2.6.3 | Start Milestone | PDU ROJ COLO-3 Cell-4 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | MDC1.C3.C4340: FS | MDC1.C3.C4360: FS |  | 0 | 0
MDC1.C3.E1450 | Not Started | MDC1-BL.4.10.3.6.3 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-3 Cell-4 | 2021-03-27 07:00 |  |  |  | 2021-03-27 07:00 |  | 0 | 0 | 0 | 0 | 2 | 2 | Start On or After | 2021-03-27 07:00 |  |  | MDC1-2527: FS | MDC1.C3.C4360: FS |  | 0 | 0
MDC1.C4.E1400 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-1 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1.C4.C1350: FS | MDC1.C4.C1370: FS |  | 0 | 0
MDC1.C4.E1410 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-1 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2021-04-19 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C1370: FS |  | 0 | 0
MDC1.C4.E1440 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-3 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C4.C3340: FS | MDC1.C4.C3360: FS |  | 0 | 0
MDC1.C4.E1450 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-3 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 | Start On or After | 2021-05-04 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C3360: FS |  | 0 | 0
MDC1.C4.E1420 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-2 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1.C4.C2320: FS | MDC1.C4.C2350: FS |  | 0 | 0
MDC1.C4.E1430 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-2 | 2021-04-19 07:00 |  |  |  | 2021-04-19 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2021-04-19 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C2350: FS |  | 0 | 0
MDC1.C4.E1460 | Not Started | MDC1-BL.4.10.2.6.4 | Start Milestone | PDU ROJ COLO-4 Cell-4 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 |  |  |  |  | MDC1.C4.C4320: FS | MDC1.C4.C4350: FS |  | 0 | 0
MDC1.C4.E1470 | Not Started | MDC1-BL.4.10.3.6.4 | Start Milestone | MDC1 Deliery -PDU ROJ COLO-4 Cell-4 | 2021-05-04 07:00 |  |  |  | 2021-05-04 07:00 |  | 0 | 0 | 0 | 0 | 6 | 6 | Start On or After | 2021-05-04 07:00 |  |  | MDC1-2527: FS | MDC1.C4.C4350: FS |  | 0 | 0
MDC1-2503 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | UMS - ROJ | 2020-11-04 07:00 |  |  |  | 2020-11-04 07:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.S.1370: FS | MDC1.S.1570: FS |  | 0 | 0
MDC1-2504 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | URS - ROJ | 2020-10-19 07:00 |  |  |  | 2020-10-19 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 |  |  |  |  | MDC1.S.1250: FS | MDC1.S.1310: FS |  | 0 | 0
MDC1-2505 | Completed | MDC1-BL.4.10.2.7 | Start Milestone | ATS- ROJ | 2020-06-29 07:00 |  |  |  | 2020-06-29 07:00 |  | 100 | 0 | 0 | 0 | [6 empty] | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0
MDC1-2506 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | MSB - ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0
MDC1-2507 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | TCP - ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0
MDC1-2508 | Not Started | MDC1-BL.4.10.2.7 | Start Milestone | UPS- ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1019: FS |  | 0 | 0
MDC1-2509 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -UMS - ROJ | 2020-10-05 07:00 |  |  |  | 2020-10-05 07:00 |  | 0 | 0 | 0 | 0 | 74 | 74 | Start On or After | 2020-11-04 07:00 |  |  | MDC1-2527: FS | MDC1.S.1570: FS |  | 0 | 0
MDC1-2510 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -URS - ROJ | 2020-09-26 07:00 |  |  |  | 2020-09-26 07:00 |  | 0 | 0 | 0 | 0 | 39 | 39 | Start On or After | 2020-09-26 07:00 |  |  | MDC1-2527: FS | MDC1.S.1310: FS |  | 0 | 0
MDC1-2511 | Completed | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -ATS- ROJ | 2020-06-29 07:00 |  |  |  | 2020-06-29 07:00 |  | 100 | 0 | 0 | 0 |  |  | Start On or After |  |  |  | MDC1-2527: FS, MDC1-2527: SS | MDC1AD-1019: FS |  | 0 | 0
MDC1-2512 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -MSB - ROJ | 2020-10-12 07:00 |  |  |  | 2020-10-12 07:00 |  | 0 | 0 | 0 | 0 | 21 | 21 | Start On or After |  |  |  | MDC1-2527: FS | MDC1AD-1019: FS |  | 0 | 0
MDC1-2513 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -TCP - ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2020-10-28 07:00 |  |  | MDC1-2527: FS | MDC1AD-1019: FS |  | 0 | 0
MDC1-2514 | Not Started | MDC1-BL.4.10.3.7 | Start Milestone | MDC1 Deliery -UPS- ROJ | 2020-10-28 07:00 |  |  |  | 2020-10-28 07:00 |  | 0 | 0 | 0 | 0 | 8 | 8 | Start On or After | 2020-10-28 07:00 |  |  | MDC1-2527: FS | MDC1AD-1019: FS |  | 0 | 0
MDC1.M6010 | Not Started | MDC1-BL.1 | Finish Milestone | Project Completion |  | 2021-10-29 16:00 |  |  | 2021-10-29 16:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C3.Cx4020: FS, MDC1.C2.Cx4020: FS, MDC1.C1.Cx4020: FS, MDC1-C1.P2200: FS, MDC1.C2.Cx4020: FF, MDC1.C3.Cx4020: FF, MDC1-C1.P2200: FF, MDC1-C2.P2200: FS, MDC1-C3.P2200: FS, MDC1-C4.P2200: FS, MDC1.M1010: FS, MDC1.M4010: FS |  |  | 0 | 0
MDC1.C4.Cx4020 | Not Started | MDC1-BL.5.2.12.5 | Task Dependent | Punch List/ Lock down COLO-4 | 2021-10-09 08:00 | 2021-10-29 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 0 | 0 |  |  |  |  | MDC1.C4.Cx4000: FS, MDC1.C4.Cx4000: FF, MDC1-C4.P2100: FS | MDC1-C4.P2200: FS | VECA Electricians | 2240 | 0
MDC1-C4.P2200 | Not Started | MDC1-BL.3.5 | Finish Milestone | Ready for Lock down COLO 4 |  | 2021-10-29 16:00 |  |  | 2021-10-29 16:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.Cx4020: FS, MDC1.C4.Cx4010: FS | MDC1.M6010: FS |  | 0 | 0
MDC1.C4.Cx4000 | Not Started | MDC1-BL.5.2.12.5 | Task Dependent | COLO 4 Level 4 & Level 5 IST | 2021-09-18 08:00 | 2021-10-08 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 0 | 0 |  |  |  |  | MDC1.C4.C4460: FS, MDC1.C4.C2460: FS, MDC1.C4.C3460: FS, MDC1.C4.C1460: FS, MDC1.C4.Cx3040: FS, MDC1.M4010: FS | MDC1.C4.Cx4020: FS, MDC1.C4.Cx4020: FF, MDC1-C4.P2100: FS | VECA Electricians | 2240 | 0
MDC1-C4.P2100 | Not Started | MDC1-BL.3.5 | Finish Milestone | Ready for Network Install |  | 2021-10-08 16:00 |  |  | 2021-10-08 16:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | MDC1.C4.Cx4000: FS | MDC1.C4.Cx4020: FS |  | 0 | 0
MDC1.C4.Cx4010 | Not Started | MDC1-BL.5.2.12.5 | Task Dependent | Security Commissioning | 2021-09-13 08:00 | 2021-09-22 16:00 |  |  |  |  | 0 | 0 | 10 | 10 | 37 | 37 |  |  |  |  | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS | MDC1-C4.P2200: FS | VECA Electricians | 2240 | 0
MDC1.M4010 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 COLO4 - LV3 Cx Complete |  | 2021-09-18 08:00 |  |  | 2021-09-18 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-09-17 17:00 |  |  | MDC1.S.1910: FS, MDC1.C4.Cx3040: FS, MDC1.C4.Cx3050: FS, MDC1-C4.P1900: FS, MDC1-1958: FS, MDC1-C4.P1900: FF | MDC1.C4.Cx4000: FS, MDC1.M6010: FS |  | 0 | 0
MDC1-1958 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 COLO4 - Fitout Summary | 2020-11-12 07:00 | 2021-09-18 08:00 |  |  |  |  | 0 | 0 | 241 | 241 | 0 | 0 |  |  |  |  | MDC1.C4.C1020: SS | MDC1.M4010: FS |  | 0 | 0
MDC1.C4.Cx3050 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Weather (5 Days) | 2021-09-13 08:00 | 2021-09-18 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C4.Cx3040: FS | MDC1.M4010: FS |  | 0 | 0
MDC1.C3.Cx4020 | Not Started | MDC1-BL.5.2.1.5 | Task Dependent | Punch List/ Lock down COLO-3 | 2021-08-28 08:00 | 2021-09-17 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 42 | 42 |  |  |  |  | MDC1.C3.Cx4000: FS, MDC1-C3.P2100: FS | MDC1.M6010: FS, MDC1.M6010: FF, MDC1-C3.P2200: FS | VECA Electricians | 2240 | 0
MDC1-C3.P2200 | Not Started | MDC1-BL.3.4 | Finish Milestone | Ready for Lock down COLO-3 |  | 2021-09-17 16:00 |  |  | 2021-09-17 16:00 |  | 0 | 0 | 0 | 0 | 42 | 42 |  |  |  |  | MDC1.C3.Cx4020: FS, MDC1.C3.Cx4010: FS | MDC1.M6010: FS |  | 0 | 0
MDC1.C4.Cx3040 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Level 3 Cx - COLO-4 | 2021-08-27 08:00 | 2021-09-13 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx3030: FS, MDC1.C4.Cx2060: FS, MDC1.C4.Cx2140: FS, MDC1.C4.Cx2100: FS, MDC1.C4.Cx3020: FF 10 | MDC1.C4.Cx4000: FS, MDC1.M4010: FS, MDC1.C4.Cx3050: FS, MDC1.C4.Cx4010: FS | VECA Electricians | 1200 | 0
MDC1.C3.Cx4000 | Not Started | MDC1-BL.5.2.1.5 | Task Dependent | COLO 3 Level 4 & Level 5 IST | 2021-08-07 08:00 | 2021-08-27 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 42 | 42 |  |  |  |  | MDC1.C3.C4460: FS, MDC1.C3.C2460: FS, MDC1.C3.C3420: FS, MDC1.C3.C1460: FS, MDC1.C3.Cx3040: FS, MDC1.M3010: FS | MDC1.C3.Cx4020: FS, MDC1-C3.P2100: FS | VECA Electricians | 2240 | 0
MDC1-C3.P2100 | Not Started | MDC1-BL.3.4 | Finish Milestone | Ready for Network Install |  | 2021-08-27 16:00 |  |  | 2021-08-27 16:00 |  | 0 | 0 | 0 | 0 | 33 | 33 |  |  |  |  | MDC1.C3.Cx4000: FS | MDC1.C3.Cx4020: FS |  | 0 | 0
MDC1.C4.Cx3030 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Load Bank & IR Scan | 2021-08-05 08:00 | 2021-08-27 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2170: FS, MDC1.C4.Cx2100: FS, MDC1.C4.Cx2140: FS, MDC1.C4.Cx2060: FS, MDC1.C4.Cx3010: FS, MDC1.C3.Cx3030: FS 15 | MDC1.C4.Cx3040: FS, MDC1.C4.Cx4010: FS | VECA Electricians | 3600 | 0
MDC1.C4.Cx3020 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-07-21 07:00 | 2021-08-13 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C4.Cx2090: FS, MDC1.C4.Cx2160: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2190: FS, MDC1.C3.Cx3020: FS, MDC1.C4.C1160: FS, MDC1.C4.C3160: FS, MDC1.C4.C2160: FS, MDC1.C4.C4160: FS, MDC1-C4.P2000: FS | MDC1.C4.Cx3040: FF 10 | LINX- TELECOM | 2000 | 0
MDC1.C3.Cx4010 | Not Started | MDC1-BL.5.2.1.5 | Task Dependent | Security Commissioning | 2021-08-02 08:00 | 2021-08-11 16:00 |  |  |  |  | 0 | 0 | 10 | 10 | 79 | 79 |  |  |  |  | MDC1.C3.Cx3040: FS | MDC1-C3.P2200: FS | VECA Electricians | 2240 | 0
MDC1.M3010 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 COLO3 - LV3 Cx Complete |  | 2021-08-07 08:00 |  |  | 2021-08-07 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-08-06 17:00 |  |  | MDC1.C3.Cx3040: FS, MDC1.C3.Cx2060: FS, MDC1.C3.Cx2140: FS, MDC1.C3.Cx2090: FS, MDC1.C3.Cx3050: FS, MDC1-C2.P1900: FS, MDC1-1957: FS, MDC1-C3.P1900: FS | MDC1.C3.Cx4000: FS |  | 0 | 0
MDC1-1957 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 COLO3 - Fitout Summary | 2020-10-14 07:00 | 2021-08-07 08:00 |  |  |  |  | 0 | 0 | 232 | 232 | 0 | 0 |  |  |  |  | MDC1.C3.C1010: SS | MDC1.M3010: FS |  | 0 | 0
MDC1.C3.Cx3050 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Weather (5 days) | 2021-08-02 08:00 | 2021-08-07 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C3.Cx3040: FS | MDC1.M3010: FS |  | 0 | 0
MDC1.C2.Cx4020 | Not Started | MDC1-BL.5.2.2.5 | Task Dependent | Punch List/ Lock down COLO-2 | 2021-07-17 08:00 | 2021-08-06 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 84 | 84 |  |  |  |  | MDC1.C2.Cx4010: FS, MDC1.C2.Cx4010: FF, MDC1-C2.P2100: FS | MDC1.M6010: FS, MDC1.M6010: FF, MDC1-C2.P2200: FS | VECA Electricians | 2240 | 0
MDC1-C2.P2200 | Not Started | MDC1-BL.3.3 | Finish Milestone | Ready for Lock down COLO-2 |  | 2021-08-06 16:00 |  |  | 2021-08-06 16:00 |  | 0 | 0 | 0 | 0 | 84 | 84 |  |  |  |  | MDC1.C2.Cx4020: FS, MDC1.C2.Cx4000: FS | MDC1.M6010: FS |  | 0 | 0
MDC1.C4.Cx3010 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Cooling Automation | 2021-07-21 07:00 | 2021-08-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx3000: FS, MDC1.C4.Cx2070: FS, MDC1.C4.Cx2090: FS, MDC1.C4.Cx2150: FS, MDC1.C4.Cx2160: FS, MDC1.C4.Cx2120: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2180: FS, MDC1.C4.Cx2190: FS, MDC1.C3.Cx3010: FS | MDC1.C4.Cx3030: FS | TCM | 1200 | 0
MDC1.C3.Cx3040 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Level 3 Cx- COLO-3 | 2021-07-17 08:00 | 2021-08-02 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.Cx3030: FS, MDC1.C3.Cx2060: FS, MDC1.C3.Cx2140: FS, MDC1.C3.Cx2090: FS, MDC1.C3.Cx3020: FF 10 | MDC1.C3.Cx4000: FS, MDC1.M3010: FS, MDC1.C3.Cx3050: FS, MDC1.C3.Cx4010: FS | VECA Electricians | 1200 | 0
MDC1.C4.Cx3000 | Not Started | MDC1-BL.5.2.12.6 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-07-07 07:00 | 2021-07-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2070: SS 10, MDC1.C4.Cx2150: SS 10, MDC1.C4.Cx2120: SS 10, MDC1.C4.Cx2180: SS 10, MDC1.C3.Cx3000: FS | MDC1.C4.Cx3010: FS | TCM | 1200 | 0
MDC1.C4.Cx2190 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-07-07 07:00 | 2021-07-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2110: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0
MDC1-C4.P2000 | Not Started | MDC1-BL.3.5 | Finish Milestone | Construction Server- COLO-4 |  | 2021-07-20 17:00 |  |  | 2021-07-20 17:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C4.Cx2090: FS, MDC1.C4.Cx2160: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2190: FS | MDC1.C4.Cx3020: FS |  | 0 | 0
MDC1-C1.P2200 | Not Started | MDC1-BL.3.2 | Finish Milestone | Ready for Lock down COLO-1 |  | 2021-07-18 08:00 |  |  | 2021-07-18 08:00 |  | 0 | 0 | 0 | 0 | 104 | 104 |  |  |  |  | MDC1.C1.Cx4000: FS, MDC1.S.1910: FS, MDC1.C1.Cx4020: FS, MDC1.C1.Cx4010: FS | MDC1.M6010: FS, MDC1.M6010: FF |  | 0 | 0
MDC1.S.1900 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Site Lighting | 2021-05-15 07:00 | 2021-07-17 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 49 | 49 |  |  |  |  | MDC1.C3.C4290: FS, MDC1.C2.C4250: FS, MDC1.C1.C4280: FS, MDC1.S.1040: FS, MDC1.S.1300: FS, MDC1.S.1870: FS, MDC1.C4.CS1050: FS, MDC1.C4.CS1060: FS | MDC1.S.1910: FS | VECA Electricians | 4000 | 0
MDC1.C4.Cx2170 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-07-07 07:00 | 2021-07-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C4.Cx2110: FS, MDC1.C4.Cx2100: FS | MDC1.C4.Cx3030: FS | LINX- TELECOM | 1200 | 0
MDC1.C4.Cx2180 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-23 07:00 | 2021-07-17 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C4.Cx2050: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.S.1910 | Not Started | MDC1-BL.5.1.4 | Finish Milestone | Site Work Complete |  | 2021-07-17 17:00 |  |  | 2021-07-17 17:00 |  | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | MDC1.S.1900: FS, MDC1.S.1160: FS, MDC1.S.1890: FS, MDC1.S.1120: FS, MDC1.S.1880: FS | MDC1.M4010: FS, MDC1-C1.P2200: FS |  | 0 | 0
MDC1.C3.Cx3030 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Load Bank & IR Scan | 2021-06-24 08:00 | 2021-07-17 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2150: FS, MDC1.C3.Cx2090: FS, MDC1.C3.Cx2140: FS, MDC1.C3.Cx2060: FS, MDC1.C2.Cx3030: FS 15, MDC1.C3.Cx3010: FS | MDC1.C3.Cx3040: FS, MDC1.C4.Cx3030: FS 15 | VECA Electricians | 3600 | 0
MDC1.C4.Cx2160 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-07-01 07:00 | 2021-07-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.Cx2080: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0
MDC1.C2.Cx4010 | Not Started | MDC1-BL.5.2.2.5 | Task Dependent | COLO 2 Level 4 & Level 5 IST (NIC) | 2021-06-26 08:00 | 2021-07-16 16:00 |  |  |  |  | 0 | 0 | 21 | 21 | 84 | 84 |  |  |  |  | MDC1.C2.C4420: FS, MDC1.C2.C2450: FS, MDC1.C2.C3460: FS, MDC1.C2.C1440: FS, MDC1.C1.C3460: FS, MDC1.C1.C2440: FS, MDC1.C1.C4460: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS | MDC1.C2.Cx4020: FS, MDC1.C2.Cx4020: FF, MDC1-C2.P2100: FS | VECA Electricians | 2240 | 0
MDC1-C2.P2100 | Not Started | MDC1-BL.3.3 | Finish Milestone | Ready for Network Install |  | 2021-07-16 16:00 |  |  | 2021-07-16 16:00 |  | 0 | 0 | 0 | 0 | 67 | 67 |  |  |  |  | MDC1.C2.Cx4010: FS | MDC1.C2.Cx4020: FS |  | 0 | 0
MDC1.C4.Cx2140 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-07-01 07:00 | 2021-07-14 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 17 | 17 |  |  |  |  | MDC1.C4.Cx2080: FS, MDC1.C4.Cx2060: FS | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS | LINX- TELECOM | 1200 | 0
MDC1.C4.Cx2150 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-19 07:00 | 2021-07-14 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C4.Cx2030: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C1.Cx4020 | Not Started | MDC1-BL.5.2.3.5 | Task Dependent | Punch List/ Lockdown- Admin/COLO 1 | 2021-06-12 08:00 | 2021-07-10 17:00 |  |  |  |  | 0 | 0 | 28 | 28 | 111 | 111 |  |  |  |  | MDC1.C1.Cx4000: FS, MDC1.C1.Cx3040: FS, MDC1-C4.P1900: FS, MDC1-C3.P1900: FS, MDC1-C2.P1800: FS, MDC1.C1.C4400: FS, MDC1-C1.P2100: FS | MDC1.M6010: FS, MDC1-C1.P2200: FS |  | 0 | 0
MDC1.C4.Cx2130 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-06-23 07:00 | 2021-07-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C4.Cx2040: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0
MDC1.C4.C3460 | Not Started | MDC1-BL.5.3.6.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-06-14 07:00 | 2021-07-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C4.C1460: FS, MDC1.C4.C3400: FS | MDC1.C4.Cx4000: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C4460 | Not Started | MDC1-BL.5.3.6.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-06-14 07:00 | 2021-07-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C4.C2460: FS, MDC1.C4.C4400: FS | MDC1.C4.Cx4000: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.Cx2100 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-06-23 07:00 | 2021-07-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C4.Cx2040: FS | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS, MDC1.C4.Cx2170: FS | LINX- TELECOM | 1200 | 0
MDC1.C4.Cx2110 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | Network Startup | 2021-06-23 07:00 | 2021-07-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4400: FS, MDC1.C4.Cx2050: FS, MDC1.C4.Cx2040: FS | MDC1.C4.Cx2170: FS, MDC1.C4.Cx2190: FS | LINX- TELECOM | 600 | 0
MDC1.C4.Cx2120 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-10 07:00 | 2021-07-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C4.Cx2010: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C2.Cx4000 | Not Started | MDC1-BL.5.2.2.5 | Task Dependent | Security Commissioning | 2021-06-21 08:00 | 2021-07-02 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 95 | 95 |  |  |  |  | MDC1.C2.Cx3040: FS | MDC1-C2.P2200: FS |  | 0 | 0
MDC1.C3.Cx3020 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-06-08 07:00 | 2021-07-01 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 13 | 13 |  |  |  |  | MDC1.C3.Cx2110: FS, MDC1.C3.Cx2180: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2190: FS, MDC1.C2.Cx3020: FS, MDC1.C3.C1130: FS, MDC1.C3.C3130: FS, MDC1.C3.C2130: FS, MDC1.C3.C4160: FS, MDC1-C3.P2000: FS | MDC1.C3.Cx3040: FF 10, MDC1.C4.Cx3020: FS | LINX- TELECOM | 2000 | 0
MDC1.C4.Cx2080 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | Network Startup | 2021-06-19 07:00 | 2021-06-30 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C3400: FS, MDC1.C4.Cx2030: FS, MDC1.C4.Cx2020: FS | MDC1.C4.Cx2140: FS, MDC1.C4.Cx2160: FS | LINX- TELECOM | 600 | 0
MDC1.C4.Cx2090 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-06-17 07:00 | 2021-06-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 15 | 15 |  |  |  |  | MDC1.C4.Cx2020: FS | MDC1.C4.Cx3010: FS, MDC1.C4.Cx3020: FS, MDC1-C4.P2000: FS | TCM | 640 | 0
MDC1.C4.Cx2060 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-06-17 07:00 | 2021-06-28 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 19 | 19 |  |  |  |  | MDC1.C4.Cx2020: FS | MDC1.C4.Cx3030: FS, MDC1.C4.Cx3040: FS, MDC1.C4.Cx2140: FS | LINX- TELECOM | 1200 | 0
MDC1.C4.Cx2070 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-06-04 07:00 | 2021-06-28 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 15 | 15 |  |  |  |  | MDC1.C4.Cx2000: FS | MDC1.C4.Cx3000: SS 10, MDC1.C4.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.M2010 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 COLO2 - LV3 Cx Complete |  | 2021-06-26 08:00 |  |  | 2021-06-26 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-06-25 17:00 |  |  | MDC1.C2.Cx3040: FS, MDC1.C2.Cx2060: FS, MDC1.C2.Cx2160: FS, MDC1.C2.Cx2090: FS, MDC1.C2.C3150: FS, MDC1.C1.Cx3040: FS, MDC1.C2.Cx3050: FS, MDC1-1956: FS | MDC1.C2.Cx4010: FS |  | 0 | 0
MDC1-1956 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 COLO2 - Fitout Summary | 2020-09-15 07:00 | 2021-06-26 08:00 |  |  |  |  | 0 | 0 | 223 | 223 | 0 | 0 |  |  |  |  | MDC1.C2.C1010: SS | MDC1.M2010: FS |  | 0 | 0
MDC1.C2.Cx3050 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Weather (5 days) | 2021-06-21 08:00 | 2021-06-26 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.Cx3040: FS | MDC1.M2010: FS |  | 0 | 0
MDC1.C3.Cx3010 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Cooling Automation | 2021-06-09 07:00 | 2021-06-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.Cx3000: FS, MDC1.C3.Cx2070: FS, MDC1.C3.Cx2110: FS, MDC1.C3.Cx2160: FS, MDC1.C3.Cx2180: FS, MDC1.C3.Cx2120: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2170: FS, MDC1.C3.Cx2190: FS, MDC1.C2.Cx3010: FS | MDC1.C3.Cx3030: FS, MDC1.C4.Cx3010: FS | TCM | 1200 | 0
MDC1.C4.Cx2040 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | Network Startup | 2021-06-10 07:00 | 2021-06-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2390: FS, MDC1.C4.Cx2010: FS | MDC1.C4.Cx2100: FS, MDC1.C4.Cx2130: FS, MDC1.C4.Cx2110: FS | LINX- TELECOM | 600 | 0
MDC1.C4.Cx2050 | Not Started | MDC1-BL.5.2.12.7.4 | Task Dependent | Equipment Yellow Tagging | 2021-06-10 07:00 | 2021-06-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4200: FF, MDC1.C4.C4420: FS, MDC1.C4.C4400: FS, MDC1.C4.C4430: FS, MDC1.C4.C4410: FS, MDC1.C4.C4240: FS, MDC1.C4.C4370: FS, MDC1.C4.C4440: FS, MDC1.C4.C4120: FS, MDC1.C4.Cx2010: FS, MDC1-C4.P1800: FS | MDC1.C4.Cx2110: FS, MDC1.C4.Cx2180: FS | VECA Electricians | 1200 | 0
MDC1.C2.Cx3040 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Level 3 Cx- COLO-2 | 2021-06-05 08:00 | 2021-06-21 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx3030: FS, MDC1.C2.Cx2060: FS, MDC1.C2.Cx2160: FS, MDC1.C2.Cx2090: FS, MDC1.C2.C3150: FS, MDC1.C2.Cx3020: FF 10 | MDC1.C2.Cx4010: FS, MDC1.M2010: FS, MDC1.C2.Cx3050: FS, MDC1.C2.Cx4000: FS | VECA Electricians | 1200 | 0
MDC1.C4.Cx2030 | Not Started | MDC1-BL.5.2.12.7.2 | Task Dependent | Equipment Yellow Tagging | 2021-06-07 07:00 | 2021-06-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C3390: FS, MDC1.C4.C3200: FF, MDC1.C4.C3420: FS, MDC1.C4.C3400: FS, MDC1.C4.C3430: FS, MDC1.C4.C3410: FS, MDC1.C4.C3250: FS, MDC1.C4.C3380: FS, MDC1.C4.C3440: FS, MDC1.C4.C3120: FS, MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | MDC1.C4.Cx2080: FS, MDC1.C4.Cx2150: FS | VECA Electricians | 1200 | 0
MDC1.S.1890 | Not Started | MDC1-BL.5.1.5 | Task Dependent | Landscape and Site Specialties | 2021-04-16 07:00 | 2021-06-17 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 73 | 73 |  |  |  |  | MDC1.S.1880: FF 6 | MDC1.S.1910: FS | Advantage | 2500 | 0
MDC1.C4.Cx2020 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | Network Startup | 2021-06-04 07:00 | 2021-06-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 5 | 5 |  |  |  |  | MDC1.C4.C1400: FS, MDC1.C4.Cx2000: FS | MDC1.C4.Cx2060: FS, MDC1.C4.Cx2090: FS, MDC1.C4.Cx2080: FS | LINX- TELECOM | 600 | 0
MDC1.C4.C3450 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-06-05 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 77 | 77 |  |  |  |  | MDC1.C4.C3420: FS, MDC1.C4.C3430: FS, MDC1.C4.C3360: FS | MDC1-C4.P1900: FS, MDC1-C4.P1900: SS | VECA Electricians | 480 | 0
MDC1.C4.C4450 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-06-05 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 77 | 77 |  |  |  |  | MDC1.C4.C4430: FS, MDC1.C4.C4350: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0
MDC1-C4.P1900 | Not Started | MDC1-BL.3.5 | Finish Milestone | COLO 4 CSA complete |  | 2021-06-11 17:00 |  |  | 2021-06-11 17:00 |  | 0 | 0 | 0 | 0 | 77 | 77 |  |  |  |  | MDC1.C4.C3220: FS, MDC1.C4.C1260: FS, MDC1.C4.C2250: FS, MDC1.C4.C1200: FS, MDC1.C4.C1300: FS, MDC1.C4.C1240: FS, MDC1.C4.C1250: FS, MDC1.C4.C3280: FS, MDC1.C4.C3290: FS, MDC1.C4.C3300: FS, MDC1.C4.C2370: FS, MDC1.C4.C2230: FS, MDC1.C4.C2240: FS, MDC1.C4.C4380: FS, MDC1.C4.C4270: FS, MDC1.C4.C4330: FS, MDC1.C4.C3450: FS, MDC1.C4.C2450: FS, MDC1.C4.C4450: FS, MDC1.C4.C1450: FS, MDC1.C4.C3450: SS, MDC1.C4.C2450: SS | MDC1.C1.Cx4020: FS, MDC1.M4010: FS, MDC1.M4010: FF |  | 0 | 0
MDC1.C4.C1460 | Not Started | MDC1-BL.5.3.6.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-05-18 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C3420: FS, MDC1.C4.C1400: FS | MDC1.C4.Cx4000: FS, MDC1.C4.C3460: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C2460 | Not Started | MDC1-BL.5.3.6.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-05-18 07:00 | 2021-06-11 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C4460: FS, MDC1.C4.C2390: FS | MDC1.C4.Cx4000: FS, MDC1.C4.C4460: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.Cx4000 | Not Started | MDC1-BL.5.2.3.5 | Task Dependent | COLO 1 Level 4 & Level 5 IST | 2021-05-15 08:00 | 2021-06-11 16:00 |  |  |  |  | 0 | 0 | 28 | 28 | 0 | 0 | Finish On or Before | 2021-06-11 16:00 |  |  | MDC1.C1.C4460: FS, MDC1.C1.C2440: FS, MDC1.C1.C3460: FS, MDC1.C1.C1430: FS, MDC1.S.1830: FS, MDC1.M1010: FS | MDC1.C1.Cx4020: FS, MDC1-C1.P2200: FS, MDC1-C1.P2100: FS | VECA Electricians | 2240 | 0
MDC1-C1.P2100 | Not Started | MDC1-BL.3.2 | Finish Milestone | Ready for Network Install |  | 2021-06-11 16:00 |  |  | 2021-06-11 16:00 |  | 0 | 0 | 0 | 0 | 88 | 88 |  |  |  |  | MDC1.C1.Cx4000: FS | MDC1.C1.Cx4020: FS |  | 0 | 0
MDC1.S.1880 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Pave HMA | 2021-05-15 07:00 | 2021-06-09 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 73 | 73 |  |  |  |  | MDC1.S.1870: FS, MDC1.S.1300: FS, MDC1.S.1860: FS, MDC1.S.1860: FF | MDC1.S.1890: FF 6, MDC1.S.1910: FS | Advantage | 2000 | 0
MDC1.C4.Cx2010 | Not Started | MDC1-BL.5.2.12.7.3 | Task Dependent | Equipment Yellow Tagging | 2021-05-28 07:00 | 2021-06-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2180: FF, MDC1.C4.C2410: FS, MDC1.C4.C2390: FS, MDC1.C4.C2420: FS, MDC1.C4.C2430: FS, MDC1.C4.C2210: FS, MDC1.C4.C2380: FS, MDC1.C4.C2440: FS, MDC1.C4.C2120: FS, MDC1-C4.P1800: FS | MDC1.C4.Cx2040: FS, MDC1.C4.Cx2120: FS, MDC1.C4.Cx2050: FS | VECA Electricians | 1200 | 0
MDC1.C4.C4440 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-05-18 07:00 | 2021-06-09 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C4.C4100: FS, MDC1.C4.C4370: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 1440 | 0
MDC1.C3.Cx3000 | Not Started | MDC1-BL.5.2.1.6 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-05-25 07:00 | 2021-06-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2070: SS 11, MDC1.C3.Cx2160: SS 11, MDC1.C3.Cx2120: SS 11, MDC1.C3.Cx2170: SS 11, MDC1.C2.Cx3000: FS 11 | MDC1.C3.Cx3010: FS, MDC1.C4.Cx3000: FS | TCM | 1200 | 0
MDC1.C3.Cx2180 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-24 07:00 | 2021-06-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 1 | 1 |  |  |  |  | MDC1.C3.Cx2080: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0
MDC1.C3.Cx2190 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-24 07:00 | 2021-06-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 1 | 1 |  |  |  |  | MDC1.C3.Cx2100: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0
MDC1-C3.P2000 | Not Started | MDC1-BL.3.4 | Finish Milestone | Construction Server- COLO-3 |  | 2021-06-07 17:00 |  |  | 2021-06-07 17:00 |  | 0 | 0 | 0 | 0 | 13 | 13 |  |  |  |  | MDC1.C3.Cx2190: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2180: FS, MDC1.C3.Cx2110: FS | MDC1.C3.Cx3020: FS |  | 0 | 0
MDC1.C4.C3440 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-05-12 07:00 | 2021-06-05 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C4.C3100: FS, MDC1.C4.C3380: FS | MDC1.C4.Cx2030: FS | VECA Electricians | 1440 | 0
MDC1.C2.Cx3030 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Load Bank & IR Scan | 2021-05-13 08:00 | 2021-06-05 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2140: FS, MDC1.C2.Cx2060: FS, MDC1.C2.Cx2160: FS, MDC1.C2.Cx2090: FS, MDC1.C2.C3150: FS, MDC1.C2.Cx3010: FS, MDC1.C1.Cx3030: FS 15, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.Cx3040: FS, MDC1.C3.Cx3030: FS 15 | VECA Electricians | 3600 | 0
MDC1.C3.Cx2140 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-24 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 15 | 15 |  |  |  |  | MDC1.C3.Cx2080: FS, MDC1.C3.Cx2060: FS | MDC1.M3010: FS, MDC1.C3.Cx3030: FS, MDC1.C3.Cx3040: FS | LINX- TELECOM | 1200 | 0
MDC1.C3.Cx2150 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-24 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 15 | 15 |  |  |  |  | MDC1.C3.Cx2100: FS, MDC1.C3.Cx2090: FS | MDC1.C3.Cx3030: FS | LINX- TELECOM | 1200 | 0
MDC1.C4.C3430 | Not Started | MDC1-BL.5.3.6.4.10.3 | Task Dependent | Controls Installation | 2021-05-20 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C3310: FS, MDC1.C4.C3330: FS, MDC1.C4.C3400: FS | MDC1.C4.C3450: FS, MDC1.C4.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C4.C4430 | Not Started | MDC1-BL.5.3.6.4.13.3 | Task Dependent | Controls Installation | 2021-05-20 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4280: FS, MDC1.C4.C4300: FS, MDC1.C4.C4400: FS | MDC1.C4.C4450: FS, MDC1.C4.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.C3.Cx2160 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-05-11 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2030: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C3.Cx2170 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-05-11 07:00 | 2021-06-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C3.Cx2050: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C4.Cx2000 | Not Started | MDC1-BL.5.2.12.7.1 | Task Dependent | Equipment Yellow Tagging | 2021-05-21 07:00 | 2021-06-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 5 | 5 |  |  |  |  | MDC1.C4.C1180: FF, MDC1.C4.C1420: FS, MDC1.C4.C1400: FS, MDC1.C4.C1430: FS, MDC1.C4.C1410: FS, MDC1.C4.C1210: FS, MDC1.C4.C1380: FS, MDC1.C4.C1440: FS, MDC1.C4.C1120: FS | MDC1.C4.Cx2020: FS, MDC1-C4.P1800: SS, MDC1.C4.Cx2070: FS, MDC1.C4.Cx2030: FS | VECA Electricians | 1200 | 0
MDC1.C4.C3420 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2021-05-07 07:00 | 2021-06-02 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 6 | 6 |  |  |  |  | MDC1.C4.C3360: FS | MDC1.C4.C3450: FS, MDC1.C4.Cx2030: FS | VECA Electricians | 1680 | 0
MDC1.C4.C4420 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2021-05-07 07:00 | 2021-06-02 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 6 | 6 |  |  |  |  | MDC1.C4.C4350: FS, MDC1.C4.C4280: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 1680 | 0
MDC1.C4.C4410 | Not Started | MDC1-BL.5.3.6.4.4.4 | Task Dependent | Controls Installation | 2021-05-15 07:00 | 2021-05-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C4.C4100: FS, MDC1.C4.C4110: FS, MDC1.C4.C4360: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.C4.C1450 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-05-20 07:00 | 2021-05-27 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 89 | 89 |  |  |  |  | MDC1.C4.C1420: FS, MDC1.C4.C1430: FS, MDC1.C4.C1370: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0
MDC1.C4.C2440 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-05-05 07:00 | 2021-05-27 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C4.C2100: FS, MDC1.C4.C2380: FS | MDC1.C4.Cx2010: FS | VECA Electricians | 1440 | 0
MDC1.C4.C2450 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Light Fixtures Installation | 2021-05-20 07:00 | 2021-05-27 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 89 | 89 |  |  |  |  | MDC1.C4.C2410: FS, MDC1.C4.C2420: FS, MDC1.C4.C2350: FS | MDC1-C4.P1900: FS, MDC1-C4.P1900: SS | VECA Electricians | 480 | 0
MDC1.C3.Cx2130 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-11 07:00 | 2021-05-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C3.Cx2040: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0
MDC1.C4.C2430 | Not Started | MDC1-BL.5.3.6.4.3.4 | Task Dependent | Controls Installation | 2021-05-10 07:00 | 2021-05-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C2100: FS, MDC1.C4.C2110: FS, MDC1.C4.C2400: FS | MDC1.C4.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C2.Cx3020 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-04-28 08:00 | 2021-05-24 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C2.Cx2130: FS, MDC1.C2.Cx2190: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2180: FS, MDC1.C1.Cx3020: FS, MDC1.C2.C1150: FS, MDC1.C2.C3140: FS, MDC1.C2.C2130: FS, MDC1.C2.C4120: FS, MDC1-C2.P2000: FS | MDC1.C2.Cx3040: FF 10, MDC1.C3.Cx3020: FS | LINX- TELECOM | 2000 | 0
MDC1.C3.Cx2080 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | Network Startup | 2021-05-11 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.C3.C3360: FS, MDC1.C3.Cx2030: FS, MDC1.C3.Cx2020: FS | MDC1.C3.Cx2140: FS, MDC1.C3.Cx2180: FS | LINX- TELECOM | 600 | 0
MDC1.C3.Cx2090 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-11 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 15 | 15 |  |  |  |  | MDC1.C3.Cx2040: FS | MDC1.C3.Cx3030: FS, MDC1.C3.Cx3040: FS, MDC1.M3010: FS, MDC1.C3.Cx2150: FS | LINX- TELECOM | 1200 | 0
MDC1.C3.Cx2100 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | Network Startup | 2021-05-11 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.C3.C4390: FS, MDC1.C3.Cx2050: FS, MDC1.C3.Cx2040: FS | MDC1.C3.Cx2150: FS, MDC1.C3.Cx2190: FS | LINX- TELECOM | 600 | 0
MDC1.C4.C3410 | Not Started | MDC1-BL.5.3.6.4.2.4 | Task Dependent | Controls Installation | 2021-05-08 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C4.C3100: FS, MDC1.C4.C3110: FS, MDC1.C4.C3370: FS | MDC1.C4.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C3.Cx2110 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-05-08 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 13 | 13 |  |  |  |  | MDC1.C3.Cx2020: FS | MDC1.C3.Cx3010: FS, MDC1.C3.Cx3020: FS, MDC1-C3.P2000: FS | TCM | 640 | 0
MDC1.C3.Cx2120 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-28 07:00 | 2021-05-21 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C3.Cx2010: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C4.C1440 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Pull Conductors into Building | 2021-04-27 07:00 | 2021-05-20 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C4.C1100: FS, MDC1.C4.C1380: FS | MDC1.C4.Cx2000: FS | VECA Electricians | 1440 | 0
MDC1.C3.Cx2060 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-05-08 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 17 | 17 |  |  |  |  | MDC1.C3.Cx2020: FS | MDC1.M3010: FS, MDC1.C3.Cx3030: FS, MDC1.C3.Cx3040: FS, MDC1.C3.Cx2140: FS | LINX- TELECOM | 1200 | 0
MDC1.C4.C1430 | Not Started | MDC1-BL.5.3.6.4.9.3 | Task Dependent | Controls Installation | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C1310: FS, MDC1.C4.C1330: FS, MDC1.C4.C1400: FS | MDC1.C4.C1450: FS, MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | VECA Electricians | 720 | 0
MDC1.C4.C3400 | Not Started | MDC1-BL.5.3.6.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C3350: FS | MDC1.C4.C3460: FS, MDC1.C4.Cx2080: FS, MDC1.C4.Cx2030: FS, MDC1.C4.C3430: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C2420 | Not Started | MDC1-BL.5.3.6.4.11.3 | Task Dependent | Controls Installation | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C2290: FS, MDC1.C4.C2310: FS, MDC1.C4.C2390: FS | MDC1.C4.C2450: FS, MDC1.C4.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C4.C4400 | Not Started | MDC1-BL.5.3.6.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-05-06 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4340: FS | MDC1.C4.C4460: FS, MDC1.C4.Cx2110: FS, MDC1.C4.Cx2050: FS, MDC1.C4.C4430: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.Cx2070 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-26 07:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C3.Cx2000: FS | MDC1.C3.Cx3000: SS 11, MDC1.C3.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C1.Cx4010 | Not Started | MDC1-BL.5.2.3.5 | Task Dependent | Security Commissioning | 2021-05-10 08:00 | 2021-05-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 162 | 162 |  |  |  |  | MDC1.C1.Cx3040: FS | MDC1-C1.P2200: FS |  | 0 | 0
MDC1.C4.C4390 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-04-24 07:00 | 2021-05-18 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 8 | 8 |  |  |  |  | MDC1.C4.C2360: FS, MDC1.C4.C4110: FS, MDC1.C4.C4100: FS, MDC1.C4.C4260: FS, MDC1.C4.C2360: FF | MDC1.C4.C4360: SS 5 | VECA Electricians | 1080 | 0
MDC1.C4.C1420 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2021-04-22 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 8 | 8 |  |  |  |  | MDC1.C4.C1370: FS | MDC1.C4.C1450: FS, MDC1.C4.Cx2000: FS | VECA Electricians | 1680 | 0
MDC1.C4.C2410 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2021-04-22 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 8 | 8 |  |  |  |  | MDC1.C4.C2350: FS | MDC1.C4.C2450: FS, MDC1.C4.Cx2010: FS | VECA Electricians | 1680 | 0
MDC1.C4.C4370 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-05-04 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C4310: FS, MDC1.C4.C4100: FS, MDC1.C4.C4260: FS | MDC1.C4.Cx2050: FS, MDC1.C4.C4440: FS | VECA Electricians | 960 | 0
MDC1.C4.C4380 | Not Started | MDC1-BL.5.3.6.4.8.1 | Task Dependent | Ligthing Installation | 2021-05-04 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C4.C2370: FS, MDC1.C4.C4160: FS, MDC1.C4.C4230: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0
MDC1.C3.C3420 | Not Started | MDC1-BL.5.3.8.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-04-23 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C1460: FS, MDC1.C3.C3360: FS | MDC1.C3.Cx4000: FS, MDC1.C4.C1460: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C4460 | Not Started | MDC1-BL.5.3.8.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-04-23 07:00 | 2021-05-17 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C3.C2460: FS, MDC1.C3.C4390: FS | MDC1.C3.Cx4000: FS, MDC1.C4.C2460: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C1410 | Not Started | MDC1-BL.5.3.6.4.1.4 | Task Dependent | Controls Installation | 2021-05-03 07:00 | 2021-05-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 9 | 9 |  |  |  |  | MDC1.C4.C1100: FS, MDC1.C4.C1110: FS, MDC1.C4.C1390: FS | MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | VECA Electricians | 720 | 0
MDC1.M1010 | Not Started | MDC1-BL.1 | Finish Milestone | MDC1 Admin/COLO1 - LV3 Cx Complete |  | 2021-05-15 08:00 |  |  | 2021-05-15 08:00 |  | 0 | 0 | 0 | 0 | 0 | 0 | Finish On or Before | 2021-05-14 17:00 |  |  | MDC1.C1.Cx3040: FS, MDC1.C1.Cx2090: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2060: FS, MDC1.AD.Cx2000: FS, MDC1.AD.Cx2020: FS, MDC1.C1.C1350: FS, MDC1.C1.C2330: FS, MDC1.C1.C4310: FS, MDC1.C1.C4490: FS, MDC1.C1.C3320: FS, MDC1-C2.P1800: FS, MDC1.C1.Cx3050: FS, MDC1-1955: FS | MDC1.C1.Cx4000: FS, MDC1.M6010: FS |  | 0 | 0
MDC1-1955 | Not Started | MDC1-BL.2 | Level of Effort | MDC1 Admin/COLO1 - Fitout Summary | 2020-08-14 07:00 | 2021-05-15 08:00 |  |  |  |  | 0 | 0 | 214 | 214 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: SS | MDC1.M1010: FS |  | 0 | 0
MDC1.C1.Cx3050 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Weather(5 Days) | 2021-05-10 08:00 | 2021-05-15 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.C4400: FS, MDC1.AD.Cx2000: FS, MDC1.AD.Cx2020: FS, MDC1.C1.Cx2060: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2090: FS, MDC1.C1.Cx3040: FS | MDC1.M1010: FS |  | 0 | 0
MDC1.C4.C4360 | Not Started | MDC1-BL.5.3.6.4.4.4 | Task Dependent | Fire Alarm Installation | 2021-04-30 07:00 | 2021-05-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C4.C4110: FS, MDC1.C4.C4100: FS, MDC1.C4.C4390: SS 5 | MDC1.C4.C4410: FS | VECA Electricians | 240 | 0
MDC1.S.1870 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Curb & Gutter | 2021-04-08 07:00 | 2021-05-14 17:00 |  |  |  |  | 0 | 0 | 30 | 30 | 49 | 49 |  |  |  |  | MDC1.S.1040: FS, MDC1.S.1300: FS, MDC1.C4.C4250: FS, MDC1.C4.CS1050: FS, MDC1.C4.CS1060: FS | MDC1.S.1880: FS, MDC1.S.1900: FS | Advantage | 1500 | 0
MDC1.C2.Cx3010 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Cooling Automation | 2021-04-28 08:00 | 2021-05-13 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx3000: FS, MDC1.C2.Cx2130: FS, MDC1.C2.Cx2170: FS, MDC1.C2.Cx2190: FS, MDC1.C2.Cx2080: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2150: FS, MDC1.C2.Cx2180: FS, MDC1.C1.Cx3010: FS | MDC1.C2.Cx3030: FS, MDC1.C3.Cx3010: FS | TCM | 1200 | 0
MDC1.C4.C3380 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-04-27 07:00 | 2021-05-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C3320: FS, MDC1.C4.C3100: FS, MDC1.C4.C3260: FS, MDC1.C4.C1380: FS | MDC1.C4.Cx2030: FS, MDC1.C4.C3440: FS | VECA Electricians | 960 | 0
MDC1.C4.C3390 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-04-17 07:00 | 2021-05-11 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 14 | 14 |  |  |  |  | MDC1.C4.C1340: FS, MDC1.C4.C3110: FS, MDC1.C4.C3100: FS, MDC1.C4.C3260: FS, MDC1.C4.C1340: FF | MDC1.C4.Cx2030: FS, MDC1.C4.C3370: SS 5 | VECA Electricians | 1080 | 0
MDC1.C3.Cx2030 | Not Started | MDC1-BL.5.2.1.7.2 | Task Dependent | Equipment Yellow Tagging | 2021-04-28 07:00 | 2021-05-10 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C3150: FF, MDC1.C3.C3390: FS, MDC1.C3.C3360: FS, MDC1.C3.C3400: FS, MDC1.C3.C3370: FS, MDC1.C3.C3170: FS, MDC1.C3.C3330: FS, MDC1.C3.C3380: FS, MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.Cx2080: FS, MDC1.C3.Cx2160: FS | VECA Electricians | 1200 | 0
MDC1.C3.Cx2040 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | Network Startup | 2021-04-28 07:00 | 2021-05-10 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.C3.C2400: FS, MDC1.C3.Cx2010: FS | MDC1.C3.Cx2090: FS, MDC1.C3.Cx2130: FS, MDC1.C3.Cx2100: FS | LINX- TELECOM | 600 | 0
MDC1.C3.Cx2050 | Not Started | MDC1-BL.5.2.1.7.4 | Task Dependent | Equipment Yellow Tagging | 2021-04-28 07:00 | 2021-05-10 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C4190: FF, MDC1.C3.C4420: FS, MDC1.C3.C4390: FS, MDC1.C3.C4440: FS, MDC1.C3.C4410: FS, MDC1.C3.C4210: FS, MDC1.C3.C4370: FS, MDC1.C3.C4430: FS, MDC1.C3.C4140: FS, MDC1.C3.Cx2010: FS, MDC1-C3.P1800: FS | MDC1.C3.Cx2100: FS, MDC1.C3.Cx2170: FS | VECA Electricians | 1200 | 0
MDC1.C1.Cx3040 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Level 3 Cx - ADMIN AND COLO1 | 2021-04-24 08:00 | 2021-05-10 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx3030: FS, MDC1.C1.Cx3020: FF 10, MDC1-C1.P1900: FS | MDC1.M1010: FS, MDC1.M2010: FS, MDC1.C1.Cx3050: FS, MDC1.C1.Cx4020: FS, MDC1.C1.Cx4010: FS | VECA Electricians | 1200 | 0
MDC1.C4.C2400 | Not Started | MDC1-BL.5.3.6.4.3.4 | Task Dependent | Fire Alarm Installation | 2021-04-24 07:00 | 2021-05-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C2110: FS, MDC1.C4.C2100: FS, MDC1.C4.C2360: FS | MDC1.C4.C2430: FS | VECA Electricians | 240 | 0
MDC1.C3.Cx2020 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | Network Startup | 2021-04-26 07:00 | 2021-05-07 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C3.C1410: FS, MDC1.C3.Cx2000: FS | MDC1.C3.Cx2060: FS, MDC1.C3.Cx2110: FS, MDC1.C3.Cx2080: FS | LINX- TELECOM | 600 | 0
MDC1.C4.C3370 | Not Started | MDC1-BL.5.3.6.4.2.4 | Task Dependent | Fire Alarm Installation | 2021-04-23 07:00 | 2021-05-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C4.C3110: FS, MDC1.C4.C3100: FS, MDC1.C4.C3390: SS 5 | MDC1.C4.C3410: FS | VECA Electricians | 240 | 0
MDC1.C4.C3360 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | PDU's Installation | 2021-05-04 07:00 | 2021-05-06 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 6 | 6 |  |  |  |  | MDC1.C4.C3340: FS, MDC1.C4.E1440: FS, MDC1.C4.E1450: FS | MDC1.C4.C3420: FS, MDC1.C4.C3450: FS | VECA Electricians | 180 | 0
MDC1.C4.C4350 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | PDU's Installation | 2021-05-04 07:00 | 2021-05-06 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 6 | 6 |  |  |  |  | MDC1.C4.C4320: FS, MDC1.C4.C4210: FS, MDC1.C4.E1460: FS, MDC1.C4.E1470: FS | MDC1.C4.C4420: FS, MDC1.C4.C4450: FS | VECA Electricians | 180 | 0
MDC1.C3.C3410 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-04-28 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 74 | 74 |  |  |  |  | MDC1.C3.C3390: FS, MDC1.C3.C3400: FS, MDC1.C3.C3340: FS | MDC1-C3.P1900: FS, MDC1-C3.P1900: SS | VECA Electricians | 480 | 0
MDC1.C3.C4450 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-04-28 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 74 | 74 |  |  |  |  | MDC1.C3.C4420: FS, MDC1.C3.C4440: FS, MDC1.C3.C4360: FS | MDC1-C3.P1900: FS, MDC1-C3.P1900: SS | VECA Electricians | 480 | 0
MDC1.C4.C1400 | Not Started | MDC1-BL.5.3.6.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C1360: FS | MDC1.C4.C1460: FS, MDC1.C4.Cx2020: FS, MDC1.C4.Cx2000: FS, MDC1.C4.C1430: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C3350 | Not Started | MDC1-BL.5.3.6.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C3310: FS | MDC1.C4.C3400: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C2390 | Not Started | MDC1-BL.5.3.6.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C2340: FS | MDC1.C4.C2460: FS, MDC1.C4.Cx2040: FS, MDC1.C4.Cx2010: FS, MDC1.C4.C2420: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C4340 | Not Started | MDC1-BL.5.3.6.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-21 07:00 | 2021-05-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4280: FS | MDC1.C4.C4400: FS | LINX- TELECOM | 1440 | 0
MDC1-C3.P1900 | Not Started | MDC1-BL.3.4 | Finish Milestone | COLO 3 CSA complete |  | 2021-05-05 17:00 |  |  | 2021-05-05 17:00 |  | 0 | 0 | 0 | 0 | 74 | 74 |  |  |  |  | MDC1.C3.C3240: FS, MDC1.C3.C4260: FS, MDC1.C3.C1250: FS, MDC1.C3.C3160: FS, MDC1.C3.C2200: FS, MDC1.C3.C4200: FS, MDC1.C3.C3290: FS, MDC1.C3.C2410: FS, MDC1.C3.C2230: FS, MDC1.C3.C4250: FS, MDC1.C3.C3410: FS, MDC1.C3.C2450: FS, MDC1.C3.C4450: FS, MDC1.C4.C1260: FS, MDC1.C4.C3220: FS, MDC1.C3.C1450: FS, MDC1.C3.C3410: SS, MDC1.C3.C2450: SS, MDC1.C3.C4450: SS, MDC1.C3.C1300: FS, MDC1.C3.C3220: FS, MDC1.C3.C1290: FS, MDC1.C3.C3210: FS, MDC1.C3.C2220: FS, MDC1.C3.C4240: FS | MDC1.C1.Cx4020: FS, MDC1.M3010: FS |  | 0 | 0
MDC1.C4.C2380 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-04-20 07:00 | 2021-05-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C2330: FS, MDC1.C4.C2100: FS, MDC1.C4.C2280: FS | MDC1.C4.Cx2010: FS, MDC1.C4.C2440: FS | VECA Electricians | 960 | 0
MDC1.C4.C4330 | Not Started | MDC1-BL.5.3.6.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-04-20 07:00 | 2021-05-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 108 | 108 |  |  |  |  | MDC1.C4.C4270: FS, MDC1.C4.C4230: FS | MDC1-C4.P1900: FS | TCM | 480 | 0
MDC1.C4.C2370 | Not Started | MDC1-BL.5.3.6.4.7.1 | Task Dependent | Ligthing Installation | 2021-04-19 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C4400: FS, MDC1.C4.C2160: FS, MDC1.C4.C2200: FS | MDC1.C4.C4380: FS, MDC1-C4.P1900: FS | VECA Electricians | 480 | 0
MDC1.C4.C4300 | Not Started | MDC1-BL.5.3.6.4.13.3 | Task Dependent | Fire Alarm System | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 18 | 18 |  |  |  |  | MDC1.C4.C4280: FS | MDC1.C4.C4430: FS | VECA Electricians | 600 | 0
MDC1.C4.C4310 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4260: FS, MDC1.C4.C4290: FS, MDC1.C4.C2330: FS | MDC1.C4.C4370: FS | VECA Electricians | 560 | 0
MDC1.C4.C3340 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Power Bus Installation | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C3310: FS | MDC1.C4.C3360: FS, MDC1.C4.E1440: FS | VECA Electricians | 1200 | 0
MDC1.C4.C4320 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Power Bus Installation | 2021-04-21 07:00 | 2021-05-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C4280: FS | MDC1.C4.C4350: FS, MDC1.C4.E1460: FS | VECA Electricians | 1200 | 0
MDC1.C4.C1390 | Not Started | MDC1-BL.5.3.6.4.1.4 | Task Dependent | Fire Alarm Installation | 2021-04-17 07:00 | 2021-04-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 9 | 9 |  |  |  |  | MDC1.C4.C1110: FS, MDC1.C4.C1100: FS, MDC1.C4.C1340: FS, MDC1.C4.C1120: FS | MDC1.C4.C1410: FS, MDC1-C4.P1800: FS | VECA Electricians | 240 | 0
MDC1.C2.Cx3000 | Not Started | MDC1-BL.5.2.2.1 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-04-14 08:00 | 2021-04-28 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2110: SS 10, MDC1.C2.Cx2170: SS 10, MDC1.C2.Cx2080: SS 10, MDC1.C2.Cx2150: SS 10, MDC1.C1.Cx3000: FS | MDC1.C2.Cx3010: FS, MDC1.C3.Cx3000: FS 11 | TCM | 1200 | 0
MDC1.C2.Cx2190 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-14 08:00 | 2021-04-28 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2100: FS | MDC1.C2.Cx3010: FS, MDC1.C2.Cx3020: FS, MDC1-C2.P2000: FS | TCM | 640 | 0
MDC1-C2.P2000 | Not Started | MDC1-BL.3.3 | Finish Milestone | Construction Server- COLO-2 |  | 2021-04-28 08:00 |  |  | 2021-04-28 08:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C2.Cx2180: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2190: FS, MDC1.C2.Cx2130: FS | MDC1.C2.Cx3020: FS |  | 0 | 0
MDC1.C3.C3400 | Not Started | MDC1-BL.5.3.8.4.10.3 | Task Dependent | Controls Installation | 2021-04-14 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3270: FS, MDC1.C3.C3300: FS, MDC1.C3.C3360: FS | MDC1.C3.C3410: FS, MDC1.C3.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C3.Cx2010 | Not Started | MDC1-BL.5.2.1.7.3 | Task Dependent | Equipment Yellow Tagging | 2021-04-16 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C2180: FF, MDC1.C3.C2420: FS, MDC1.C3.C2400: FS, MDC1.C3.C2430: FS, MDC1.C3.C2390: FS, MDC1.C3.C2210: FS, MDC1.C3.C2380: FS, MDC1.C3.C2440: FS, MDC1.C3.C2170: FS, MDC1-C3.P1800: FS | MDC1.C3.Cx2040: FS, MDC1.C3.Cx2120: FS, MDC1.C3.Cx2050: FS | VECA Electricians | 1200 | 0
MDC1.C3.C4430 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-04-06 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C3.C4100: FS, MDC1.C3.C4370: FS | MDC1.C3.Cx2050: FS | VECA Electricians | 1440 | 0
MDC1.C3.C4440 | Not Started | MDC1-BL.5.3.8.4.13.3 | Task Dependent | Controls Installation | 2021-04-14 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4310: FS, MDC1.C3.C4330: FS, MDC1.C3.C4390: FS | MDC1.C3.C4450: FS, MDC1.C3.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.C4.C3330 | Not Started | MDC1-BL.5.3.6.4.10.3 | Task Dependent | Fire Alarm System | 2021-04-16 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 22 | 22 |  |  |  |  | MDC1.C4.C3310: FF 6 | MDC1.C4.C3430: FS | VECA Electricians | 600 | 0
MDC1.C2.Cx2180 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-14 07:00 | 2021-04-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2070: FS | MDC1.C2.Cx3010: FS, MDC1.C2.Cx3020: FS, MDC1-C2.P2000: FS | TCM | 640 | 0
MDC1.C4.C1380 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-04-13 07:00 | 2021-04-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C4.C1320: FS, MDC1.C4.C1100: FS, MDC1.C4.C1280: FS | MDC1.C4.Cx2000: FS, MDC1.C4.C1440: FS, MDC1.C4.C3380: FS | VECA Electricians | 960 | 0
MDC1.C2.Cx2160 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-14 08:00 | 2021-04-26 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2100: FS, MDC1.C2.Cx2090: FS | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS | LINX- TELECOM | 1200 | 0
MDC1.C2.Cx2170 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-01 08:00 | 2021-04-26 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2050: FS | MDC1.C2.Cx3000: SS 10, MDC1.C2.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C2.Cx2140 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-14 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2070: FS, MDC1.C2.Cx2060: FS | MDC1.C2.Cx3030: FS | LINX- TELECOM | 1200 | 0
MDC1.C3.Cx2000 | Not Started | MDC1-BL.5.2.1.7.1 | Task Dependent | Equipment Yellow Tagging | 2021-04-14 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C1180: FF, MDC1.C3.C1430: FS, MDC1.C3.C1410: FS, MDC1.C3.C1440: FS, MDC1.C3.C1400: FS, MDC1.C3.C1190: FS, MDC1.C3.C1380: FS, MDC1.C3.C1420: FS, MDC1.C3.C1170: FS | MDC1.C3.Cx2020: FS, MDC1-C3.P1800: SS, MDC1.C3.Cx2070: FS, MDC1.C3.Cx2030: FS | VECA Electricians | 1200 | 0
MDC1.C3.C3390 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-31 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 2 | 2 |  |  |  |  | MDC1.C3.C3340: FS | MDC1.C3.C3410: FS, MDC1.C3.Cx2030: FS | VECA Electricians | 1680 | 0
MDC1.C3.C4420 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-31 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 2 | 2 |  |  |  |  | MDC1.C3.C4360: FS | MDC1.C3.C4450: FS, MDC1.C3.Cx2050: FS | VECA Electricians | 1680 | 0
MDC1.C2.Cx2150 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-04-01 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.Cx2030: FS | MDC1.C2.Cx3000: SS 10, MDC1.C2.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C4.C3320 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-04-14 07:00 | 2021-04-24 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C3260: FS, MDC1.C4.C3270: FS, MDC1.C4.C1320: FS | MDC1.C4.C3380: FS | VECA Electricians | 560 | 0
MDC1.C1.Cx3030 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Load Bank & IR Scan | 2021-04-02 08:00 | 2021-04-24 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2190: FS, MDC1.C1.Cx2090: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2060: FS, MDC1.AD.Cx2020: FS, MDC1.C1.Cx3010: FS, MDC1.S.1850: FS | MDC1.C1.Cx3040: FS, MDC1.C2.Cx3030: FS 15 | VECA Electricians | 3600 | 0
MDC1.C3.C3380 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-03-31 07:00 | 2021-04-23 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3330: FS | MDC1.C3.Cx2030: FS | VECA Electricians | 1440 | 0
MDC1.C4.C2360 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-31 07:00 | 2021-04-23 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 3 | 3 |  |  |  |  | MDC1.C4.C2110: FS, MDC1.C4.C2100: FS, MDC1.C4.C2280: FS | MDC1.C4.C4390: FS, MDC1.C4.C2400: FS, MDC1.C4.C4390: FF | VECA Electricians | 1080 | 0
MDC1.C3.C1460 | Not Started | MDC1-BL.5.3.8.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-30 07:00 | 2021-04-22 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C2.C3460: FS, MDC1.C3.C1410: FS | MDC1.C3.Cx4000: FS, MDC1.C3.C3420: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C2460 | Not Started | MDC1-BL.5.3.8.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-30 07:00 | 2021-04-22 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C2.C4420: FS, MDC1.C3.C2400: FS | MDC1.C3.Cx4000: FS, MDC1.C3.C4460: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C3370 | Not Started | MDC1-BL.5.3.8.4.2.4 | Task Dependent | Controls Installation | 2021-04-07 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 5 | 5 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3110: FS, MDC1.C3.C3350: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C3.C4410 | Not Started | MDC1-BL.5.3.8.4.4.4 | Task Dependent | Controls Installation | 2021-04-07 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 5 | 5 |  |  |  |  | MDC1.C3.C4100: FS, MDC1.C3.C4130: FS, MDC1.C3.C4180: FS, MDC1.C3.C4380: FS | MDC1.C3.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.C4.C1370 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | PDU's Installation | 2021-04-19 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 8 | 8 |  |  |  |  | MDC1.C4.C1350: FS, MDC1.C4.E1400: FS, MDC1.C4.E1410: FS | MDC1.C4.C1420: FS, MDC1.C4.C1450: FS | VECA Electricians | 180 | 0
MDC1.C4.C2350 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | PDU's Installation | 2021-04-19 07:00 | 2021-04-21 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 8 | 8 |  |  |  |  | MDC1.C4.C2320: FS, MDC1.C4.E1420: FS, MDC1.C4.E1430: FS | MDC1.C4.C2410: FS, MDC1.C4.C2450: FS | VECA Electricians | 180 | 0
MDC1.C3.C1450 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-04-14 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 86 | 86 |  |  |  |  | MDC1.C3.C1430: FS, MDC1.C3.C1440: FS, MDC1.C3.C1390: FS | MDC1-C3.P1900: FS | VECA Electricians | 480 | 0
MDC1.C3.C2450 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Light Fixtures Installation | 2021-04-14 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 86 | 86 |  |  |  |  | MDC1.C3.C2420: FS, MDC1.C3.C2430: FS, MDC1.C3.C2370: FS | MDC1-C3.P1900: FS, MDC1-C3.P1900: SS | VECA Electricians | 480 | 0
MDC1.C4.C1360 | Not Started | MDC1-BL.5.3.6.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C1310: FS, MDC1.C4.C1330: FF 6 | MDC1.C4.C1400: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C3310 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | Cable Tray Installation | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C1310: FS, MDC1.C4.C3230: FS | MDC1.C4.C3350: FS, MDC1.C4.C3340: FS, MDC1.C4.C3430: FS, MDC1.C4.C3330: FF 6 | VECA Electricians | 1440 | 0
MDC1.C4.C2340 | Not Started | MDC1-BL.5.3.6.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C2290: FS | MDC1.C4.C2390: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C4280 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | Cable Tray Installation | 2021-04-06 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C4220: FS, MDC1.C4.C2290: FS | MDC1.C4.C4340: FS, MDC1.C4.C4320: FS, MDC1.C4.C4420: FS, MDC1.C4.C4430: FS, MDC1.C4.C4300: FS | VECA Electricians | 1440 | 0
MDC1.C4.C4290 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-04-08 07:00 | 2021-04-20 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C4250: FS | MDC1.C4.C4310: FS |  | 0 | 0
MDC1.C4.C3280 | Not Started | MDC1-BL.5.3.6.4.6.1 | Task Dependent | Ligthing Installation | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C1300: FS, MDC1.C4.C3160: FS, MDC1.C4.C3240: FS | MDC1-C4.P1900: FS | VECA Electricians | 480 | 0
MDC1.C4.C3290 | Not Started | MDC1-BL.5.3.6.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C3010: FS, MDC1.C4.C3240: FS | MDC1-C4.P1900: FS |  | 0 | 0
MDC1.C4.C3300 | Not Started | MDC1-BL.5.3.6.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C3240: FS | MDC1-C4.P1900: FS | TCM | 480 | 0
MDC1.C4.C4270 | Not Started | MDC1-BL.5.3.6.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-04-05 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 108 | 108 |  |  |  |  | MDC1.C4.C4010: FS, MDC1.C4.C4230: FS | MDC1.C4.C4330: FS, MDC1-C4.P1900: FS |  | 0 | 0
MDC1.C4.C2330 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-04-07 07:00 | 2021-04-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2280: FS, MDC1.C4.C2300: FS | MDC1.C4.C2380: FS, MDC1.C4.C4310: FS | VECA Electricians | 560 | 0
MDC1.C3.C4400 | Not Started | MDC1-BL.5.3.8.4.8.1 | Task Dependent | Ligthing Installation | 2021-04-03 07:00 | 2021-04-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C2410: FS, MDC1.C3.C4160: FS, MDC1.C3.C4200: FS | MDC1.C4.C2370: FS | VECA Electricians | 480 | 0
MDC1.C4.C1350 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Power Bus Installation | 2021-04-06 07:00 | 2021-04-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 8 | 8 |  |  |  |  | MDC1.C4.C1310: FS | MDC1.C4.C1370: FS, MDC1.C4.E1400: FS | VECA Electricians | 1200 | 0
MDC1.C4.C2320 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Power Bus Installation | 2021-04-06 07:00 | 2021-04-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 8 | 8 |  |  |  |  | MDC1.C4.C2290: FS, MDC1.C4.C2260: FS | MDC1.C4.C2350: FS, MDC1.C4.E1420: FS | VECA Electricians | 1200 | 0
MDC1.C4.C1340 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-24 07:00 | 2021-04-16 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 9 | 9 |  |  |  |  | MDC1.C4.C1110: FS, MDC1.C4.C1100: FS, MDC1.C4.C1280: FS | MDC1.C4.C3390: FS, MDC1.C4.C1390: FS, MDC1.C4.C3390: FF | VECA Electricians | 1080 | 0
MDC1.C2.Cx2130 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-01 08:00 | 2021-04-16 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2040: FS | MDC1.C2.Cx3020: FS, MDC1.C2.Cx3010: FS, MDC1-C2.P2000: FS | TCM | 640 | 0
MDC1.C3.C2440 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-03-24 07:00 | 2021-04-15 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C3.C2110: FS, MDC1.C3.C2380: FS | MDC1.C3.Cx2010: FS | VECA Electricians | 1440 | 0
MDC1.C2.Cx2120 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-04-01 07:00 | 2021-04-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2020: FS | MDC1.C2.Cx3010: FS, MDC1.C2.Cx3020: FS, MDC1-C2.P2000: FS | TCM | 640 | 0
MDC1.C2.Cx2090 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-01 08:00 | 2021-04-14 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2040: FS | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS, MDC1.C2.Cx2160: FS | LINX- TELECOM | 1200 | 0
MDC1.C2.Cx2100 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | Network Startup | 2021-04-01 08:00 | 2021-04-14 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3330: FS, MDC1.C2.Cx2050: FS, MDC1.C2.Cx2040: FS | MDC1.C2.Cx2160: FS, MDC1.C2.Cx2190: FS | LINX- TELECOM | 600 | 0
MDC1.C2.Cx2110 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-03-19 08:00 | 2021-04-14 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2010: FS | MDC1.C2.Cx3000: SS 10 | VECA Electricians | 2000 | 0
MDC1.C2.Cx2060 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.Cx2020: FS | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS, MDC1.C2.Cx2140: FS | LINX- TELECOM | 1200 | 0
MDC1.C2.Cx2070 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | Network Startup | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C4290: FS, MDC1.C2.Cx2030: FS, MDC1.C2.Cx2020: FS | MDC1.C2.Cx2140: FS, MDC1.C2.Cx2180: FS | LINX- TELECOM | 600 | 0
MDC1.C3.C1440 | Not Started | MDC1-BL.5.3.8.4.9.3 | Task Dependent | Controls Installation | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C1310: FS, MDC1.C3.C1340: FS, MDC1.C3.C1410: FS | MDC1.C3.C1450: FS, MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS | VECA Electricians | 720 | 0
MDC1.C3.C3360 | Not Started | MDC1-BL.5.3.8.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3320: FS | MDC1.C3.C3420: FS, MDC1.C3.Cx2080: FS, MDC1.C3.Cx2030: FS, MDC1.C3.C3400: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C2430 | Not Started | MDC1-BL.5.3.8.4.11.3 | Task Dependent | Controls Installation | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C2310: FS, MDC1.C3.C2320: FS, MDC1.C3.C2400: FS | MDC1.C3.C2450: FS, MDC1.C3.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C3.C4390 | Not Started | MDC1-BL.5.3.8.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-30 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4350: FS | MDC1.C3.C4460: FS, MDC1.C3.Cx2100: FS, MDC1.C3.Cx2050: FS, MDC1.C3.C4440: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C1330 | Not Started | MDC1-BL.5.3.6.4.9.3 | Task Dependent | Fire Alarm System | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C1310: FF 6 | MDC1.C4.C1360: FF 6, MDC1.C4.C1430: FS, MDC1-C4.P1800: FS | VECA Electricians | 600 | 0
MDC1.C4.C3270 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C3210: FS | MDC1.C4.C3320: FS |  | 0 | 0
MDC1.C4.C2310 | Not Started | MDC1-BL.5.3.6.4.11.3 | Task Dependent | Fire Alarm System | 2021-04-01 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 24 | 24 |  |  |  |  | MDC1.C4.C2290: FF 6 | MDC1.C4.C2420: FS | VECA Electricians | 600 | 0
MDC1.C4.C4260 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-04-08 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C4.C4060: FS, MDC1.C4.C4250: FS, MDC1.C4.C2280: FS | MDC1.C4.C4310: FS, MDC1.C4.C4370: FS, MDC1.C4.C4390: FS | SURE STEEL | 160 | 0
MDC1.C2.Cx2080 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-03-19 07:00 | 2021-04-13 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 10 | 10 |  |  |  |  | MDC1.C2.Cx2000: FS | MDC1.C2.Cx3000: SS 10, MDC1.C2.Cx3010: FS | VECA Electricians | 2000 | 0
MDC1.C1.Cx3020 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | BAS Prefunctional Testing on Construction Server | 2021-03-18 08:00 | 2021-04-13 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 12 | 12 |  |  |  |  | MDC1.C1.Cx2170: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2180: FS, MDC1.C1.Cx2080: FS, MDC1.C1.C4240: FS, MDC1.C1.C2200: FS, MDC1.C1.C3280: FS, MDC1.C1.C1220: FS, MDC1-C1.P2000: FS | MDC1.C1.Cx3040: FF 10, MDC1.C2.Cx3020: FS | LINX- TELECOM | 2000 | 0
MDC1.C4.C1320 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-03-31 07:00 | 2021-04-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C1280: FS, MDC1.C4.C1290: FS | MDC1.C4.C1380: FS, MDC1.C4.C3320: FS | VECA Electricians | 560 | 0
MDC1.C3.C1430 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-16 07:00 | 2021-04-09 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 4 | 4 |  |  |  |  | MDC1.C3.C1390: FS | MDC1.C3.C1450: FS, MDC1.C3.Cx2000: FS | VECA Electricians | 1680 | 0
MDC1.C3.C2420 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2021-03-16 07:00 | 2021-04-09 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 4 | 4 |  |  |  |  | MDC1.C3.C2370: FS | MDC1.C3.C2450: FS, MDC1.C3.Cx2010: FS | VECA Electricians | 1680 | 0
MDC1.C3.C1420 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Pull Conductors into Building | 2021-03-16 07:00 | 2021-04-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C1110: FS, MDC1.C3.C1380: FS, MDC1.C3.C1360: FS | MDC1.C3.Cx2000: FS | VECA Electricians | 1440 | 0
MDC1.C4.C4250 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Lift & Set MER in Place | 2021-04-02 07:00 | 2021-04-07 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C4.E1390: FS, MDC1.C4.E1230: FS, MDC1.C4.C4060: FS, MDC1.C4.C3210: FS | MDC1.C4.C4260: FS, MDC1.C4.C4290: FS, MDC1.S.1870: FS | VECA Electricians | 120 | 0
MDC1.C3.C3350 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-13 07:00 | 2021-04-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3230: FS, MDC1.C3.C3260: FS, MDC1.C3.C1360: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.C3370: FS | VECA Electricians | 1080 | 0
MDC1.C3.C4380 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-03-13 07:00 | 2021-04-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C4130: FS, MDC1.C3.C4100: FS, MDC1.C3.C4290: FS, MDC1.C3.C4300: FS, MDC1.C3.C2350: FS | MDC1.C3.C4410: FS | VECA Electricians | 1080 | 0
MDC1.C4.C2300 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-03-26 07:00 | 2021-04-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C4.C2270: FS | MDC1.C4.C2330: FS |  | 0 | 0
MDC1.C3.C4370 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-23 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4320: FS, MDC1.C3.C4100: FS, MDC1.C3.C4290: FS | MDC1.C3.Cx2050: FS, MDC1.C3.C4430: FS | VECA Electricians | 960 | 0
MDC1.C4.C1310 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | Cable Tray Installation | 2021-03-23 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C3.C3270: FS, MDC1.C4.C1270: FS | MDC1.C4.C3310: FS, MDC1.C4.C1360: FS, MDC1.C4.C1350: FS, MDC1.C4.C1430: FS, MDC1.C4.C1330: FF 6 | VECA Electricians | 1440 | 0
MDC1.C4.C3260 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-04-01 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 10 | 10 |  |  |  |  | MDC1.C4.C3060: FS, MDC1.C4.C3210: FS, MDC1.C4.C1280: FS | MDC1.C4.C3320: FS, MDC1.C4.C3380: FS, MDC1.C4.C3390: FS | SURE STEEL | 160 | 0
MDC1.C4.C2290 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | Cable Tray Installation | 2021-03-23 07:00 | 2021-04-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C3.C4310: FS, MDC1.C4.C2260: FS | MDC1.C4.C2340: FS, MDC1.C4.C2320: FS, MDC1.C4.C4280: FS, MDC1.C4.C2420: FS, MDC1.C4.C2310: FF 6 | VECA Electricians | 1440 | 0
MDC1.C4.C3240 | Not Started | MDC1-BL.5.3.6.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 120 | 120 |  |  |  |  | MDC1.C4.C3150: FS, MDC1.C4.C3010: FS | MDC1.C4.C3280: FS, MDC1.C4.C3300: FS, MDC1.C4.C3290: FS | PCI | 180 | 0
MDC1.C4.C3250 | Not Started | MDC1-BL.5.3.6.4.6.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 53 | 53 |  |  |  |  | MDC1.C4.C3160: FS, MDC1.C4.C3090: FS | MDC1.C4.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C4.C4230 | Not Started | MDC1-BL.5.3.6.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 108 | 108 |  |  |  |  | MDC1.C4.C4150: FS, MDC1.C4.C4010: FS | MDC1.C4.C4380: FS, MDC1.C4.C4330: FS, MDC1.C4.C4270: FS | PCI | 180 | 0
MDC1.C4.C4240 | Not Started | MDC1-BL.5.3.6.4.8.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 53 | 53 |  |  |  |  | MDC1.C4.C4160: FS, MDC1.C4.C4090: FS | MDC1.C4.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.S.1860 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Plant shutdown for winter | 2020-11-24 07:00 | 2021-04-03 17:00 |  |  |  |  | 0 | 0 | 100 | 100 | 106 | 106 | Start On or After | 2020-11-23 17:00 |  |  | MDC1.S.1300: FS | MDC1.S.1880: FS, MDC1.S.1880: FF |  | 0 | 0
MDC1.C3.C2410 | Not Started | MDC1-BL.5.3.8.4.7.1 | Task Dependent | Ligthing Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C2.C4410: FS, MDC1.C3.C2130: FS, MDC1.C3.C2200: FS | MDC1.C3.C4400: FS, MDC1-C3.P1900: FS | VECA Electricians | 480 | 0
MDC1.C4.C1300 | Not Started | MDC1-BL.5.3.6.4.5.1 | Task Dependent | Ligthing Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 121 | 121 |  |  |  |  | MDC1.C3.C3290: FS, MDC1.C4.C1160: FS, MDC1.C4.C1200: FS | MDC1.C4.C3280: FS, MDC1-C4.P1900: FS | VECA Electricians | 480 | 0
MDC1.C4.C3220 | Not Started | MDC1-BL.5.3.6.3.2.2 | Task Dependent | Datahall Finishes | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C3190: FS | MDC1-C3.P1900: FS, MDC1-C4.P1900: FS | PCI | 480 | 0
MDC1.C4.C4210 | Not Started | MDC1-BL.5.3.6.3.4.2 | Task Dependent | Datahall Finishes | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 30 | 30 |  |  |  |  | MDC1.C4.C4190: FS | MDC1.C4.C4350: FS | PCI | 480 | 0
MDC1.C4.C3230 | Not Started | MDC1-BL.5.3.6.4.10.1 | Task Dependent | HAC Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C3190: FS | MDC1.C4.C3310: FS | TCM | 480 | 0
MDC1.C4.C4220 | Not Started | MDC1-BL.5.3.6.4.13.1 | Task Dependent | HAC Installation | 2021-03-19 07:00 | 2021-04-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C4.C4190: FS | MDC1.C4.C4280: FS | TCM | 480 | 0
MDC1.C1.Cx3010 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Cooling Automation | 2021-03-18 08:00 | 2021-04-02 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2170: FS, MDC1.C1.Cx2120: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2160: FS, MDC1.C1.Cx2180: FS, MDC1.C1.Cx2140: FS, MDC1.C1.Cx2080: FS, MDC1.C1.Cx3000: FS | MDC1.C1.Cx3030: FS, MDC1.C2.Cx3010: FS | TCM | 1200 | 0
MDC1.C2.Cx2040 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | Network Startup | 2021-03-19 08:00 | 2021-04-01 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1340: FS, MDC1.C2.Cx2010: FS | MDC1.C2.Cx2090: FS, MDC1.C2.Cx2130: FS, MDC1.C2.Cx2100: FS | LINX- TELECOM | 600 | 0
MDC1.C2.Cx2050 | Not Started | MDC1-BL.5.2.2.6.2 | Task Dependent | Equipment Yellow Tagging | 2021-03-19 08:00 | 2021-04-01 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3320: FF, MDC1.C2.C3360: FS, MDC1.C2.C3330: FS, MDC1.C2.C3370: FS, MDC1.C2.C3300: FS, MDC1.C2.C3440: FS, MDC1.C2.C3380: FS, MDC1.C2.C3450: FS, MDC1.C2.C3150: FS, MDC1.C2.Cx2010: FS, MDC1-C2.P1800: FS | MDC1.C2.Cx2100: FS, MDC1.C2.Cx2170: FS | VECA Electricians | 1200 | 0
MDC1.C2.Cx2020 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | Network Startup | 2021-03-19 07:00 | 2021-03-31 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2350: FS, MDC1.C2.Cx2000: FS | MDC1.C2.Cx2060: FS, MDC1.C2.Cx2120: FS, MDC1.C2.Cx2070: FS | LINX- TELECOM | 600 | 0
MDC1.C2.Cx2030 | Not Started | MDC1-BL.5.2.2.6.4 | Task Dependent | Equipment Yellow Tagging | 2021-03-19 07:00 | 2021-03-31 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C4270: FF, MDC1.C2.C4320: FS, MDC1.C2.C4290: FS, MDC1.C2.C4330: FS 5, MDC1.C2.C4370: FS, MDC1.C2.C4390: FS, MDC1.C2.C4400: FS, MDC1.C2.C4260: FS 5, MDC1.C2.C4380: FS, MDC1.C2.Cx2000: FS, MDC1-C2.P1800: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS, MDC1.C2.C4120: FS | MDC1.C2.Cx2070: FS, MDC1.C2.Cx2150: FS | VECA Electricians | 1200 | 0
MDC1.C4.C3210 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Lift & Set MER in Place | 2021-03-26 07:00 | 2021-03-31 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C4.E1380: FS, MDC1.C4.E1220: FS, MDC1.C4.C3060: FS | MDC1.C4.C3260: FS, MDC1.C4.C3270: FS, MDC1.C4.C4250: FS | VECA Electricians | 120 | 0
MDC1.C3.C3330 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-16 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C3.C3280: FS, MDC1.C3.C3080: FS, MDC1.C3.C3230: FS, MDC1.C3.C1380: FS | MDC1.C3.Cx2030: FS, MDC1.C3.C3380: FS | VECA Electricians | 960 | 0
MDC1.C3.C3340 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | PDU's Installation | 2021-03-27 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 2 | 2 |  |  |  |  | MDC1.C3.C3310: FS, MDC1.C3.E1420: FS, MDC1.C3.E1430: FS | MDC1.C3.C3390: FS, MDC1.C3.C3410: FS | VECA Electricians | 180 | 0
MDC1.C3.C4360 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | PDU's Installation | 2021-03-27 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 2 | 2 |  |  |  |  | MDC1.C3.C4340: FS, MDC1.C3.E1440: FS, MDC1.C3.E1450: FS | MDC1.C3.C4420: FS, MDC1.C3.C4450: FS | VECA Electricians | 180 | 0
MDC1.C4.C1290 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-03-18 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C4.C1230: FS | MDC1.C4.C1320: FS |  | 0 | 0
MDC1.C4.C2280 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-03-26 07:00 | 2021-03-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.C4.C2060: FS, MDC1.C4.C2270: FS | MDC1.C4.C2330: FS, MDC1.C4.C2380: FS, MDC1.C4.C2360: FS, MDC1.C4.C4260: FS | SURE STEEL | 160 | 0
MDC1.C3.C1410 | Not Started | MDC1-BL.5.3.8.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C1370: FS | MDC1.C3.C1460: FS, MDC1.C3.Cx2020: FS, MDC1.C3.Cx2000: FS, MDC1.C3.C1440: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C3320 | Not Started | MDC1-BL.5.3.8.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3270: FS | MDC1.C3.C3360: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C2400 | Not Started | MDC1-BL.5.3.8.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C2360: FS | MDC1.C3.C2460: FS, MDC1.C3.Cx2040: FS, MDC1.C3.Cx2010: FS, MDC1.C3.C2430: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C4350 | Not Started | MDC1-BL.5.3.8.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-15 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4310: FS | MDC1.C3.C4390: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C4420 | Not Started | MDC1-BL.5.3.9.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-05 07:00 | 2021-03-29 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C2.C2450: FS, MDC1.C2.C4290: FS | MDC1.C2.Cx4010: FS, MDC1.C3.C2460: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C1400 | Not Started | MDC1-BL.5.3.8.4.1.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 15 | 15 |  |  |  |  | MDC1.C3.C1110: FS, MDC1.C3.C1160: FS, MDC1.C3.C1200: FS, MDC1.C3.C1360: FS | MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS | VECA Electricians | 720 | 0
MDC1.C3.C2390 | Not Started | MDC1-BL.5.3.8.4.3.4 | Task Dependent | Controls Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 15 | 15 |  |  |  |  | MDC1.C3.C2110: FS, MDC1.C3.C2160: FS, MDC1.C3.C2190: FS, MDC1.C3.C2330: FS, MDC1.C3.C2350: FS | MDC1.C3.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C4.C3200 | Not Started | MDC1-BL.5.3.6.4.6.2 | Task Dependent | Hydronic Piping Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C3170: FS | MDC1.C4.Cx2030: FF | TCM | 480 | 0
MDC1.C4.C4200 | Not Started | MDC1-BL.5.3.6.4.8.2 | Task Dependent | Hydronic Piping Installation | 2021-03-13 07:00 | 2021-03-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C4170: FS | MDC1.C4.Cx2050: FF | TCM | 480 | 0
MDC1.C3.C4330 | Not Started | MDC1-BL.5.3.8.4.13.3 | Task Dependent | Fire Alarm System | 2021-03-15 07:00 | 2021-03-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C3.C4310: FS | MDC1.C3.C4440: FS | VECA Electricians | 600 | 0
MDC1.C3.C3310 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Power Bus Installation | 2021-03-15 07:00 | 2021-03-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C3270: FS | MDC1.C3.C3340: FS, MDC1.C3.E1420: FS | VECA Electricians | 1200 | 0
MDC1.C3.C4340 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Power Bus Installation | 2021-03-15 07:00 | 2021-03-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C4310: FS | MDC1.C3.C4360: FS, MDC1.C3.E1440: FS | VECA Electricians | 1200 | 0
MDC1.C4.C2270 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Lift & Set MER in Place | 2021-03-19 07:00 | 2021-03-25 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C4.E1370: FS, MDC1.C4.E1130: FS, MDC1.C4.C2060: FS, MDC1.C4.C1230: FS | MDC1.C4.C2280: FS, MDC1.C4.C2300: FS | VECA Electricians | 120 | 0
MDC1.C2.C3460 | Not Started | MDC1-BL.5.3.9.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-03-01 07:00 | 2021-03-24 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 61 | 61 |  |  |  |  | MDC1.C2.C1440: FS, MDC1.C2.C3330: FS | MDC1.C2.Cx4010: FS, MDC1.C3.C1460: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C2380 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-09 07:00 | 2021-03-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2110: FS, MDC1.C3.C2290: FS, MDC1.C3.C2330: FS | MDC1.C3.Cx2010: FS, MDC1.C3.C2440: FS | VECA Electricians | 960 | 0
MDC1.C4.C1280 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-03-18 07:00 | 2021-03-23 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 9 | 9 |  |  |  |  | MDC1.C4.C1060: FS, MDC1.C4.C1230: FS | MDC1.C4.C1320: FS, MDC1.C4.C1380: FS, MDC1.C4.C1340: FS, MDC1.C4.C3260: FS | SURE STEEL | 160 | 0
MDC1.C3.C3300 | Not Started | MDC1-BL.5.3.8.4.10.3 | Task Dependent | Fire Alarm System | 2021-03-10 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 18 | 18 |  |  |  |  | MDC1.C3.C3270: FF 6 | MDC1.C3.C3400: FS | VECA Electricians | 600 | 0
MDC1.C4.C1260 | Not Started | MDC1-BL.5.3.6.3.1.2 | Task Dependent | Datahall Finishes | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 110 | 110 |  |  |  |  | MDC1.C4.C1220: FS | MDC1-C3.P1900: FS, MDC1-C4.P1900: FS | PCI | 480 | 0
MDC1.C4.C2250 | Not Started | MDC1-BL.5.3.6.3.3.2 | Task Dependent | Datahall Finishes | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 143 | 143 |  |  |  |  | MDC1.C4.C2220: FS | MDC1-C4.P1900: FS | PCI | 480 | 0
MDC1.C3.C4320 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-03-10 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C4290: FS, MDC1.C3.C4300: FS, MDC1.C3.C2330: FS | MDC1.C3.C4370: FS | VECA Electricians | 560 | 0
MDC1.C4.C1270 | Not Started | MDC1-BL.5.3.6.4.9.1 | Task Dependent | HAC Installation | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C1220: FS | MDC1.C4.C1310: FS | TCM | 480 | 0
MDC1.C4.C2260 | Not Started | MDC1-BL.5.3.6.4.11.1 | Task Dependent | HAC Installation | 2021-03-08 07:00 | 2021-03-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 4 | 4 |  |  |  |  | MDC1.C4.C2220: FS | MDC1.C4.C2290: FS, MDC1.C4.C2320: FS | TCM | 480 | 0
MDC1.C1.Cx2190 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | EPMS Checkout / Point to Point | 2021-03-09 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 10 | 10 |  |  |  |  | MDC1.C1.Cx2100: FS, MDC1.C1.Cx2090: FS | MDC1.C1.Cx3030: FS | LINX- TELECOM | 1200 | 0
MDC1.C4.C1240 | Not Started | MDC1-BL.5.3.6.4.5.3 | Task Dependent | Floor Drain System Installation | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C1010: FS, MDC1.C4.C1200: FS | MDC1-C4.P1900: FS |  | 0 | 0
MDC1.C4.C1250 | Not Started | MDC1-BL.5.3.6.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C1200: FS | MDC1-C4.P1900: FS | TCM | 480 | 0
MDC1.C4.C2230 | Not Started | MDC1-BL.5.3.6.4.7.3 | Task Dependent | Floor Drain System Installation | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C2010: FS, MDC1.C4.C2200: FS | MDC1-C4.P1900: FS |  | 0 | 0
MDC1.C4.C2240 | Not Started | MDC1-BL.5.3.6.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2021-03-06 07:00 | 2021-03-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 144 | 144 |  |  |  |  | MDC1.C4.C2200: FS | MDC1-C4.P1900: FS | TCM | 480 | 0
MDC1.C2.Cx2010 | Not Started | MDC1-BL.5.2.2.6.1 | Task Dependent | Equipment Yellow Tagging | 2021-03-08 08:00 | 2021-03-19 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1320: FS, MDC1.C2.C1260: FF, MDC1.C2.C1390: FS, MDC1.C2.C1340: FS, MDC1.C2.C1400: FS, MDC1.C2.C1410: FS, MDC1.C2.C1460: FS, MDC1-1996: FS, MDC1-1993: FS, MDC1-2004: FS, MDC1.C2.C1130: FS, MDC1.C2.C1450: FS, MDC1-C2.P1800: FS | MDC1.C2.Cx2040: FS, MDC1.C2.Cx2110: FS, MDC1.C2.Cx2050: FS | VECA Electricians | 1200 | 0
MDC1.C2.C3450 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-02-25 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.C3080: FS, MDC1.C2.C3380: FS, MDC1.C2.C3430: FS | MDC1.C2.Cx2050: FS | VECA Electricians | 1440 | 0
MDC1.C2.Cx2000 | Not Started | MDC1-BL.5.2.2.6.3 | Task Dependent | Equipment Yellow Tagging | 2021-03-08 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2250: FF, MDC1.C2.C2380: FS, MDC1.C2.C2350: FS, MDC1.C2.C2390: FS, MDC1.C2.C2430: FS, MDC1.C2.C2320: FS, MDC1.C2.C2420: FS, MDC1.C2.C2460: FS, MDC1.C2.C2180: FS, MDC1-C2.P1800: FS | MDC1.C2.Cx2020: FS, MDC1.C2.Cx2080: FS, MDC1.C2.Cx2030: FS | VECA Electricians | 1200 | 0
MDC1.C2.C4390 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-02-25 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4370: FS | MDC1.C2.Cx2030: FS | VECA Electricians | 1440 | 0
MDC1.C2.C4400 | Not Started | MDC1-BL.5.3.9.4.4.4 | Task Dependent | Controls Installation | 2021-03-05 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4100: FS, MDC1.C2.C4380: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.Cx2030: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C2.C4410 | Not Started | MDC1-BL.5.3.9.4.8.1 | Task Dependent | Ligthing Installation | 2021-03-05 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C2.C2440: FS, MDC1.C2.C4120: FS, MDC1.C2.C4300: FS | MDC1.C3.C2410: FS | VECA Electricians | 480 | 0
MDC1.C3.C3290 | Not Started | MDC1-BL.5.3.8.4.6.1 | Task Dependent | Ligthing Installation | 2021-03-05 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 112 | 112 |  |  |  |  | MDC1.C3.C1330: FS, MDC1.C3.C3130: FS, MDC1.C3.C3160: FS | MDC1.C4.C1300: FS, MDC1-C3.P1900: FS | VECA Electricians | 480 | 0
MDC1.C4.C3190 | Not Started | MDC1-BL.5.3.6.3.2.1 | Task Dependent | Hang Wall Partitions | 2021-03-10 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 6 | 6 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C3180: SS 6 | MDC1.C4.C3220: FS, MDC1.C4.C3230: FS | PCI | 600 | 0
MDC1.C4.C4190 | Not Started | MDC1-BL.5.3.6.3.4.1 | Task Dependent | Hang Wall Partitions | 2021-03-10 07:00 | 2021-03-18 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 6 | 6 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C4180: SS 6 | MDC1.C4.C4210: FS, MDC1.C4.C4220: FS | PCI | 600 | 0
MDC1.C1.Cx3000 | Not Started | MDC1-BL.5.2.3.7 | Task Dependent | Hydronic Pipe Flush (Open and closed Loop) | 2021-03-04 08:00 | 2021-03-18 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2120: SS 10, MDC1.C1.Cx2130: SS 10, MDC1.C1.Cx2160: SS 10, MDC1.C1.Cx2140: SS 10 | MDC1.C1.Cx3010: FS, MDC1.C2.Cx3000: FS | TCM | 1200 | 0
MDC1.C1.Cx2180 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-03-04 08:00 | 2021-03-18 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2070: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0
MDC1-C1.P2000 | Not Started | MDC1-BL.3.2 | Finish Milestone | Construction Server- COLO-1 |  | 2021-03-18 08:00 |  |  | 2021-03-18 08:00 |  | 0 | 0 | 0 | 0 | 12 | 12 |  |  |  |  | MDC1.C1.Cx2170: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2180: FS, MDC1.C1.Cx2080: FS | MDC1.C1.Cx3020: FS |  | 0 | 0
MDC1.C1.Cx2170 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-03-04 07:00 | 2021-03-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2100: SS 6 | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0
MDC1.C4.C1230 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Lift & Set MER in Place | 2021-03-12 07:00 | 2021-03-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C4.E1360: FS, MDC1.C4.E1120: FS, MDC1.C4.C1060: FS, MDC1-C4.P1600: FS, MDC1.C3.C4270: FS | MDC1.C4.C1280: FS, MDC1.C4.C1290: FS, MDC1.C4.C2270: FS | VECA Electricians | 120 | 0
MDC1.C1.Cx2150 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | EPMS Checkout / Point to Point | 2021-03-04 08:00 | 2021-03-16 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C1.Cx2070: FS, MDC1.C1.Cx2060: FS, MDC1.C1.Cx2060: FF | MDC1.C1.Cx3030: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS | LINX- TELECOM | 1200 | 0
MDC1.C1.Cx2160 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 08:00 | 2021-03-16 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2030: FS, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0
MDC1.C3.C1380 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-03-02 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 3 | 3 |  |  |  |  | MDC1.C3.C1320: FS, MDC1.C3.C1110: FS, MDC1.C3.C1240: FS | MDC1.C3.Cx2000: FS, MDC1.C3.C1420: FS, MDC1.C3.C3330: FS | VECA Electricians | 960 | 0
MDC1.C3.C1390 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | PDU's Installation | 2021-03-12 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 4 | 4 |  |  |  |  | MDC1.C3.C1350: FS, MDC1.C3.E1380: FS, MDC1.C3.E1390: FS | MDC1.C3.C1430: FS, MDC1.C3.C1450: FS | VECA Electricians | 180 | 0
MDC1.C3.C2370 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | PDU's Installation | 2021-03-12 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 4 | 4 |  |  |  |  | MDC1.C3.C2340: FS, MDC1.C3.E1400: FS, MDC1.C3.E1410: FS | MDC1.C3.C2420: FS, MDC1.C3.C2450: FS | VECA Electricians | 180 | 0
MDC1.C1.Cx2120 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2050: SS 6, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0
MDC1.C1.Cx2130 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2010: FS, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0
MDC1.C1.Cx2140 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | 2021-02-19 07:00 | 2021-03-15 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2000: FS, MDC1.S.1840: FS, MDC1.S.1850: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3000: SS 10 | VECA Electricians | 2000 | 0
MDC1.C3.C1370 | Not Started | MDC1-BL.5.3.8.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C1310: FS | MDC1.C3.C1410: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C3270 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | Cable Tray Installation | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C1310: FS, MDC1.C3.C3250: FS | MDC1.C4.C1310: FS, MDC1.C3.C3320: FS, MDC1.C3.C3310: FS, MDC1.C3.C3400: FS, MDC1.C3.C3300: FF 6 | VECA Electricians | 1440 | 0
MDC1.C3.C2360 | Not Started | MDC1-BL.5.3.8.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C2310: FS, MDC1.C3.C2320: FF 6 | MDC1.C3.C2400: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.C4310 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | Cable Tray Installation | 2021-03-01 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2310: FS, MDC1.C3.C4280: FS | MDC1.C3.C4350: FS, MDC1.C4.C2290: FS, MDC1.C3.C4340: FS, MDC1.C3.C4440: FS, MDC1.C3.C4330: FS | VECA Electricians | 1440 | 0
MDC1.C4.C3180 | Not Started | MDC1-BL.5.3.6.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-03-03 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C1190: FS, MDC1.C4.C3130: FS | MDC1.C4.C3190: SS 6 | VECA Electricians | 1200 | 0
MDC1.C4.C4180 | Not Started | MDC1-BL.5.3.6.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-03-03 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 6 | 6 |  |  |  |  | MDC1.C4.C2190: FS, MDC1.C4.C4130: FS | MDC1.C4.C4190: SS 6 | VECA Electricians | 1200 | 0
MDC1.C3.C3280 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-03-03 07:00 | 2021-03-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C3230: FS, MDC1.C3.C3260: FS, MDC1.C3.C1320: FS | MDC1.C3.C3330: FS | VECA Electricians | 560 | 0
MDC1.C3.C1360 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-17 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C1160: FS, MDC1.C3.C1110: FS, MDC1.C3.C1240: FS, MDC1.C3.C1280: FS | MDC1.C3.C1400: FS, MDC1.C3.C3350: FS, MDC1.C3.C1420: FS | VECA Electricians | 1080 | 0
MDC1.C3.C2350 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-17 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 5 | 5 |  |  |  |  | MDC1.C3.C2160: FS, MDC1.C3.C2110: FS, MDC1.C3.C2290: FS | MDC1.C3.C2390: FS, MDC1.C3.C4380: FS | VECA Electricians | 1080 | 0
MDC1.C4.C3150 | Not Started | MDC1-BL.5.3.6.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 120 | 120 |  |  |  |  | MDC1.C4.C3140: FS | MDC1.C4.C3240: FS | VECA Electricians | 960 | 0
MDC1.C4.C3160 | Not Started | MDC1-BL.5.3.6.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C3140: FS | MDC1.C4.C3280: FS, MDC1.C4.C3250: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C4.C3170 | Not Started | MDC1-BL.5.3.6.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C3140: FS, MDC1.C4.E1320: FS, MDC1.C4.E1340: FS | MDC1.C4.C3200: FS | TCM | 480 | 0
MDC1.C4.C4150 | Not Started | MDC1-BL.5.3.6.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 108 | 108 |  |  |  |  | MDC1.C4.C4140: FS | MDC1.C4.C4230: FS | VECA Electricians | 960 | 0
MDC1.C4.C4160 | Not Started | MDC1-BL.5.3.6.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C4140: FS | MDC1.C4.C4380: FS, MDC1.C4.C4240: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C4.C4170 | Not Started | MDC1-BL.5.3.6.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-02-26 07:00 | 2021-03-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C4.C4140: FS, MDC1.C4.E1330: FS, MDC1.C4.E1350: FS | MDC1.C4.C4200: FS | TCM | 480 | 0
MDC1.C2.C3440 | Not Started | MDC1-BL.5.3.9.4.2.4 | Task Dependent | Controls Installation | 2021-02-25 07:00 | 2021-03-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C2.C3080: FS, MDC1.C2.C3120: FS, MDC1.C2.C3180: FS, MDC1.C2.C3430: FS | MDC1.C2.Cx2050: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C3.C1350 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Power Bus Installation | 2021-03-01 07:00 | 2021-03-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C1310: FS | MDC1.C3.C1390: FS, MDC1.C3.E1380: FS | VECA Electricians | 1200 | 0
MDC1.C3.C2340 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Power Bus Installation | 2021-03-01 07:00 | 2021-03-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C2310: FS | MDC1.C3.C2370: FS, MDC1.C3.E1400: FS | VECA Electricians | 1200 | 0
MDC1.C1.Cx2110 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-02-24 07:00 | 2021-03-10 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C1.Cx2040: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0
MDC1.C3.C4300 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-25 07:00 | 2021-03-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C4270: FS | MDC1.C3.C4320: FS, MDC1.C3.C4380: FS |  | 0 | 0
MDC1.AD.Cx2020 | Not Started | MDC1-BL.5.2.5.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 20 | 20 |  |  |  |  | MDC1.AD.Cx2010: FS | MDC1.M1010: FS, MDC1.C1.Cx3030: FS, MDC1.C1.Cx3050: FS | LINX- TELECOM | 1200 | 0
MDC1.C1.Cx2090 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | EPMS Checkout / Point to Point | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 10 | 10 |  |  |  |  | MDC1.C1.Cx2040: FS | MDC1.C1.Cx3030: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS, MDC1.C1.Cx2190: FS | LINX- TELECOM | 1200 | 0
MDC1.C1.Cx2100 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | Network Startup | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C4380: FS, MDC1.C1.Cx2050: FS, MDC1.C1.Cx2040: FS | MDC1.C1.Cx2190: FS, MDC1.C1.Cx2170: SS 6 | LINX- TELECOM | 600 | 0
MDC1.C3.C2330 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-02-24 07:00 | 2021-03-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C2290: FS, MDC1.C3.C2300: FS, MDC1.C3.C2300: FF | MDC1.C3.C2390: FS, MDC1.C3.C2380: FS, MDC1.C3.C4320: FS | VECA Electricians | 560 | 0
MDC1.C2.C1460 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Pull Conductors into Building | 2021-02-13 08:00 | 2021-03-08 08:00 |  |  |  |  | 0 | 0 | 18 | 18 | 0 | 0 |  |  |  |  | MDC1.C2.C1080: FS, MDC1.C2.C1410: FS, MDC1.C2.C1430: FS | MDC1.C2.Cx2010: FS | VECA Electricians | 1440 | 0
MDC1.C2.C2460 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-02-11 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C2060: FS, MDC1.C2.C2420: FS | MDC1.C2.Cx2000: FS | VECA Electricians | 1440 | 0
MDC1.C3.C1340 | Not Started | MDC1-BL.5.3.8.4.9.3 | Task Dependent | Fire Alarm System | 2021-02-23 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 20 | 20 |  |  |  |  | MDC1.C3.C1310: FF 6 | MDC1.C3.C1440: FS, MDC1-C3.P1800: FS | VECA Electricians | 600 | 0
MDC1.C3.C2320 | Not Started | MDC1-BL.5.3.8.4.11.3 | Task Dependent | Fire Alarm System | 2021-02-23 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C2310: FF 6 | MDC1.C3.C2360: FF 6, MDC1.C3.C2430: FS | VECA Electricians | 600 | 0
MDC1.C4.C1220 | Not Started | MDC1-BL.5.3.6.3.1.1 | Task Dependent | Hang Wall Partitions | 2021-02-25 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 4 | 4 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C1190: SS 6 | MDC1.C4.C1260: FS, MDC1.C4.C1270: FS | PCI | 600 | 0
MDC1.C4.C2220 | Not Started | MDC1-BL.5.3.6.3.3.1 | Task Dependent | Hang Wall Partitions | 2021-02-25 07:00 | 2021-03-06 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 4 | 4 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C2190: SS 6 | MDC1.C4.C2250: FS, MDC1.C4.C2260: FS | PCI | 600 | 0
MDC1.C1.Cx2080 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | 2021-02-19 08:00 | 2021-03-06 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C1.Cx2020: FS, MDC1.S.1840: FS | MDC1.C1.Cx3010: FS, MDC1.C1.Cx3020: FS, MDC1-C1.P2000: FS | TCM | 640 | 0
MDC1.C4.C1200 | Not Started | MDC1-BL.5.3.6.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 132 | 132 |  |  |  |  | MDC1.C4.C1150: FS, MDC1.C4.C1010: FS | MDC1.C4.C1300: FS, MDC1.C4.C1250: FS, MDC1-C4.P1900: FS, MDC1.C4.C1240: FS | PCI | 180 | 0
MDC1.C4.C1210 | Not Started | MDC1-BL.5.3.6.4.5.4 | Task Dependent | Controls Installation | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C4.C1160: FS, MDC1.C4.C1090: FS | MDC1.C4.Cx2000: FS, MDC1-C4.P1800: FS | VECA Electricians | 720 | 0
MDC1.C4.C2200 | Not Started | MDC1-BL.5.3.6.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 132 | 132 |  |  |  |  | MDC1.C4.C2150: FS, MDC1.C4.C2010: FS | MDC1.C4.C2370: FS, MDC1.C4.C2240: FS, MDC1.C4.C2230: FS | PCI | 180 | 0
MDC1.C4.C2210 | Not Started | MDC1-BL.5.3.6.4.7.4 | Task Dependent | Controls Installation | 2021-02-12 07:00 | 2021-03-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C4.C2160: FS, MDC1.C4.C2090: FS | MDC1.C4.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C2.C2440 | Not Started | MDC1-BL.5.3.9.4.7.1 | Task Dependent | Ligthing Installation | 2021-02-18 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C1.C4480: FS, MDC1.C2.C2130: FS, MDC1.C2.C2300: SS 6 | MDC1.C2.C4410: FS | VECA Electricians | 480 | 0
MDC1.C2.C4380 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-09 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4250: FS, MDC1.C2.C4280: FS, MDC1.C2.C2410: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.Cx2030: FS, MDC1.C2.C4400: FS | VECA Electricians | 1080 | 0
MDC1.C3.C1330 | Not Started | MDC1-BL.5.3.8.4.5.1 | Task Dependent | Ligthing Installation | 2021-02-18 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 112 | 112 |  |  |  |  | MDC1.C2.C3390: FS, MDC1.C3.C1130: FS, MDC1.C3.C1250: FS | MDC1.C3.C3290: FS | VECA Electricians | 480 | 0
MDC1.C2.C2450 | Not Started | MDC1-BL.5.3.9.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-02-09 07:00 | 2021-03-04 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C1.C4460: FS, MDC1.C2.C2350: FS | MDC1.C2.Cx4010: FS, MDC1.C2.C4420: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.Cx2060 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | EPMS Checkout / Point to Point | 2021-02-19 08:00 | 2021-03-04 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C1.Cx2020: FS | MDC1.C1.Cx3030: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS, MDC1.C1.Cx2150: FS, MDC1.C1.Cx2150: FF | LINX- TELECOM | 1200 | 0
MDC1.C1.Cx2070 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | Network Startup | 2021-02-19 08:00 | 2021-03-04 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3380: FS, MDC1.C1.Cx2030: FS, MDC1.C1.Cx2020: FS | MDC1.C1.Cx2180: FS, MDC1.C1.Cx2150: FS | LINX- TELECOM | 600 | 0
MDC1AD-1029 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | Concrete Floor Sealing/Epoxy | 2021-02-23 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 43 | 43 |  |  |  |  | MDC1AD-1025: FS, MDC1AD-1010: FS | MDC1-C1.P1900: FS | PCI | 120 | 0
MDC1.C3.C3260 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-18 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C3.C3200: FS | MDC1.C3.C3280: FS, MDC1.C3.C3350: FS |  | 0 | 0
MDC1.C3.C4290 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-25 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C3.C4050: FS, MDC1.C3.C4270: FS, MDC1.C3.C2290: FS | MDC1.C3.C4320: FS, MDC1.C3.C4370: FS, MDC1.C3.C4380: FS, MDC1.S.1900: FS | SURE STEEL | 160 | 0
MDC1.C4.C1190 | Not Started | MDC1-BL.5.3.6.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-02-18 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C3130: FS, MDC1.C4.C1140: FS | MDC1.C4.C3180: FS, MDC1.C4.C1220: SS 6 | VECA Electricians | 1200 | 0
MDC1.C4.C2190 | Not Started | MDC1-BL.5.3.6.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-02-18 07:00 | 2021-03-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 4 | 4 |  |  |  |  | MDC1.C4.C4130: FS, MDC1.C4.C2140: FS | MDC1.C4.C4180: FS, MDC1.C4.C2220: SS 6 | VECA Electricians | 1200 | 0
MDC1-C1.P1900 | Not Started | MDC1-BL.3.2 | Finish Milestone | Admin / COLO 1 CSA complete |  | 2021-03-02 17:00 |  |  | 2021-03-02 17:00 |  | 0 | 0 | 0 | 0 | 43 | 43 |  |  |  |  | MDC1AD-1029: FS, MDC1AD-1026: FS, MDC1.C1.C4420: FS, MDC1.C1.C4430: FS, MDC1.C1.C1450: FS, MDC1.C1.C1350: FS, MDC1.C1.C2330: FS, MDC1.C1.C1450: SS, MDC1.C1.C3400: FS, MDC1.C1.C2400: FS, MDC1.C1.C4390: FS | MDC1.C1.Cx3040: FS |  | 0 | 0
MDC1.C3.C1320 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-02-17 07:00 | 2021-03-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C3.C1240: FS, MDC1.C3.C1280: FS | MDC1.C3.C1380: FS, MDC1.C3.C3280: FS | VECA Electricians | 560 | 0
MDC1.C2.C1450 | Not Started | MDC1-BL.5.3.9.4.1.4 | Task Dependent | Controls Installation | 2021-02-13 08:00 | 2021-03-01 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 6 | 6 |  |  |  |  | MDC1.C2.C1080: FS, MDC1.C2.C1120: FS, MDC1.C2.C1190: FS, MDC1.C2.C1430: FS | MDC1.C2.Cx2010: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C3.C1310 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | Cable Tray Installation | 2021-02-13 07:00 | 2021-02-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3210: FS, MDC1.C3.C1270: FS | MDC1.C3.C3270: FS, MDC1.C3.C1370: FS, MDC1.C3.C1350: FS, MDC1.C3.C1440: FS, MDC1.C3.C1340: FF 6 | VECA Electricians | 1440 | 0
MDC1.C3.C2310 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | Cable Tray Installation | 2021-02-13 07:00 | 2021-02-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4170: FS, MDC1.C3.C2280: FS | MDC1.C3.C2360: FS, MDC1.C3.C4310: FS, MDC1.C3.C2340: FS, MDC1.C3.C2430: FS, MDC1.C3.C2320: FF 6 | VECA Electricians | 1440 | 0
MDC1.C2.C1440 | Not Started | MDC1-BL.5.3.9.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-02-03 07:00 | 2021-02-26 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 61 | 61 |  |  |  |  | MDC1.C1.C3460: FS, MDC1.C2.C1340: FS | MDC1.C2.Cx4010: FS, MDC1.C2.C3460: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C1180 | Not Started | MDC1-BL.5.3.6.4.5.2 | Task Dependent | Hydronic Piping Installation | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C1170: FS | MDC1.C4.Cx2000: FF | TCM | 480 | 0
MDC1.C4.C3140 | Not Started | MDC1-BL.5.3.6.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C1150: FS, MDC1.C4.C1130: FS | MDC1.C4.C3160: FS, MDC1.C4.C3170: FS, MDC1.C4.C3150: FS, MDC1.C4.E1320: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C4.C2180 | Not Started | MDC1-BL.5.3.6.4.7.2 | Task Dependent | Hydronic Piping Installation | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C2170: FS | MDC1.C4.Cx2010: FF | TCM | 480 | 0
MDC1.C4.C4140 | Not Started | MDC1-BL.5.3.6.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-02-12 07:00 | 2021-02-25 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C2150: FS, MDC1.C4.C2130: FS | MDC1.C4.C4160: FS, MDC1.C4.C4170: FS, MDC1.C4.C4150: FS, MDC1.C4.E1330: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C2.C3430 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-02-02 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C2.C3120: FS, MDC1.C2.C3080: FS, MDC1.C2.C3270: FS, MDC1.C2.C3310: FS, MDC1.C2.C3340: FS | MDC1.C2.C3440: FS, MDC1.C2.C3450: FS | VECA Electricians | 1080 | 0
MDC1.C2.C4370 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4310: FS, MDC1.C2.C4060: FS, MDC1.C2.C4250: FS, MDC1.C2.C2420: FS | MDC1.C2.Cx2030: FS, MDC1.C2.C4390: FS | VECA Electricians | 960 | 0
MDC1.C3.C1290 | Not Started | MDC1-BL.5.3.8.4.5.3 | Task Dependent | Floor Drain System Installation | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C1030: FS, MDC1.C3.C1250: FS | MDC1-C3.P1900: FS |  | 0 | 0
MDC1.C3.C1300 | Not Started | MDC1-BL.5.3.8.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C1250: FS | MDC1-C3.P1900: FS | TCM | 480 | 0
MDC1.C3.C3240 | Not Started | MDC1-BL.5.3.8.3.2.2 | Task Dependent | Datahall Finishes | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C3190: FS | MDC1-C3.P1900: FS | PCI | 480 | 0
MDC1.C3.C4260 | Not Started | MDC1-BL.5.3.8.3.4.2 | Task Dependent | Datahall Finishes | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 130 | 130 |  |  |  |  | MDC1.C3.C4230: FS | MDC1-C3.P1900: FS | PCI | 480 | 0
MDC1.C3.C4270 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Lift & Set MER in Place | 2021-02-19 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C3.E1370: FS, MDC1.C3.E1270: FS, MDC1.C3.C4050: FS, MDC1.C3.C3200: FS | MDC1.C3.C4290: FS, MDC1.C3.C4300: FS, MDC1.C4.C1230: FS | VECA Electricians | 120 | 0
MDC1.C3.C3250 | Not Started | MDC1-BL.5.3.8.4.10.1 | Task Dependent | HAC Installation | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C3190: FS | MDC1.C3.C3270: FS | TCM | 480 | 0
MDC1.C3.C4280 | Not Started | MDC1-BL.5.3.8.4.13.1 | Task Dependent | HAC Installation | 2021-02-11 07:00 | 2021-02-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C4230: FS | MDC1.C3.C4310: FS | TCM | 480 | 0
MDC1.AD.Cx2010 | Not Started | MDC1-BL.5.2.5.1 | Task Dependent | Network Startup | 2021-02-10 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 20 | 20 |  |  |  |  | MDC1AD-1027: FS, MDC1.AD.Cx2000: FS | MDC1.AD.Cx2020: FS | LINX- TELECOM | 720 | 0
MDC1.C1.Cx2040 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | Network Startup | 2021-02-12 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2370: FS, MDC1.C1.Cx2010: FS | MDC1.C1.Cx2090: FS, MDC1.C1.Cx2110: FS, MDC1.C1.Cx2100: FS | LINX- TELECOM | 600 | 0
MDC1.C1.Cx2050 | Not Started | MDC1-BL.5.2.3.6.4 | Task Dependent | Equipment Yellow Tagging | 2021-02-12 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C4210: FS, MDC1.C1.C4360: FS, MDC1.C1.C4380: FS, MDC1.C1.C4300: FS, MDC1.C1.C4440: FS, MDC1.C1.C4290: FS, MDC1.C1.C4150: FS, MDC1.C1.C4470: FS, MDC1.C1.C4040: FS, MDC1.C1.C4450: FS, MDC1.C1.Cx2010: FS | MDC1.C1.Cx2100: FS, MDC1.C1.Cx2120: SS 6 | VECA Electricians | 1200 | 0
MDC1.C3.C2300 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-12 07:00 | 2021-02-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C3.C2260: FS | MDC1.C3.C2330: FS, MDC1.C3.C2330: FF |  | 0 | 0
MDC1AD-1010 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | Loading Dock Equipment & Dock Doors | 2021-01-29 07:00 | 2021-02-22 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 43 | 43 |  |  |  |  | MDC1-C1.P1200: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1.C1.CS1110: FS, MDC1AD-1025: FS | MDC1AD-1029: FS | VECA Electricians | 400 | 0
MDC1.C2.C2430 | Not Started | MDC1-BL.5.3.9.4.3.4 | Task Dependent | Controls Installation | 2021-02-09 07:00 | 2021-02-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C2.C2060: FS, MDC1.C2.C2170: FS, MDC1.C2.C2230: FS, MDC1.C2.C2410: FS | MDC1.C2.Cx2000: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C3.C3230 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-18 07:00 | 2021-02-22 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 10 | 10 |  |  |  |  | MDC1.C3.C3050: FS, MDC1.C3.C3200: FS, MDC1.C3.C1240: FS | MDC1.C3.C3280: FS, MDC1.C3.C3330: FS, MDC1.C3.C3350: FS | SURE STEEL | 160 | 0
MDC1.C2.C3420 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-02-15 07:00 | 2021-02-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 11 | 11 |  |  |  |  | MDC1.C2.C3360: FS, MDC1.C2.C3370: FS, MDC1.C2.C3290: FS | MDC1-C2.P1800: FS | VECA Electricians | 480 | 0
MDC1.C2.C4360 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-02-15 07:00 | 2021-02-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 11 | 11 |  |  |  |  | MDC1.C2.C4320: FS, MDC1.C2.C4330: FS, MDC1.C2.C4240: FS | MDC1-C2.P1800: FS, MDC1-C2.P1800: SS | VECA Electricians | 480 | 0
MDC1-C2.P1800 | Not Started | MDC1-BL.3.3 | Finish Milestone | COLO 2 CSA complete |  | 2021-02-20 17:00 |  |  | 2021-02-20 17:00 |  | 0 | 0 | 0 | 0 | 11 | 11 |  |  |  |  | MDC1.C2.C4360: FS, MDC1.C2.C3400: FS, MDC1.C2.C3410: FS, MDC1.C2.C1420: FS, MDC1.C2.C3420: FS, MDC1.C2.C2400: FS, MDC1.C2.C4360: SS, MDC1.C2.C1360: FS, MDC1.C2.C2360: FS, MDC1.C2.C4340: FS, MDC1.C2.C1370: FS, MDC1.C2.C2310: FS, MDC1.C2.C4350: FS | MDC1.M1010: FS, MDC1.C1.Cx4020: FS, MDC1.C2.Cx2030: FS, MDC1.C2.Cx2000: FS, MDC1.C2.Cx2050: FS, MDC1.C2.Cx2010: FS |  | 0 | 0
MDC1.C1.Cx2020 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | Network Startup | 2021-02-08 08:00 | 2021-02-19 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.Cx2000: FS, MDC1-1976: FS, MDC1-C1.P1800: FS | MDC1.C1.Cx2060: FS, MDC1.C1.Cx2080: FS, MDC1.C1.Cx2070: FS | LINX- TELECOM | 600 | 0
MDC1.C1.Cx2030 | Not Started | MDC1-BL.5.2.3.6.2 | Task Dependent | Equipment Yellow Tagging | 2021-02-08 08:00 | 2021-02-19 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3360: FS, MDC1.C1.C3380: FS, MDC1.C1.C3310: FS, MDC1.C1.C3410: FS, MDC1.C1.C3150: FS, MDC1.C1.C3230: FS, MDC1.C1.C3450: FS, MDC1.C1.C3470: FS, MDC1.C1.C3040: FS, MDC1.C1.C3330: FS, MDC1.C1.Cx2000: FS | MDC1.C1.Cx2070: FS, MDC1.C1.Cx2160: FS | VECA Electricians | 1200 | 0
MDC1.C3.C3210 | Not Started | MDC1-BL.5.3.8.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C3030: FS, MDC1.C3.C3160: FS | MDC1-C3.P1900: FS |  | 0 | 0
MDC1.C3.C3220 | Not Started | MDC1-BL.5.3.8.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C3160: FS | MDC1-C3.P1900: FS | TCM | 480 | 0
MDC1.C3.C4240 | Not Started | MDC1-BL.5.3.8.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C4030: FS, MDC1.C3.C4200: FS | MDC1-C3.P1900: FS |  | 0 | 0
MDC1.C3.C4250 | Not Started | MDC1-BL.5.3.8.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-04 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 135 | 135 |  |  |  |  | MDC1.C3.C4200: FS | MDC1-C3.P1900: FS | TCM | 480 | 0
MDC1.S.1850 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Yellow Tagging for UMS | 2021-01-18 07:00 | 2021-02-18 17:00 |  |  |  |  | 0 | 0 | 27 | 27 | 0 | 0 |  |  |  |  | MDC1.S.1810: FF, MDC1.S.1660: FF, MDC1.S.1530: FF, MDC1.S.1610: FF, MDC1.S.1450: FF, MDC1.S.1430: FF, MDC1.S.1800: FS, MDC1.S.1780: FS, MDC1.S.1810: FS, MDC1.S.1660: FS, MDC1.S.1530: FS, MDC1.S.1610: FS, MDC1.S.1790: FS, MDC1.S.1450: FS, MDC1.S.1430: FS, MDC1.S.1760: FS, MDC1.S.1490: FS, MDC1.S.1820: FS, MDC1.S.1570: FS, MDC1-P1050: FS | MDC1.C1.Cx3030: FS, MDC1.C1.Cx2140: FS, MDC1.C1.Cx2160: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2120: FS | VECA Electricians | 540 | 0
MDC1.C1.C4480 | Not Started | MDC1-BL.5.3.1.4.8.1 | Task Dependent | Ligthing Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C2470: FF, MDC1.C1.C2470: FS, MDC1.C1.C4240: FS, MDC1.C1.C4350: FS | MDC1.C2.C2440: FS, MDC1.C1.C4490: FS | VECA Electricians | 480 | 0
MDC1.C2.C3390 | Not Started | MDC1-BL.5.3.9.4.6.1 | Task Dependent | Ligthing Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 112 | 112 |  |  |  |  | MDC1.C2.C1350: FS, MDC1.C2.C3350: FS | MDC1.C3.C1330: FS | VECA Electricians | 480 | 0
MDC1.C2.C3400 | Not Started | MDC1-BL.5.3.9.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C3100: FS, MDC1.C2.C3350: FS | MDC1-C2.P1800: FS |  | 0 | 0
MDC1.C2.C3410 | Not Started | MDC1-BL.5.3.9.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C3350: FS | MDC1-C2.P1800: FS | TCM | 480 | 0
MDC1.C2.C4340 | Not Started | MDC1-BL.5.3.9.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C4080: FS, MDC1.C2.C4300: FS | MDC1-C2.P1800: FS |  | 0 | 0
MDC1.C2.C4350 | Not Started | MDC1-BL.5.3.9.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-02-03 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 14 | 14 |  |  |  |  | MDC1.C2.C4300: FS | MDC1-C2.P1800: FS | TCM | 480 | 0
MDC1.C4.C3130 | Not Started | MDC1-BL.5.3.6.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-12 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C4.C1140: FS | MDC1.C4.C1190: FS, MDC1.C4.C3180: FS | TCM, VECA Electricians | 800 | 0
MDC1.C4.C4130 | Not Started | MDC1-BL.5.3.6.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-12 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C4.C2140: FF, MDC1.C4.C2140: FS | MDC1.C4.C2190: FS, MDC1.C4.C4180: FS | TCM, VECA Electricians | 800 | 0
MDC1.C1.C4490 | Not Started | MDC1-BL.5.3.1.4.8.4 | Finish Milestone | Mechanical Corridor complete |  | 2021-02-17 17:00 |  |  | 2021-02-17 17:00 |  | 0 | 0 | 0 | 0 | 70 | 70 |  |  |  |  | MDC1.C1.C4430: FS, MDC1.C1.C4420: FS, MDC1.C1.C2360: FS, MDC1.C1.C2350: FS, MDC1.C1.C3440: FS, MDC1.C1.C3430: FS, MDC1.C1.C1370: FS, MDC1.C1.C1380: FS, MDC1.C1.C1470: FS, MDC1.C1.C3420: FS, MDC1.C1.C2470: FS, MDC1.C1.C4480: FS, MDC1.C1.C4290: FS | MDC1.M1010: FS |  | 0 | 0
MDC1.S.1840 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Yellow Tagging for URS | 2021-01-18 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 26 | 26 | 1 | 1 |  |  |  |  | MDC1.S.1800: FS, MDC1.S.1780: FS, MDC1.S.1810: FS, MDC1.S.1660: FS, MDC1.S.1530: FS, MDC1.S.1610: FS, MDC1.S.1790: SS 4, MDC1.S.1450: FS, MDC1.S.1430: FS, MDC1.S.1760: FS, MDC1.S.1490: FS, MDC1.S.1310: FS, MDC1-P1050: FS | MDC1.C1.Cx2140: FS, MDC1.C1.Cx2080: FS, MDC1.C1.Cx2160: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2120: FS | VECA Electricians | 540 | 0
MDC1.C3.C3200 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Lift & Set MER in Place | 2021-02-12 07:00 | 2021-02-17 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C3.E1360: FS, MDC1.C3.E1260: FS, MDC1.C3.C3050: FS, MDC1.C3.C2260: FS | MDC1.C3.C3230: FS, MDC1.C3.C3260: FS, MDC1.C3.C4270: FS | VECA Electricians | 120 | 0
MDC1.C2.C3380 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-02-02 07:00 | 2021-02-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 7 | 7 |  |  |  |  | MDC1.C2.C3340: FS, MDC1.C2.C3080: FS, MDC1.C2.C3270: FS | MDC1.C2.Cx2050: FS, MDC1.C2.C3450: FS | VECA Electricians | 960 | 0
MDC1.C3.C1280 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-02-04 07:00 | 2021-02-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.C3.C1230: FS | MDC1.C3.C1320: FS, MDC1.C3.C1360: FS |  | 0 | 0
MDC1.C3.C2290 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-12 07:00 | 2021-02-16 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 5 | 5 |  |  |  |  | MDC1.C3.C2050: FS, MDC1.C3.C2260: FS | MDC1.C3.C2330: FS, MDC1.C3.C2380: FS, MDC1.C3.C2350: FS, MDC1.C3.C4290: FS | SURE STEEL | 160 | 0
MDC1.C2.C3370 | Not Started | MDC1-BL.5.3.9.4.10.3 | Task Dependent | Controls Installation | 2021-01-30 07:00 | 2021-02-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C3210: FS, MDC1.C2.C3220: FS, MDC1.C2.C3330: FS | MDC1.C2.C3420: FS, MDC1.C2.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.C2.C4330 | Not Started | MDC1-BL.5.3.9.4.13.3 | Task Dependent | Controls Installation | 2021-01-30 07:00 | 2021-02-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C4170: FS, MDC1.C2.C4200: FS, MDC1.C2.C4290: FS | MDC1.C2.C4360: FS, MDC1.C2.Cx2030: FS 5, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C2.C1430 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-01-20 08:00 | 2021-02-13 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C1120: FS, MDC1.C2.C1080: FS, MDC1.C2.C1290: FS, MDC1.C2.C1330: FS, MDC1.C2.C1380: FS | MDC1.C2.C1450: FS, MDC1.C2.C1460: FS | VECA Electricians | 1080 | 0
MDC1.C3.C1260 | Not Started | MDC1-BL.5.3.8.3.1.2 | Task Dependent | Datahall Finishes | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C3.C1220: FS | MDC1-C3.P1800: FS | PCI | 480 | 0
MDC1.C3.C2270 | Not Started | MDC1-BL.5.3.8.3.3.2 | Task Dependent | Datahall Finishes | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C3.C2250: FS | MDC1-C3.P1800: FS | PCI | 480 | 0
MDC1.C3.C1270 | Not Started | MDC1-BL.5.3.8.4.9.1 | Task Dependent | HAC Installation | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C1220: FS | MDC1.C3.C1310: FS | TCM | 480 | 0
MDC1.C3.C2280 | Not Started | MDC1-BL.5.3.8.4.11.1 | Task Dependent | HAC Installation | 2021-01-29 07:00 | 2021-02-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2250: FS | MDC1.C3.C2310: FS | TCM | 480 | 0
MDC1.C1.Cx2010 | Not Started | MDC1-BL.5.2.3.6.3 | Task Dependent | Equipment Yellow Tagging | 2021-01-30 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2380: FS, MDC1.C1.C2370: FS, MDC1.C1.C2320: FS, MDC1.C1.C2140: FS, MDC1.C1.C2430: FS, MDC1.C1.C2300: FS, MDC1.C1.C2450: FS, MDC1.C1.C2460: FS, MDC1.C1.C2040: FS, MDC1.C1.C2310: FF 6 | MDC1.C1.Cx2040: FS, MDC1.C1.Cx2130: FS, MDC1.C1.Cx2050: FS | VECA Electricians | 1200 | 0
MDC1.C1.C4470 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Pull Conductors into Building | 2021-01-22 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 17 | 17 | 0 | 0 |  |  |  |  | MDC1.C1.C4090: FS, MDC1.C1.C4440: FS | MDC1.C1.Cx2050: FS | VECA Electricians | 1440 | 0
MDC1.C2.C3360 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-18 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 13 | 13 |  |  |  |  | MDC1.C2.C3290: FS | MDC1.C2.C3420: FS, MDC1.C2.Cx2050: FS | VECA Electricians | 1680 | 0
MDC1.C2.C4320 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-18 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 13 | 13 |  |  |  |  | MDC1.C2.C4240: FS | MDC1.C2.C4360: FS, MDC1.C2.Cx2030: FS | VECA Electricians | 1680 | 0
MDC1.C4.C1140 | Not Started | MDC1-BL.5.3.6.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-05 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C3.C3180: FS, MDC1.C3.C3060: FS, MDC1.C4.CS1090: FS, MDC1-C4.P1500: FS | MDC1.C4.C3130: FS, MDC1.C4.C1190: FS | TCM, VECA Electricians | 800 | 0
MDC1.C4.C1150 | Not Started | MDC1-BL.5.3.6.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C1130: FS | MDC1.C4.C1200: FS, MDC1.C4.C3140: FS | VECA Electricians | 960 | 0
MDC1.C4.C1160 | Not Started | MDC1-BL.5.3.6.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C4.C1130: FS | MDC1.C4.C1300: FS, MDC1.C4.C1210: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C4.C1170 | Not Started | MDC1-BL.5.3.6.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C1130: FS, MDC1.C4.E1280: FS, MDC1.C4.E1300: FS | MDC1.C4.C1180: FS | TCM | 480 | 0
MDC1.C4.C2140 | Not Started | MDC1-BL.5.3.6.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2021-02-05 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 4 | 4 |  |  |  |  | MDC1.C3.C4220: FS, MDC1.C3.C4060: FS | MDC1.C4.C4130: FF, MDC1.C4.C4130: FS, MDC1.C4.C2190: FS | TCM, VECA Electricians | 800 | 0
MDC1.C4.C2150 | Not Started | MDC1-BL.5.3.6.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C4.C2130: FS | MDC1.C4.C4140: FS, MDC1.C4.C2200: FS | VECA Electricians | 960 | 0
MDC1.C4.C2160 | Not Started | MDC1-BL.5.3.6.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C4.C2130: FS | MDC1.C4.C2370: FS, MDC1.C4.C2210: FS, MDC1.C4.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C4.C2170 | Not Started | MDC1-BL.5.3.6.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2021-01-28 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C4.C2130: FS, MDC1.C4.E1290: FS, MDC1.C4.E1310: FS | MDC1.C4.C2180: FS | TCM | 480 | 0
MDC1.C3.C2260 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Lift & Set MER in Place | 2021-02-05 07:00 | 2021-02-11 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C3.E1350: FS, MDC1.C3.E1130: FS, MDC1.C3.C2050: FS, MDC1.C3.C1230: FS | MDC1.C3.C2290: FS, MDC1.C3.C2300: FS, MDC1.C3.C3200: FS | VECA Electricians | 120 | 0
MDC1.C2.C2420 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-01-27 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2060: FS, MDC1.C2.C2330: FS, MDC1.C2.C2370: FS | MDC1.C2.Cx2000: FS, MDC1.C2.C2460: FS, MDC1.C2.C4370: FS | VECA Electricians | 960 | 0
MDC1.C3.C1250 | Not Started | MDC1-BL.5.3.8.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-20 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 118 | 118 |  |  |  |  | MDC1.C3.C1120: FS, MDC1.C3.C1030: FS, MDC1.C2.C1360: FS | MDC1.C3.C1330: FS, MDC1.C3.C1300: FS, MDC1-C3.P1900: FS, MDC1.C3.C1290: FS | PCI | 180 | 0
MDC1.C3.C3190 | Not Started | MDC1-BL.5.3.8.3.2.1 | Task Dependent | Hang Wall Partitions | 2021-02-01 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 2 | 2 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C3180: SS 6 | MDC1.C3.C3240: FS, MDC1.C3.C3250: FS | PCI | 600 | 0
MDC1.C3.C4230 | Not Started | MDC1-BL.5.3.8.3.4.1 | Task Dependent | Hang Wall Partitions | 2021-02-01 07:00 | 2021-02-10 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 2 | 2 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C4220: SS 6 | MDC1.C3.C4260: FS, MDC1.C3.C4280: FS | PCI | 600 | 0
MDC1.AD.Cx2000 | Not Started | MDC1-BL.5.2.5.1 | Task Dependent | Level 2 Cx Admin | 2021-01-26 07:00 | 2021-02-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 20 | 20 |  |  |  |  | MDC1AD-1019: FS, MDC1AD-1027: FS, MDC1AD-1023: FS, MDC1-P1050: FS, MDC1-1969: FS 10, MDC1-1967: FS, MDC1-1971: FS, MDC1AD-1022: FS | MDC1.AD.Cx2010: FS, MDC1.M1010: FS, MDC1.C1.Cx3050: FS |  | 0 | 0
MDC1.C3.C1240 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-02-04 07:00 | 2021-02-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 9 | 9 |  |  |  |  | MDC1.C3.C1230: FS | MDC1.C3.C1320: FS, MDC1.C3.C1380: FS, MDC1.C3.C1360: FS, MDC1.C3.C3230: FS | SURE STEEL | 160 | 0
MDC1.C2.C2410 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2021-01-14 07:00 | 2021-02-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C2.C2170: FS, MDC1.C2.C2060: FS, MDC1.C2.C2330: FS, MDC1.C2.C2340: FS | MDC1.C2.C2430: FS, MDC1.C2.C4380: FS | VECA Electricians | 1080 | 0
MDC1.C2.C4310 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-27 07:00 | 2021-02-08 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C2.C4250: FS, MDC1.C2.C4280: FS, MDC1.C2.C2370: FS | MDC1.C2.C4370: FS | VECA Electricians | 560 | 0
MDC1.C1.C4460 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-01-14 07:00 | 2021-02-08 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C1.C2440: FS, MDC1.C1.C4380: FS | MDC1.C2.Cx4010: FS, MDC1.C1.Cx4000: FS, MDC1.C2.C2450: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.Cx2000 | Not Started | MDC1-BL.5.2.3.6.1 | Task Dependent | Equipment Yellow Tagging | 2021-01-25 08:00 | 2021-02-08 08:00 |  |  |  |  | 0 | 0 | 11 | 11 | 0 | 0 |  |  |  |  | MDC1.C1.C1410: FS, MDC1.C1.C1400: FS, MDC1.C1.C1390: FS, MDC1.C1.C1340: FS, MDC1.C1.C1420: FS, MDC1-P1050: FS, MDC1.C1.C1460: FS, MDC1.C1.C1440: FS, MDC1.C1.C1320: FS, MDC1.C1.C1330: FS, MDC1.C1.C1130: FS, MDC1.C1.C1040: FS, MDC1.C1.C1290: FF, MDC1.C1.C3340: FF, MDC1.C1.C2260: FF, MDC1.C1.C4320: FF | MDC1.C1.Cx2020: FS, MDC1.C1.Cx2140: FS, MDC1.C1.Cx2030: FS | VECA Electricians | 1200 | 0
MDC1.C1.C3470 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Pull Conductors into Building | 2021-01-13 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.C3080: FS, MDC1.C1.C3410: FS | MDC1.C1.Cx2030: FS | VECA Electricians | 1440 | 0
MDC1.C1.C4450 | Not Started | MDC1-BL.5.3.1.4.4.4 | Task Dependent | Controls Installation | 2021-01-19 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 16 | 16 | 4 | 4 |  |  |  |  | MDC1.C1.C4090: FS, MDC1.C1.C4120: FS, MDC1.C1.C4170: FS, MDC1.C1.C4410: FS | MDC1.C1.Cx2050: FS | VECA Electricians | 640 | 0
MDC1.C2.C1420 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-01-30 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 23 | 23 |  |  |  |  | MDC1.C2.C1400: FS, MDC1.C2.C1300: FS | MDC1-C2.P1800: FS | VECA Electricians | 480 | 0
MDC1.C2.C2400 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Light Fixtures Installation | 2021-01-30 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 23 | 23 |  |  |  |  | MDC1.C2.C2380: FS, MDC1.C2.C2390: FS, MDC1.C2.C2280: FS | MDC1-C2.P1800: FS | VECA Electricians | 480 | 0
MDC1.C4.C3120 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-23 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 99 | 99 |  |  |  |  | MDC1.C4.C3110: SS 5 | MDC1.C4.Cx2030: FS | TCM | 720 | 0
MDC1.C4.C4120 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-23 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 99 | 99 |  |  |  |  | MDC1.C4.C4110: SS 5 | MDC1.C4.Cx2050: FS | TCM | 720 | 0
MDC1.S.1830 | Not Started | MDC1-BL.5.1.9 | Task Dependent | Telecom-RNG Fiber CNR buildout | 2020-12-02 07:00 | 2021-02-05 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 79 | 79 |  |  |  |  | MDC1.S.1540: FS | MDC1.C1.Cx4000: FS | LINX- TELECOM | 5000 | 0
MDC1.C3.C3180 | Not Started | MDC1-BL.5.3.8.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-25 07:00 | 2021-02-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C1210: FS, MDC1.C3.C3060: FS | MDC1.C4.C1140: FS, MDC1.C3.C3190: SS 6 | VECA Electricians | 1200 | 0
MDC1.C3.C4220 | Not Started | MDC1-BL.5.3.8.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-25 07:00 | 2021-02-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C3.C2240: FS, MDC1.C3.C4060: FS | MDC1.C4.C2140: FS, MDC1.C3.C4230: SS 6 | VECA Electricians | 1200 | 0
MDC1.C3.C3160 | Not Started | MDC1-BL.5.3.8.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 135 | 135 |  |  |  |  | MDC1.C3.C3120: FS, MDC1.C3.C3030: FS | MDC1.C3.C3290: FS, MDC1.C3.C3220: FS, MDC1-C3.P1900: FS, MDC1.C3.C3210: FS | PCI | 180 | 0
MDC1.C3.C3170 | Not Started | MDC1-BL.5.3.8.4.6.4 | Task Dependent | Controls Installation | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C3.C3130: FS, MDC1.C3.C3100: FS | MDC1.C3.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C3.C4200 | Not Started | MDC1-BL.5.3.8.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 135 | 135 |  |  |  |  | MDC1.C3.C4150: FS, MDC1.C3.C4030: FS | MDC1.C3.C4400: FS, MDC1.C3.C4250: FS, MDC1-C3.P1900: FS, MDC1.C3.C4240: FS | PCI | 180 | 0
MDC1.C3.C4210 | Not Started | MDC1-BL.5.3.8.4.8.4 | Task Dependent | Controls Installation | 2021-01-13 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 67 | 67 |  |  |  |  | MDC1.C3.C4160: FS, MDC1.C3.C4120: FS | MDC1.C3.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.C3.C1230 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Lift & Set MER in Place | 2021-01-29 07:00 | 2021-02-03 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.C3.E1340: FS, MDC1.C3.E1120: FS, MDC1.C3.C1050: FS, MDC1-C3.P1600: FS, MDC1.C2.C4220: FS | MDC1.C3.C1240: FS, MDC1.C3.C1280: FS, MDC1.C3.C2260: FS | VECA Electricians | 120 | 0
MDC1.C2.C1410 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-01-20 08:00 | 2021-02-03 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C2.C1380: FS, MDC1.C2.C1080: FS, MDC1.C2.C1290: FS | MDC1.C2.Cx2010: FS, MDC1.C2.C1460: FS | VECA Electricians | 960 | 0
MDC1.C1.C1470 | Not Started | MDC1-BL.5.3.1.4.5.1 | Task Dependent | Ligthing Installation | 2021-01-20 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 82 | 82 |  |  |  |  | MDC1.C1.C3420: FS, MDC1.C1.C1220: FS, MDC1.C1.C1310: FS | MDC1.C1.C4490: FS | VECA Electricians | 480 | 0
MDC1.C1.C2470 | Not Started | MDC1-BL.5.3.1.4.7.1 | Task Dependent | Ligthing Installation | 2021-01-20 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C3420: FS, MDC1.C1.C2200: FS, MDC1.C1.C2290: FS | MDC1.C1.C4480: FF, MDC1.C1.C4480: FS, MDC1.C1.C4490: FS | VECA Electricians | 480 | 0
MDC1.C2.C3350 | Not Started | MDC1-BL.5.3.9.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-12 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 14 | 14 |  |  |  |  | MDC1.C2.C3240: FS, MDC1.C2.C3100: FS | MDC1.C2.C3390: FS, MDC1.C2.C3410: FS, MDC1.C2.C3400: FS | PCI | 180 | 0
MDC1.C2.C4300 | Not Started | MDC1-BL.5.3.9.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2021-01-12 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 14 | 14 |  |  |  |  | MDC1.C2.C4180: FS, MDC1.C2.C4080: FS | MDC1.C2.C4410: FS, MDC1.C2.C4350: FS, MDC1.C2.C4340: FS | PCI | 180 | 0
MDC1.C1.C3460 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2021-01-09 07:00 | 2021-02-02 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 61 | 61 |  |  |  |  | MDC1.C1.C1430: FS, MDC1.C1.C3380: FS | MDC1.C2.Cx4010: FS, MDC1.C1.Cx4000: FS, MDC1.C2.C1440: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C3340 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-21 07:00 | 2021-02-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3270: FS, MDC1.C2.C3310: FS | MDC1.C2.C3380: FS, MDC1.C2.C3430: FS | VECA Electricians | 560 | 0
MDC1.C4.C3110 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-18 07:00 | 2021-01-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C3080: FS, MDC1.C4.E1240: FS, MDC1.C4.E1250: FS | MDC1.C4.C3390: FS, MDC1.C4.C3120: SS 5, MDC1.C4.C3370: FS, MDC1.C4.C3410: FS | TCM | 720 | 0
MDC1.C4.C4110 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-18 07:00 | 2021-01-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C4080: FS, MDC1.C4.E1260: FS, MDC1.C4.E1270: FS | MDC1.C4.C4390: FS, MDC1.C4.C4120: SS 5, MDC1.C4.C4360: FS, MDC1.C4.C4410: FS | TCM | 720 | 0
MDC1.C1.C3450 | Not Started | MDC1-BL.5.3.1.4.2.4 | Task Dependent | Controls Installation | 2021-01-11 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 16 | 16 | 6 | 6 |  |  |  |  | MDC1.C1.C3080: FS, MDC1.C1.C3130: FS, MDC1.C1.C3180: FS, MDC1.C1.C3390: FS | MDC1.C1.Cx2030: FS | VECA Electricians | 640 | 0
MDC1.C1.C2460 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Pull Conductors into Building | 2021-01-07 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 19 | 19 | 0 | 0 |  |  |  |  | MDC1.C1.C2090: FS, MDC1.C1.C2430: FS | MDC1.C1.Cx2010: FS | VECA Electricians | 1440 | 0
MDC1.C2.C1400 | Not Started | MDC1-BL.5.3.9.4.9.3 | Task Dependent | Controls Installation | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C1230: FS, MDC1.C2.C1240: FS, MDC1.C2.C1340: FS | MDC1.C2.C1420: FS, MDC1.C2.Cx2010: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C2.C3330 | Not Started | MDC1-BL.5.3.9.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C3280: FS | MDC1.C2.C3460: FS, MDC1.C2.Cx2100: FS, MDC1.C2.Cx2050: FS, MDC1.C2.C3370: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C2390 | Not Started | MDC1-BL.5.3.9.4.11.3 | Task Dependent | Controls Installation | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C2220: FS, MDC1.C2.C2240: FS, MDC1.C2.C2350: FS | MDC1.C2.C2400: FS, MDC1.C2.Cx2000: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C2.C4290 | Not Started | MDC1-BL.5.3.9.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2021-01-15 07:00 | 2021-01-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C4230: FS | MDC1.C2.C4420: FS, MDC1.C2.Cx2070: FS, MDC1.C2.Cx2030: FS, MDC1.C2.C4330: FS | LINX- TELECOM | 1440 | 0
MDC1AD-1025 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | Ceilings / Ligthing / FA Devices | 2020-12-11 07:00 | 2021-01-28 17:00 |  |  |  |  | 0 | 0 | 36 | 36 | 43 | 43 |  |  |  |  | MDC1AD-1018: FS, MDC1AD-1024: FS, MDC1AD-1021: FS | MDC1AD-1029: FS, MDC1AD-1010: FS | PCI, VECA Electricians | 2800 | 0
MDC1.C3.C1220 | Not Started | MDC1-BL.5.3.8.3.1.1 | Task Dependent | Hang Wall Partitions | 2021-01-20 07:00 | 2021-01-28 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 0 | 0 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C1210: SS 6 | MDC1.C3.C1260: FS, MDC1.C3.C1270: FS | PCI | 600 | 0
MDC1.C3.C2250 | Not Started | MDC1-BL.5.3.8.3.3.1 | Task Dependent | Hang Wall Partitions | 2021-01-20 07:00 | 2021-01-28 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 0 | 0 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C2240: SS 6 | MDC1.C3.C2270: FS, MDC1.C3.C2280: FS | PCI | 600 | 0
MDC1.C2.C1390 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-02 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 31 | 31 |  |  |  |  | MDC1.C2.C1300: FS | MDC1.C2.Cx2010: FS | VECA Electricians | 1680 | 0
MDC1.C2.C2380 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2021-01-02 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 25 | 25 |  |  |  |  | MDC1.C2.C2280: FS | MDC1.C2.C2400: FS, MDC1.C2.Cx2000: FS | VECA Electricians | 1680 | 0
MDC1.C3.C3150 | Not Started | MDC1-BL.5.3.8.4.6.2 | Task Dependent | Hydronic Piping Installation | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C3140: FS | MDC1.C3.Cx2030: FF | TCM | 480 | 0
MDC1.C3.C4190 | Not Started | MDC1-BL.5.3.8.4.8.2 | Task Dependent | Hydronic Piping Installation | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C4170: FS | MDC1.C3.Cx2050: FF | TCM | 480 | 0
MDC1.C4.C1130 | Not Started | MDC1-BL.5.3.6.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C3120: FS, MDC1.C4.C1010: FS | MDC1.C4.C1160: FS, MDC1.C4.C1170: FS, MDC1.C4.C3140: FS, MDC1.C4.C1150: FS, MDC1.C4.E1300: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C4.C2130 | Not Started | MDC1-BL.5.3.6.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C4150: FS, MDC1.C4.C2010: FS | MDC1.C4.C2160: FS, MDC1.C4.C4140: FS, MDC1.C4.C2150: FS, MDC1.C4.C2170: FS, MDC1.C4.E1290: FS | TCM, VECA Electricians | 1360 | 0
MDC1-1976 | Not Started | MDC1-BL.5.3.2.4.5.4 | Task Dependent | Controls Installation | 2021-01-13 07:00 | 2021-01-27 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1-1963: FS, MDC1-1964: FS, MDC1-1975: FS, MDC1-1968: FS | MDC1.C1.Cx2020: FS | VECA Electricians | 720 | 0
MDC1.C2.C3320 | Not Started | MDC1-BL.5.3.9.4.6.2 | Task Dependent | Hydronic Piping Installation | 2021-01-12 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C3250: FS | MDC1.C2.Cx2050: FF | TCM | 480 | 0
MDC1.C2.C4270 | Not Started | MDC1-BL.5.3.9.4.8.2 | Task Dependent | Hydronic Piping Installation | 2021-01-12 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C4190: FS | MDC1.C2.Cx2030: FF | TCM | 480 | 0
MDC1.C2.C4280 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-01-14 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 2 | 2 |  |  |  |  | MDC1.C2.C4220: FS | MDC1.C2.C4310: FS, MDC1.C2.C4380: FS |  | 0 | 0
MDC1.C2.C2370 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-14 07:00 | 2021-01-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2330: FS, MDC1.C2.C2340: FS | MDC1.C2.C2420: FS, MDC1.C2.C4310: FS | VECA Electricians | 560 | 0
MDC1.C1.C1460 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Pull Conductors into Building | 2020-12-29 08:00 | 2021-01-25 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.C1.C1090: FS, MDC1.C1.C1420: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 1440 | 0
MDC1.C3.C1210 | Not Started | MDC1-BL.5.3.8.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-12 07:00 | 2021-01-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3240: FS, MDC1.C3.C3060: FS, MDC1.C3.C1090: FS | MDC1.C3.C3180: FS, MDC1.C3.C1220: SS 6 | VECA Electricians | 1200 | 0
MDC1.C3.C2240 | Not Started | MDC1-BL.5.3.8.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2021-01-12 07:00 | 2021-01-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C4180: FS, MDC1.C3.C4060: FS, MDC1.C3.C2090: FS | MDC1.C3.C4220: FS, MDC1.C3.C2250: SS 6 | VECA Electricians | 1200 | 0
MDC1.C4.C1120 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-08 07:00 | 2021-01-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C4.C1110: SS 5 | MDC1.C4.C1390: FS, MDC1.C4.Cx2000: FS | TCM | 720 | 0
MDC1.C4.C2120 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2021-01-08 07:00 | 2021-01-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 101 | 101 |  |  |  |  | MDC1.C4.C2110: SS 5 | MDC1.C4.Cx2010: FS | TCM | 720 | 0
MDC1.C1.C2450 | Not Started | MDC1-BL.5.3.1.4.3.4 | Task Dependent | Controls Installation | 2021-01-02 07:00 | 2021-01-21 17:00 |  |  |  |  | 0 | 0 | 16 | 16 | 7 | 7 |  |  |  |  | MDC1.C1.C2090: FS, MDC1.C1.C2120: FS, MDC1.C1.C2410: FS, MDC1.C1.C2420: FS | MDC1.C1.Cx2010: FS | VECA Electricians | 640 | 0
MDC1.C1.C4440 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2021-01-07 07:00 | 2021-01-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C4090: FS, MDC1.C1.C4280: FS, MDC1.C1.C4370: FS | MDC1.C1.Cx2050: FS, MDC1.C1.C4470: FS | VECA Electricians | 960 | 0
MDC1.C2.C3310 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-01-08 07:00 | 2021-01-20 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C3230: FS | MDC1.C2.C3340: FS, MDC1.C2.C3430: FS |  | 0 | 0
MDC1.C3.C2220 | Not Started | MDC1-BL.5.3.8.4.7.3 | Task Dependent | Floor Drain System Installation | 2021-01-06 07:00 | 2021-01-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 159 | 159 |  |  |  |  | MDC1.C3.C2030: FS, MDC1.C3.C2200: FS | MDC1-C3.P1900: FS |  | 0 | 0
MDC1.C3.C2230 | Not Started | MDC1-BL.5.3.8.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-06 07:00 | 2021-01-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 159 | 159 |  |  |  |  | MDC1.C3.C2200: FS | MDC1-C3.P1900: FS | TCM | 480 | 0
MDC1.C2.C1380 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2021-01-07 08:00 | 2021-01-20 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1290: FS, MDC1.C2.C1330: FS | MDC1.C2.C1410: FS, MDC1.C2.C1430: FS | VECA Electricians | 560 | 0
MDC1.C1.C3420 | Not Started | MDC1-BL.5.3.1.4.6.1 | Task Dependent | Ligthing Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C3280: FS, MDC1.C1.C3370: FS | MDC1.C1.C2470: FS, MDC1.C1.C1470: FS, MDC1.C1.C4490: FS | VECA Electricians | 480 | 0
MDC1.C1.C3430 | Not Started | MDC1-BL.5.3.1.4.6.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 94 | 94 |  |  |  |  | MDC1.C1.C3110: FS, MDC1.C1.C3370: FS | MDC1.C1.C4490: FS |  | 0 | 0
MDC1.C1.C3440 | Not Started | MDC1-BL.5.3.1.4.6.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 94 | 94 |  |  |  |  | MDC1.C1.C3370: FS | MDC1.C1.C4490: FS | TCM | 480 | 0
MDC1.C1.C4420 | Not Started | MDC1-BL.5.3.1.4.8.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C1.C4110: FS, MDC1.C1.C4350: FS | MDC1-C1.P1900: FS, MDC1.C1.C4490: FS |  | 0 | 0
MDC1.C1.C4430 | Not Started | MDC1-BL.5.3.1.4.8.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C1.C4350: FS | MDC1-C1.P1900: FS, MDC1.C1.C4490: FS | TCM | 480 | 0
MDC1.C2.C1350 | Not Started | MDC1-BL.5.3.9.4.5.1 | Task Dependent | Ligthing Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 124 | 124 |  |  |  |  | MDC1.C2.C1150: FS, MDC1.C2.C1310: FS | MDC1.C2.C3390: FS | VECA Electricians | 480 | 0
MDC1.C2.C1360 | Not Started | MDC1-BL.5.3.9.4.5.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C2.C1100: FS, MDC1.C2.C1310: FS | MDC1-C2.P1800: FS, MDC1.C3.C1250: FS |  | 0 | 0
MDC1.C2.C1370 | Not Started | MDC1-BL.5.3.9.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C2.C1310: FS | MDC1-C2.P1800: FS | TCM | 480 | 0
MDC1.C2.C3300 | Not Started | MDC1-BL.5.3.9.4.6.4 | Task Dependent | Controls Installation | 2020-12-23 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 48 | 48 |  |  |  |  | MDC1.C2.C3140: FS, MDC1.C2.C3200: FS | MDC1.C2.Cx2050: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C2.C2360 | Not Started | MDC1-BL.5.3.9.4.7.3 | Task Dependent | Floor Drain System Installation | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C2.C2080: SS 6, MDC1.C2.C2300: FS | MDC1-C2.P1800: FS |  | 0 | 0
MDC1.C2.C4250 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-01-14 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 8 | 8 |  |  |  |  | MDC1.C2.C4040: FS, MDC1.C2.C4220: FS, MDC1.C2.C2330: FS | MDC1.C2.C4310: FS, MDC1.C2.C4370: FS, MDC1.C2.C4380: FS, MDC1.S.1900: FS | SURE STEEL | 160 | 0
MDC1.C2.C4260 | Not Started | MDC1-BL.5.3.9.4.8.4 | Task Dependent | Controls Installation | 2020-12-23 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 43 | 43 |  |  |  |  | MDC1.C2.C4160: FS | MDC1.C2.Cx2030: FS 5, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C4.C3100 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 82 | 82 |  |  |  |  | MDC1.C4.C3060: FS, MDC1.C4.E1180: FS, MDC1.C4.E1190: FS | MDC1.C4.C3380: FS, MDC1.C4.C3390: FS, MDC1.C4.C3440: FS, MDC1.C4.C3370: FS, MDC1.C4.C3410: FS | VECA Electricians | 480 | 0
MDC1.C4.C4100 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2021-01-05 07:00 | 2021-01-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 84 | 84 |  |  |  |  | MDC1.C4.C4060: FS, MDC1.C4.E1200: FS, MDC1.C4.E1210: FS | MDC1.C4.C4370: FS, MDC1.C4.C4390: FS, MDC1.C4.C4440: FS, MDC1.C4.C4360: FS, MDC1.C4.C4410: FS | VECA Electricians | 480 | 0
MDC1.C1.C1450 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Light Fixtures Installation | 2021-01-11 07:00 | 2021-01-18 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 78 | 78 |  |  |  |  | MDC1.C1.C3400: FS, MDC1.C1.C1400: FS, MDC1.C1.C1340: FF, MDC1.C1.C1340: FS, MDC1.C1.C1270: FS | MDC1-C1.P1900: FS, MDC1-C1.P1900: SS | VECA Electricians | 480 | 0
MDC1.C1.C4410 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-23 07:00 | 2021-01-18 17:00 |  |  |  |  | 0 | 0 | 17 | 17 | 4 | 4 |  |  |  |  | MDC1.C1.C4120: FS, MDC1.C1.C4090: FS, MDC1.C1.C4280: FS, MDC1.C1.C4340: FS | MDC1.C1.C4450: FS | VECA Electricians | 1080 | 0
MDC1.C1.C1440 | Not Started | MDC1-BL.5.3.1.4.1.4 | Task Dependent | Controls Installation | 2020-12-23 08:00 | 2021-01-18 08:00 |  |  |  |  | 0 | 0 | 16 | 16 | 6 | 6 |  |  |  |  | MDC1.C1.C1090: FS, MDC1.C1.C1110: FS, MDC1.C1.C1160: FS, MDC1.C1.C1410: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 640 | 0
MDC1.C2.C3290 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | PDU's Installation | 2021-01-13 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 13 | 13 |  |  |  |  | MDC1.C2.C3260: FS, MDC1.C2.C3210: FS, MDC1.C2.C3130: FS, MDC1.C2.E1420: FS, MDC1.C2.E1430: FS | MDC1.C2.C3360: FS, MDC1.C2.C3420: FS | VECA Electricians | 180 | 0
MDC1.C2.C4240 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | PDU's Installation | 2021-01-13 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 13 | 13 |  |  |  |  | MDC1.C2.C4210: FS, MDC1.C2.E1440: FS, MDC1.C2.E1450: FS, MDC1.C2.C4110: FS | MDC1.C2.C4320: FS, MDC1.C2.C4360: FS | VECA Electricians | 180 | 0
MDC1.C3.C4180 | Not Started | MDC1-BL.5.3.8.4.4.4 | Task Dependent | Fire Alarm Installation | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C3.C4130: FS, MDC1.C3.C4100: FS | MDC1.C3.C4410: FS | VECA Electricians | 240 | 0
MDC1.C4.C1110 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C1080: FS, MDC1.C4.E1140: FS, MDC1.C4.E1150: FS, MDC1-C4.P1700: FS | MDC1.C4.C1340: FS, MDC1.C4.C1120: SS 5, MDC1.C4.C1390: FS, MDC1.C4.C1410: FS | TCM | 720 | 0
MDC1.C4.C3080 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2021-01-12 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 75 | 75 |  |  |  |  | MDC1.C4.C3070: FS | MDC1.C4.C3110: FS, MDC1.C4.E1240: FS | SURE STEEL | 160 | 0
MDC1.C4.C3090 | Not Started | MDC1-BL.5.3.6.4.6.4 | Task Dependent | Fire Alarm System | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C3050: FS | MDC1.C4.C3250: FS | VECA Electricians | 240 | 0
MDC1.C4.C2110 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C2080: FS, MDC1.C4.E1160: FS, MDC1.C4.E1170: FS | MDC1.C4.C2360: FS, MDC1.C4.C2120: SS 5, MDC1.C4.C2400: FS, MDC1.C4.C2430: FS | TCM | 720 | 0
MDC1.C4.C4080 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2021-01-12 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 75 | 75 |  |  |  |  | MDC1.C4.C4070: FS | MDC1.C4.C4110: FS, MDC1.C4.E1260: FS | SURE STEEL | 160 | 0
MDC1.C4.C4090 | Not Started | MDC1-BL.5.3.6.4.8.4 | Task Dependent | Fire Alarm System | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C4050: FS | MDC1.C4.C4240: FS | VECA Electricians | 240 | 0
MDC1.S.1810 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -4 WEST UPMS | 2021-01-09 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 0 | 0 |  |  |  |  | MDC1.S.1750: FS, MDC1.S.1710: FS, MDC1.S.1800: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0
MDC1.S.1820 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- UMS- Load side | 2021-01-02 07:00 | 2021-01-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.S.1740: FS, MDC1.S.1630: FS, MDC1.S.1650: FS, MDC1.S.1730: FS | MDC1.S.1850: FS | VECA Electricians | 720 | 0
MDC1.C2.C1340 | Not Started | MDC1-BL.5.3.9.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C1280: FS | MDC1.C2.C1440: FS, MDC1.C2.Cx2040: FS, MDC1.C2.Cx2010: FS, MDC1.C2.C1400: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C3280 | Not Started | MDC1-BL.5.3.9.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C3210: FS | MDC1.C2.C3330: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C2350 | Not Started | MDC1-BL.5.3.9.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C2270: FS | MDC1.C2.C2450: FS, MDC1.C2.Cx2020: FS, MDC1.C2.Cx2000: FS, MDC1.C2.C2390: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C4230 | Not Started | MDC1-BL.5.3.9.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-30 07:00 | 2021-01-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C4170: FS | MDC1.C2.C4290: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C3270 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-01-08 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 5 | 5 |  |  |  |  | MDC1.C2.C3050: FS, MDC1.C2.C3230: FS, MDC1.C2.C1290: FS | MDC1.C2.C3340: FS, MDC1.C2.C3380: FS, MDC1.C2.C3430: FS | SURE STEEL | 160 | 0
MDC1.C2.C2340 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2021-01-02 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C2290: FS | MDC1.C2.C2370: FS, MDC1.C2.C2410: FS |  | 0 | 0
MDC1.C2.C4220 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Lift & Set MER in Place | 2021-01-08 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 2 | 2 |  |  |  |  | MDC1.C2.E1410: FS, MDC1.C2.E1200: FS, MDC1.C2.C4040: FS, MDC1.C2.C3230: FS | MDC1.C2.C4250: FS, MDC1.C2.C4280: FS, MDC1.C3.C1230: FS | VECA Electricians | 120 | 0
MDC1.C1.C2440 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | Install Production Fiber (Includes MOR rack set) | 2020-12-16 07:00 | 2021-01-13 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 57 | 57 |  |  |  |  | MDC1.C1.C2370: FS | MDC1.C2.Cx4010: FS, MDC1.C1.Cx4000: FS, MDC1.C1.C4460: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C3410 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C3350: FS, MDC1.C1.C3080: FS, MDC1.C1.C3250: FS | MDC1.C1.Cx2030: FS, MDC1.C1.C3470: FS | VECA Electricians | 960 | 0
MDC1.C1.C4390 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Light Fixtures Installation | 2021-01-06 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 82 | 82 |  |  |  |  | MDC1.C1.C4360: FS, MDC1.C1.C4300: FS, MDC1.C1.C4220: FS | MDC1.C1.C4400: FS, MDC1-C1.P1900: FS | VECA Electricians | 480 | 0
MDC1.C2.C4200 | Not Started | MDC1-BL.5.3.9.4.13.3 | Task Dependent | Fire Alarm System | 2020-12-30 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 25 | 25 |  |  |  |  | MDC1.C2.C4170: FS | MDC1.C2.C4330: FS, MDC1-C2.P1900: FS | VECA Electricians | 600 | 0
MDC1.C3.C3120 | Not Started | MDC1-BL.5.3.8.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C3090: FF, MDC1.C3.C3090: FS | MDC1.C4.C1130: FS, MDC1.C3.C3160: FS | VECA Electricians | 960 | 0
MDC1.C3.C3130 | Not Started | MDC1-BL.5.3.8.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C3090: FS | MDC1.C3.C3290: FS, MDC1.C3.C3170: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C3.C3140 | Not Started | MDC1-BL.5.3.8.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C3090: FS, MDC1.C3.E1300: FS, MDC1.C3.E1320: FS | MDC1.C3.C3150: FS | TCM | 480 | 0
MDC1.C3.C4150 | Not Started | MDC1-BL.5.3.8.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C4110: FS | MDC1.C4.C2130: FS, MDC1.C3.C4200: FS | VECA Electricians | 960 | 0
MDC1.C3.C4160 | Not Started | MDC1-BL.5.3.8.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C4110: FS | MDC1.C3.C4400: FS, MDC1.C3.C4210: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C3.C4170 | Not Started | MDC1-BL.5.3.8.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-28 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C3.C4110: FS, MDC1.C3.E1310: FS, MDC1.C3.E1330: FS | MDC1.C3.C4190: FS | TCM | 480 | 0
MDC1-1968 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-15 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 8 | 8 |  |  |  |  | MDC1AD-1019: FS, MDC1-1963: FS | MDC1-1976: FS | VECA Electricians | 1080 | 0
MDC1-1969 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Pull Conductors into Building | 2020-12-15 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 20 | 20 |  |  |  |  | MDC1AD-1019: FS, MDC1-1963: FS | MDC1.AD.Cx2000: FS 10 | VECA Electricians | 1440 | 0
MDC1.C1.C4400 | Not Started | MDC1-BL.5.3.1.4.13.3 | Finish Milestone | Data Hall complete |  | 2021-01-12 17:00 |  |  | 2021-01-12 17:00 |  | 0 | 0 | 0 | 0 | 94 | 94 |  |  |  |  | MDC1.C1.C4390: FS, MDC1.C1.C2400: FS, MDC1.C1.C3400: FS, MDC1.C1.C4380: FS | MDC1.C1.Cx3050: FS, MDC1.C1.Cx4020: FS |  | 0 | 0
MDC1.C2.C3260 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Power Bus Installation | 2020-12-30 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C3210: FS, MDC1.C2.C3170: FS | MDC1.C2.C3290: FS, MDC1.C2.E1420: FS | VECA Electricians | 1200 | 0
MDC1.C2.C4210 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Power Bus Installation | 2020-12-30 07:00 | 2021-01-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C4170: FS | MDC1.C2.C4240: FS, MDC1.C2.E1440: FS | VECA Electricians | 1200 | 0
MDC1.C1.C4380 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 25 | 25 |  |  |  |  | MDC1.C1.C4330: FS, MDC1.C1.C4180: FS | MDC1.C1.C4460: FS, MDC1.C1.Cx2100: FS, MDC1.C1.Cx2050: FS, MDC1.C1.C4400: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C3240 | Not Started | MDC1-BL.5.3.9.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3190: FS, MDC1.C2.C3190: SS 5 | MDC1.C3.C1210: FS, MDC1.C2.C3350: FS | VECA Electricians | 960 | 0
MDC1.C2.C3250 | Not Started | MDC1-BL.5.3.9.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C3090: FS, MDC1.C2.E1320: FS, MDC1.C2.E1340: FS | MDC1.C2.C3320: FS | TCM | 480 | 0
MDC1.C2.C4180 | Not Started | MDC1-BL.5.3.9.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4150: FS, MDC1.C2.C4150: SS 5 | MDC1.C3.C2240: FS, MDC1.C2.C4300: FS | VECA Electricians | 960 | 0
MDC1.C2.C4190 | Not Started | MDC1-BL.5.3.9.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C4070: FS, MDC1.C2.E1330: FS, MDC1.C2.E1350: FS | MDC1.C2.C4270: FS | TCM | 480 | 0
MDC1.C4.C3070 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C3060: SS 6, MDC1.C4.C3000: FS | MDC1.C4.C3080: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C4.C4070 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-23 07:00 | 2021-01-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 75 | 75 |  |  |  |  | MDC1.C4.C4060: SS 6, MDC1.C4.C4000: FS | MDC1.C4.C4080: FS | CSI, VECA Electricians | 1440 | 0
MDC1AD-1023 | Not Started | MDC1-BL.5.3.2.4.4 | Task Dependent | Mechanical Devices & Trim | 2020-12-15 07:00 | 2021-01-09 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 32 | 32 |  |  |  |  | MDC1AD-1019: FS, MDC1AD-1021: FS | MDC1.AD.Cx2000: FS | TCM | 360 | 0
MDC1.C1.C3390 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-12 07:00 | 2021-01-09 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 6 | 6 |  |  |  |  | MDC1.C1.C3130: FS, MDC1.C1.C3080: FS, MDC1.C1.C3250: FS, MDC1.C1.C3300: FS | MDC1.C1.C3450: FS | VECA Electricians | 1080 | 0
MDC1.C1.C3400 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Light Fixtures Installation | 2021-01-04 07:00 | 2021-01-09 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 78 | 78 |  |  |  |  | MDC1.C1.C3360: FS, MDC1.C1.C3310: FS, MDC1.C1.C3240: FS | MDC1.C1.C1450: FS, MDC1.C1.C4400: FS, MDC1-C1.P1900: FS | VECA Electricians | 480 | 0
MDC1.C4.E1230 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-4 |  | 2021-01-09 17:00 |  |  | 2021-01-09 17:00 |  | 0 | 0 | 0 | 0 | 66 | 66 |  |  |  |  | MDC1.C4.C4060: FS 5 | MDC1.C4.C4250: FS |  | 0 | 0
MDC1.C1.C3380 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-21 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3190: FS, MDC1.C1.C3330: FS | MDC1.C1.C3460: FS, MDC1.C1.Cx2070: FS, MDC1.C1.Cx2030: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.E1220 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-3 |  | 2021-01-08 17:00 |  |  | 2021-01-08 17:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C3060: FS 4 | MDC1.C4.C3210: FS |  | 0 | 0
MDC1.S.1770 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-4 | 2021-01-05 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C4040: FS, MDC1.C4.C2040: FS, MDC1.C4.C3040: FS, MDC1.C4.C1040: FS, MDC1.S.1140: FS, MDC1.S.1180: FS, MDC1.S.1460: FS, MDC1.S.1670: FS, MDC1.S.1580: FS, MDC1.S.1200: FS, MDC1.S.1640: FS, MDC1.S.1750: FS, MDC1-1996: FS | MDC1.S.1790: FF | VECA Electricians | 240 | 0
MDC1.S.1780 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -4 East UPMS | 2021-01-02 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 6 | 6 |  |  |  |  | MDC1.S.1720: FS, MDC1.S.1710: FS, MDC1.S.1660: FS | MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0
MDC1.S.1790 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | TERM- URS- Load Side | 2020-12-21 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.S.1770: FF, MDC1.S.1640: FS, MDC1.S.1500: FS, MDC1.S.1480: FS | MDC1.S.1850: FS, MDC1.S.1840: SS 4, MDC1.S.1800: FF | VECA Electricians | 720 | 0
MDC1.S.1800 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- JAZ to Structure- (Incl Stress Cones) from ums | 2020-12-28 07:00 | 2021-01-08 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 0 | 0 |  |  |  |  | MDC1.S.1700: FS, MDC1.S.1690: FS, MDC1.S.1790: FF | MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1810: FS | VECA Electricians | 360 | 0
MDC1.C2.C3220 | Not Started | MDC1-BL.5.3.9.4.10.3 | Task Dependent | Fire Alarm System | 2020-12-22 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 29 | 29 |  |  |  |  | MDC1.C2.C3210: FF 6 | MDC1.C2.C3370: FS | VECA Electricians | 600 | 0
MDC1.C3.C1200 | Not Started | MDC1-BL.5.3.8.4.1.4 | Task Dependent | Fire Alarm Installation | 2020-12-19 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C1160: FS, MDC1.C3.C1110: FS, MDC1.C3.C1170: FS | MDC1.C3.C1400: FS, MDC1-C3.P1800: FS | VECA Electricians | 240 | 0
MDC1.C3.C4140 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-12-19 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 89 | 89 |  |  |  |  | MDC1.C3.C4130: SS 5 | MDC1.C3.Cx2050: FS | TCM | 720 | 0
MDC1.C2.C3230 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Lift & Set MER in Place | 2021-01-02 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.C3050: FS, MDC1.C2.E1210: FS, MDC1.C2.E1360: FS, MDC1.C2.C2290: FS | MDC1.C2.C3310: FS, MDC1.C2.C3270: FS, MDC1.C2.C4220: FS | VECA Electricians | 120 | 0
MDC1.S.1760 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- JUMS to URS- (Incl Stress Cones) | 2020-12-23 07:00 | 2021-01-07 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 7 | 7 |  |  |  |  | MDC1.S.1600: FS, MDC1.S.1700: FS | MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0
MDC1.C2.C1330 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-12-21 08:00 | 2021-01-07 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C2.C1250: FS | MDC1.C2.C1380: FS, MDC1.C2.C1430: FS |  | 0 | 0
MDC1.C1.C2430 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-18 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C2390: FS, MDC1.C1.C2090: FS, MDC1.C1.C2280: FS | MDC1.C1.Cx2010: FS, MDC1.C1.C2460: FS | VECA Electricians | 960 | 0
MDC1.C2.C2330 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2021-01-02 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C2.C2030: FS, MDC1.C2.C2290: FS | MDC1.C2.C2370: FS, MDC1.C2.C2420: FS, MDC1.C2.C2410: FS, MDC1.C2.C4250: FS | SURE STEEL | 160 | 0
MDC1.C1.C4370 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-12-23 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 0 | 0 |  |  |  |  | MDC1.C1.C4280: FS, MDC1.C1.C4340: FS, MDC1.C1.C2390: FS | MDC1.C1.C4440: FS | VECA Electricians | 560 | 0
MDC1.C1.C1430 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | Install Production Fiber (Includes MOR rack set & Fiber runner) | 2020-12-09 07:00 | 2021-01-06 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 63 | 63 |  |  |  |  | MDC1.C1.C1390: SS 6, MDC1.C1.C1330: SS 6 | MDC1.C1.Cx4000: FS, MDC1.C1.C3460: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C4360 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Pull / Term / Test Conductors | 2020-12-07 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 30 | 30 |  |  |  |  | MDC1.C1.C4220: FS | MDC1.C1.C4390: FS, MDC1.C1.Cx2050: FS | VECA Electricians | 1680 | 0
MDC1.C3.C1190 | Not Started | MDC1-BL.5.3.8.4.5.4 | Task Dependent | Controls Installation | 2020-12-10 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 81 | 81 |  |  |  |  | MDC1.C3.C1130: FS, MDC1.C3.C1150: FS | MDC1.C3.Cx2000: FS, MDC1-C3.P1800: FS | VECA Electricians | 720 | 0
MDC1.C3.C2200 | Not Started | MDC1-BL.5.3.8.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-10 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 156 | 156 |  |  |  |  | MDC1.C3.C2120: FS, MDC1.C3.C2030: FS | MDC1.C3.C2410: FS, MDC1.C3.C2230: FS, MDC1-C3.P1900: FS, MDC1.C3.C2220: FS | PCI | 180 | 0
MDC1.C3.C2210 | Not Started | MDC1-BL.5.3.8.4.7.4 | Task Dependent | Controls Installation | 2020-12-10 07:00 | 2021-01-05 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 81 | 81 |  |  |  |  | MDC1.C3.C2130: FS, MDC1.C3.C2150: FS | MDC1.C3.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C1.C3370 | Not Started | MDC1-BL.5.3.1.3.6.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 70 | 70 |  |  |  |  | MDC1.C1.C3270: FS, MDC1.C1.C3110: SS | MDC1.C1.C3420: FS, MDC1.C1.C3440: FS, MDC1.C1.C3430: FS | PCI | 180 | 0
MDC1.C1.C4350 | Not Started | MDC1-BL.5.3.1.3.8.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 77 | 77 |  |  |  |  | MDC1.C1.C4230: FS, MDC1.C1.C4110: SS | MDC1.C1.C4480: FS, MDC1.C1.C4430: FS, MDC1.C1.C4420: FS | PCI | 180 | 0
MDC1.C2.C1310 | Not Started | MDC1-BL.5.3.9.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 38 | 38 |  |  |  |  | MDC1.C2.C1200: FS, MDC1.C2.C1100: FS | MDC1.C2.C1350: FS, MDC1.C2.C1370: FS, MDC1.C2.C1360: FS | PCI | 180 | 0
MDC1.C2.C1320 | Not Started | MDC1-BL.5.3.9.4.5.4 | Task Dependent | Controls Installation | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1.C2.C1150: FS, MDC1.C2.C1220: FS | MDC1.C2.Cx2010: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C2.C2300 | Not Started | MDC1-BL.5.3.9.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 38 | 38 |  |  |  |  | MDC1.C2.C2190: FS, MDC1.C2.C2080: FS | MDC1.C2.C2440: SS 6, MDC1.C2.C2310: SS 6, MDC1.C2.C2360: FS | PCI | 180 | 0
MDC1.C2.C2310 | Not Started | MDC1-BL.5.3.9.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C2300: SS 6 | MDC1-C2.P1800: FS | TCM | 480 | 0
MDC1.C2.C2320 | Not Started | MDC1-BL.5.3.9.4.7.4 | Task Dependent | Controls Installation | 2020-12-09 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1.C2.C2130: FS, MDC1.C2.C2210: FS | MDC1.C2.Cx2000: FS, MDC1-C2.P1900: FS | VECA Electricians | 720 | 0
MDC1.C3.C3110 | Not Started | MDC1-BL.5.3.8.4.2.4 | Task Dependent | Fire Alarm Installation | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 80 | 80 |  |  |  |  | MDC1.C3.C3080: FS, MDC1.C3.C3050: SS, MDC1.C3.C3000: FS, MDC1-2527: FS | MDC1.C3.C3370: FS | VECA Electricians | 240 | 0
MDC1.C4.C1100 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C4.C1060: FS, MDC1.C4.E1060: FS, MDC1.C4.E1070: FS | MDC1.C4.C1380: FS, MDC1.C4.C1340: FS, MDC1.C4.C1390: FS, MDC1.C4.C1410: FS, MDC1.C4.C1440: FS | VECA Electricians | 480 | 0
MDC1.C4.C3060 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C3020: FS | MDC1.C4.C3070: SS 6, MDC1.C4.C3260: FS, MDC1.C4.C3100: FS, MDC1.C4.E1220: FS 4, MDC1.C4.C3210: FS, MDC1.C4.E1180: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C4.C2100 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C4.C2060: FS, MDC1.C4.E1040: FS, MDC1.C4.E1050: FS | MDC1.C4.C2380: FS, MDC1.C4.C2360: FS, MDC1.C4.C2440: FS, MDC1.C4.C2400: FS, MDC1.C4.C2430: FS | VECA Electricians | 480 | 0
MDC1.C4.C4060 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-16 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C4.C4020: FS | MDC1.C4.C4070: SS 6, MDC1.C4.C4260: FS, MDC1.C4.C4100: FS, MDC1.C4.E1230: FS 5, MDC1.C4.C4250: FS, MDC1.C4.E1200: FS | CSI, VECA Electricians | 1440 | 0
MDC1.S.1750 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-4 Cell 2- Cell - 4 | 2021-01-02 07:00 | 2021-01-04 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.S.1350: FS, MDC1.S.1560: FF, MDC1.S.1560: FS, MDC1.C4.C2040: FS, MDC1.C4.C4040: FS, MDC1.S.1710: FS, MDC1-1996: FS | MDC1.S.1810: FS, MDC1.S.1770: FS | VECA Electricians | 120 | 0
MDC1.C1.C3360 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Pull / Term / Test Conductors | 2020-12-03 07:00 | 2021-01-02 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 28 | 28 |  |  |  |  | MDC1.C1.C3240: FS, MDC1.C1.C3190: FS | MDC1.C1.C3400: FS, MDC1.C1.Cx2030: FS | VECA Electricians | 1680 | 0
MDC1-1967 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-15 07:00 | 2021-01-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1AD-1019: FS, MDC1-1961: FS, MDC1-2012: FS, MDC1-1963: FS | MDC1.AD.Cx2000: FS | VECA Electricians | 960 | 0
MDC1.C1.C2420 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-12-07 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 7 | 7 |  |  |  |  | MDC1.C1.C2120: FS, MDC1.C1.C2090: FS, MDC1.C1.C2280: FS, MDC1.C1.C2340: FS | MDC1.C1.C2410: SS 5, MDC1.C1.C2450: FS | VECA Electricians | 1080 | 0
MDC1.C2.C1300 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | PDU's Installation | 2020-12-28 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 31 | 31 |  |  |  |  | MDC1.C2.C1270: FS, MDC1.C2.C1230: FS, MDC1.C2.C1140: FS, MDC1.C2.E1370: FS, MDC1.C2.E1380: FS | MDC1.C2.C1390: FS, MDC1.C2.C1420: FS | VECA Electricians | 180 | 0
MDC1.C2.C2280 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | PDU's Installation | 2020-12-28 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 25 | 25 |  |  |  |  | MDC1.C2.C2260: FS, MDC1.C2.E1390: FS, MDC1.C2.E1400: FS, MDC1.C2.C2120: FS | MDC1.C2.C2380: FS, MDC1.C2.C2400: FS | VECA Electricians | 180 | 0
MDC1.C3.C2190 | Not Started | MDC1-BL.5.3.8.4.3.4 | Task Dependent | Fire Alarm Installation | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C3.C2160: FS, MDC1.C3.C2110: FS | MDC1.C3.C2390: FS | VECA Electricians | 240 | 0
MDC1.C3.C4130 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C3.C4090: FS, MDC1.C3.E1280: FS, MDC1.C3.E1290: FS | MDC1.C3.C4380: FS, MDC1.C3.C4140: SS 5, MDC1.C3.C4180: FS, MDC1.C3.C4410: FS | TCM | 720 | 0
MDC1.C4.C1080 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-12-23 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 62 | 62 |  |  |  |  | MDC1.C4.C1070: FS | MDC1.C4.C1110: FS, MDC1.C4.E1140: FS | SURE STEEL | 160 | 0
MDC1.C4.C1090 | Not Started | MDC1-BL.5.3.6.4.5.4 | Task Dependent | Fire Alarm System | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C1050: FS | MDC1.C4.C1210: FS, MDC1-C4.P1800: FS | VECA Electricians | 240 | 0
MDC1.C4.C3050 | Not Started | MDC1-BL.5.3.6.4.6.4 | Task Dependent | Fire Riser Installation | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C3010: FS | MDC1.C4.C3090: FS |  | 0 | 0
MDC1.C4.C2080 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-12-23 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 62 | 62 |  |  |  |  | MDC1.C4.C2070: FS | MDC1.C4.C2110: FS, MDC1.C4.E1160: FS | SURE STEEL | 160 | 0
MDC1.C4.C2090 | Not Started | MDC1-BL.5.3.6.4.7.4 | Task Dependent | Fire Alarm System | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C2050: FS | MDC1.C4.C2210: FS | VECA Electricians | 240 | 0
MDC1.C4.C4050 | Not Started | MDC1-BL.5.3.6.4.8.4 | Task Dependent | Fire Riser Installation | 2020-12-14 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.C4010: FS | MDC1.C4.C4090: FS |  | 0 | 0
MDC1.C2.C2290 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Lift & Set MER in Place | 2020-12-22 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.E1130: FS, MDC1.C2.C2030: FS, MDC1.C2.E1310: FS, MDC1.C2.C1250: FS | MDC1.C2.C2340: FS, MDC1.C2.C2330: FS, MDC1.C2.C3230: FS | VECA Electricians | 120 | 0
MDC1.S.1710 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | 2020-12-29 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.S.1350: FS, MDC1.S.1520: FS, MDC1.C4.C3040: FS, MDC1.C4.C4040: FS, MDC1.C4.C2040: FS, MDC1.S.1720: SS, MDC1-1996: FS | MDC1.S.1810: FS, MDC1.S.1780: FS, MDC1.S.1750: FS | VECA Electricians | 120 | 0
MDC1.S.1720 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-4 - CELL-1 to Cell-3 | 2020-12-29 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.C4.C3040: FS, MDC1.C4.C1040: FS, MDC1.S.1680: FS, MDC1-1996: FS | MDC1.S.1780: FS, MDC1.S.1710: SS | VECA Electricians | 120 | 0
MDC1.S.1730 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-1 | 2020-12-03 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 20 | 20 | 0 | 0 |  |  |  |  | MDC1.S.1550: FS, MDC1.C1.C1040: FS, MDC1.C1.C3040: FS, MDC1.C1.C2040: FS, MDC1.C1.C4040: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 1200 | 0
MDC1.S.1740 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-4 | 2020-12-29 07:00 | 2020-12-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 0 | 0 |  |  |  |  | MDC1.C4.C3040: FS, MDC1.C4.C1040: FS, MDC1.S.1590: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 120 | 0
MDC1.C2.C1290 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-12-21 08:00 | 2020-12-30 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 5 | 5 |  |  |  |  | MDC1.C2.C1040: FS, MDC1.C2.C1250: FS | MDC1.C2.C1380: FS, MDC1.C2.C1410: FS, MDC1.C2.C1430: FS, MDC1.C2.C3270: FS | SURE STEEL | 160 | 0
MDC1.C1.C2410 | Not Started | MDC1-BL.5.3.1.4.3.4 | Task Dependent | Fire Alarm Installation | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C1.C2120: FS, MDC1.C1.C2090: FS, MDC1.C1.C2420: SS 5 | MDC1.C1.C2450: FS | VECA Electricians | 240 | 0
MDC1.C2.C1280 | Not Started | MDC1-BL.5.3.9.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C1230: FS | MDC1.C2.C1340: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C3210 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | Cable Tray Installation | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C1230: FS, MDC1.C2.C3170: FS | MDC1.C3.C1310: FS, MDC1.C2.C3260: FS, MDC1.C2.C3290: FS, MDC1.C2.C3370: FS, MDC1.C2.C3220: FF 6, MDC1.C2.C3280: FS | VECA Electricians | 1440 | 0
MDC1.C2.C2270 | Not Started | MDC1-BL.5.3.9.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C2.C2220: FS | MDC1.C2.C2350: FS | LINX- TELECOM | 1440 | 0
MDC1.C2.C4170 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | Cable Tray Installation | 2020-12-12 07:00 | 2020-12-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C2220: FS, MDC1.C2.C4140: FS | MDC1.C3.C2310: FS, MDC1.C2.C4210: FS, MDC1.C2.C4330: FS, MDC1.C2.C4200: FS, MDC1.C2.C4230: FS | VECA Electricians | 1440 | 0
MDC1.C1.C1420 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Generator & Utility Power Pull-Test-Term | 2020-12-11 08:00 | 2020-12-29 08:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C1360: FS, MDC1.C1.C1090: FS, MDC1.C1.C1280: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1.C1.C1460: FS | VECA Electricians | 960 | 0
MDC1.C4.C3040 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-21 07:00 | 2020-12-28 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C3030: FS, MDC1.C4.E1080: FS, MDC1.C4.E1090: FS | MDC1.S.1770: FS, MDC1.S.1740: FS, MDC1.S.1720: FS, MDC1.S.1710: FS | VECA Electricians | 80 | 0
MDC1.C4.C4040 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-21 07:00 | 2020-12-28 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C4030: FS, MDC1.C4.E1100: FS, MDC1.C4.E1110: FS | MDC1.S.1770: FS, MDC1.S.1710: FS, MDC1.S.1750: FS | VECA Electricians | 80 | 0
MDC1.C1.C2400 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Light Fixtures Installation | 2020-12-17 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 94 | 94 |  |  |  |  | MDC1.C1.C2380: FS, MDC1.C1.C2320: FS, MDC1.C1.C2250: FS | MDC1.C1.C4400: FS, MDC1-C1.P1900: FS | VECA Electricians | 480 | 0
MDC1.C3.C1180 | Not Started | MDC1-BL.5.3.8.4.5.2 | Task Dependent | Hydronic Piping Installation | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C1140: FS | MDC1.C3.Cx2000: FF | TCM | 480 | 0
MDC1.C3.C3090 | Not Started | MDC1-BL.5.3.8.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C1120: FS, MDC1.C3.C1070: FS | MDC1.C3.C3140: FS, MDC1.C3.C3130: FS, MDC1.C3.C3120: FF, MDC1.C3.C3120: FS, MDC1.C3.E1300: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C3.C3100 | Not Started | MDC1-BL.5.3.8.4.6.4 | Task Dependent | Fire Alarm System | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C3070: FS | MDC1.C3.C3170: FS | VECA Electricians | 240 | 0
MDC1.C3.C2180 | Not Started | MDC1-BL.5.3.8.4.7.2 | Task Dependent | Hydronic Piping Installation | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C2140: FS | MDC1.C3.Cx2010: FF | TCM | 480 | 0
MDC1.C3.C4110 | Not Started | MDC1-BL.5.3.8.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C2120: FS, MDC1.C3.C2070: FS | MDC1.C3.C4170: FS, MDC1.C3.C4160: FS, MDC1.C3.C4150: FS, MDC1.C3.E1310: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C3.C4120 | Not Started | MDC1-BL.5.3.8.4.8.4 | Task Dependent | Fire Alarm System | 2020-12-10 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C4080: FS | MDC1.C3.C4210: FS | VECA Electricians | 240 | 0
MDC1.C1.C3350 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-12-12 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3250: FS, MDC1.C1.C3300: FS | MDC1.C1.C3410: FS | VECA Electricians | 560 | 0
MDC1.C2.C1270 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Power Bus Installation | 2020-12-12 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 31 | 31 |  |  |  |  | MDC1.C2.C1230: FS, MDC1.C2.C1180: FS | MDC1.C2.C1300: FS, MDC1.C2.E1370: FS | VECA Electricians | 1200 | 0
MDC1.C2.C2260 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Power Bus Installation | 2020-12-12 07:00 | 2020-12-23 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 25 | 25 |  |  |  |  | MDC1.C2.C2220: FS | MDC1.C2.C2280: FS, MDC1.C2.E1390: FS | VECA Electricians | 1200 | 0
MDC1.C1.C1410 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 2020-11-25 08:00 | 2020-12-23 08:00 |  |  |  |  | 0 | 0 | 20 | 20 | 6 | 6 |  |  |  |  | MDC1.C1.C1090: FS, MDC1.C1.C1110: FS, MDC1.C1.C1280: FS, MDC1.C1.C1300: FS | MDC1.C1.Cx2000: FS, MDC1.C1.C1440: FS | VECA Electricians | 1080 | 0
MDC1.C1.C3340 | Not Started | MDC1-BL.5.3.1.4.6.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C3290: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0
MDC1.C1.C4320 | Not Started | MDC1-BL.5.3.1.4.8.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C4250: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0
MDC1.C1.C4330 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 25 | 25 |  |  |  |  | MDC1.C1.C4260: FS, MDC1.C1.C4180: FS | MDC1.C1.C4380: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C4340 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-12-11 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C4270: FS, MDC1.C1.C2340: FS | MDC1.C1.C4370: FS, MDC1.C1.C4410: FS |  | 0 | 0
MDC1.C2.C1260 | Not Started | MDC1-BL.5.3.9.4.5.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C1210: FS | MDC1.C2.Cx2010: FF | TCM | 480 | 0
MDC1.C2.C3190 | Not Started | MDC1-BL.5.3.9.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1200: FS, MDC1.C2.C1160: FS | MDC1.C2.C3240: FS, MDC1.C2.C3240: SS 5, MDC1.C2.E1340: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C2.C3200 | Not Started | MDC1-BL.5.3.9.4.6.4 | Task Dependent | Fire Alarm System | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C2.C3160: FS | MDC1.C2.C3300: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0
MDC1.C2.C2250 | Not Started | MDC1-BL.5.3.9.4.7.2 | Task Dependent | Hydronic Piping Installation | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C2200: FS | MDC1.C2.Cx2000: FF | TCM | 480 | 0
MDC1.C2.C4150 | Not Started | MDC1-BL.5.3.9.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2190: FS, MDC1.C2.C2140: FS | MDC1.C2.C4180: FS, MDC1.C2.C4180: SS 5, MDC1.C2.E1330: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C2.C4160 | Not Started | MDC1-BL.5.3.9.4.8.4 | Task Dependent | Fire Alarm System | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C2.C4130: FS | MDC1.C2.C4260: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0
MDC1.C4.C1070 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C1060: SS 6, MDC1.C4.C1000: FS, MDC1.C3.C1060: FS, MDC1.C3.C1060: FF | MDC1.C4.C1080: FS, MDC1-C4.P1700: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C4.C2070 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-12-09 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C2060: SS 6, MDC1.C4.C2000: FS | MDC1.C4.C2080: FS | CSI, VECA Electricians | 1440 | 0
MDC1.S.1700 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term URS- Line Side | 2020-12-16 07:00 | 2020-12-22 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 1 | 1 |  |  |  |  | MDC1.S.1600: FS, MDC1.S.1660: FS | MDC1.S.1800: FS, MDC1.S.1760: FS | VECA Electricians | 360 | 0
MDC1AD-1027 | Not Started | MDC1-BL.5.3.2.4.1 | Task Dependent | Electrical Devices & Trim | 2020-11-30 07:00 | 2020-12-21 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 44 | 44 |  |  |  |  | MDC1AD-1018: FS | MDC1.AD.Cx2000: FS, MDC1.AD.Cx2010: FS | VECA Electricians | 1800 | 0
MDC1AD-1026 | Not Started | MDC1-BL.5.3.2.4.3 | Task Dependent | Security Devices & Trim | 2020-11-30 07:00 | 2020-12-21 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 96 | 96 |  |  |  |  | MDC1AD-1018: FS | MDC1-C1.P1900: FS |  | 0 | 0
MDC1.C4.E1120 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-1 |  | 2020-12-21 17:00 |  |  | 2020-12-21 17:00 |  | 0 | 0 | 0 | 0 | 62 | 62 |  |  |  |  | MDC1.C4.C1060: FS 5 | MDC1.C4.C1230: FS |  | 0 | 0
MDC1.C4.E1130 | Not Started | MDC1-BL.4.10.2.1.4 | Finish Milestone | Pad Ready for MER COLO-4 Cell-2 |  | 2020-12-21 17:00 |  |  | 2020-12-21 17:00 |  | 0 | 0 | 0 | 0 | 67 | 67 |  |  |  |  | MDC1.C4.C2060: FS 5 | MDC1.C4.C2270: FS |  | 0 | 0
MDC1.S.1690 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term- UMS- Line Side | 2020-12-15 07:00 | 2020-12-21 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 2 | 2 |  |  |  |  | MDC1.S.1680: SS | MDC1.S.1800: FS | VECA Electricians | 360 | 0
MDC1.C2.C1250 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Lift & Set MER in Place | 2020-12-15 08:00 | 2020-12-21 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C2.E1120: FS, MDC1.C2.C1040: FS, MDC1.C2.E1300: FS, MDC1-C2.P1600: FS, MDC1.C1.C4270: FS | MDC1.C2.C1330: FS, MDC1.C2.C1290: FS, MDC1.C2.C2290: FS | VECA Electricians | 120 | 0
MDC1.C1.C3330 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-12-07 07:00 | 2020-12-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3260: FS, MDC1.C1.C3190: FS | MDC1.C1.Cx2030: FS, MDC1.C1.C3380: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.C3030 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-16 07:00 | 2020-12-19 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C3020: FS | MDC1.C4.C3040: FS, MDC1.C4.E1080: FS | CSI, VECA Electricians | 480 | 0
MDC1.C4.C4030 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-16 07:00 | 2020-12-19 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C4.C4020: FS | MDC1.C4.C4040: FS, MDC1.C4.E1100: FS | CSI, VECA Electricians | 480 | 0
MDC1.C2.C1240 | Not Started | MDC1-BL.5.3.9.4.9.3 | Task Dependent | Fire Alarm System | 2020-12-08 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C1230: FF 6 | MDC1.C2.C1400: FS, MDC1-C2.P1900: FS | VECA Electricians | 600 | 0
MDC1.C2.C2240 | Not Started | MDC1-BL.5.3.9.4.11.3 | Task Dependent | Fire Alarm System | 2020-12-08 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C2220: FF 6 | MDC1.C2.C2390: FS, MDC1-C2.P1900: FS | VECA Electricians | 600 | 0
MDC1.C3.C1170 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-12-04 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 67 | 67 |  |  |  |  | MDC1.C3.C1160: SS 5 | MDC1.C3.C1200: FS, MDC1.C3.Cx2000: FS | TCM | 720 | 0
MDC1.C3.C2170 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-12-04 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 91 | 91 |  |  |  |  | MDC1.C3.C2160: SS 5 | MDC1.C3.Cx2010: FS | TCM | 720 | 0
MDC1.S.1680 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull - JAZ to UMS | 2020-12-15 07:00 | 2020-12-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 2 | 2 |  |  |  |  | MDC1.S.1470: FS, MDC1.S.1210: FS, MDC1-2133: FS, MDC1.S.1170: FS, MDC1.S.1370: FS, MDC1-2189: FS, MDC1.S.1640: FS, MDC1-1996: FS | MDC1.S.1690: SS, MDC1.S.1720: FS | VECA Electricians | 240 | 0
MDC1.C1.C4310 | Not Started | MDC1-BL.5.3.1.4.13.3 | Task Dependent | Fire Alarm System | 2020-12-07 07:00 | 2020-12-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 116 | 116 |  |  |  |  | MDC1.C1.C4220: FS | MDC1.M1010: FS | VECA Electricians | 600 | 0
MDC1.C1.C2390 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-12-07 07:00 | 2020-12-17 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2280: FS, MDC1.C1.C2340: FS | MDC1.C1.C2430: FS, MDC1.C1.C4370: FS | VECA Electricians | 560 | 0
MDC1.C1.C1400 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Pull / Term / Test Conductors | 2020-11-18 07:00 | 2020-12-16 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 27 | 27 |  |  |  |  | MDC1.C1.C1270: FS | MDC1.C1.C1450: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 1680 | 0
MDC1.C1.C2380 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Pull / Term / Test Conductors | 2020-11-18 07:00 | 2020-12-16 17:00 |  |  |  |  | 0 | 0 | 21 | 21 | 32 | 32 |  |  |  |  | MDC1.C1.C2250: FS, MDC1.C1.C2180: FS | MDC1.C1.C2400: FS, MDC1.C1.Cx2010: FS | VECA Electricians | 1680 | 0
MDC1.S.1670 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Vault to COLO-4 UPM | 2020-12-10 07:00 | 2020-12-16 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 11 | 11 |  |  |  |  | MDC1.S.1620: FS, MDC1.C4.C2020: FS | MDC1.S.1770: FS |  | 0 | 0
MDC1.C1.C1370 | Not Started | MDC1-BL.5.3.1.4.5.3 | Task Dependent | Floor Drain System Installation | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C1120: FS, MDC1.C1.C1310: FS | MDC1.C1.C4490: FS |  | 0 | 0
MDC1.C1.C1380 | Not Started | MDC1-BL.5.3.1.4.5.3 | Task Dependent | Toilet Piping Installation / DW | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C1310: FS | MDC1.C1.C4490: FS | TCM | 480 | 0
MDC1.C1.C1390 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 28 | 28 |  |  |  |  | MDC1.C1.C1330: FS | MDC1.C1.C1430: SS 6, MDC1.C1.Cx2000: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C3320 | Not Started | MDC1-BL.5.3.1.4.10.3 | Task Dependent | Fire Alarm System | 2020-12-03 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 118 | 118 |  |  |  |  | MDC1.C1.C3240: FS | MDC1.M1010: FS | VECA Electricians | 600 | 0
MDC1.C1.C2350 | Not Started | MDC1-BL.5.3.1.4.7.3 | Task Dependent | Floor Drain System Installation | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C2110: FS, MDC1.C1.C2290: FS | MDC1.C1.C4490: FS |  | 0 | 0
MDC1.C1.C2360 | Not Started | MDC1-BL.5.3.1.4.7.3 | Task Dependent | Toilet Piping Installation / DW | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 118 | 118 |  |  |  |  | MDC1.C1.C2290: FS | MDC1.C1.C4490: FS | TCM | 480 | 0
MDC1.C1.C2370 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | BMS Pull Wire / Term / Test | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2310: FS | MDC1.C1.C2440: FS, MDC1.C1.Cx2040: FS, MDC1.C1.Cx2010: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C4280 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-12-11 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C1.C4050: FS, MDC1.C1.C4270: FS, MDC1.C1.C2280: FS | MDC1.C1.C4370: FS, MDC1.C1.C4440: FS, MDC1.C1.C4410: FS, MDC1.S.1900: FS | SURE STEEL | 160 | 0
MDC1.C1.C4290 | Not Started | MDC1-BL.5.3.1.4.8.4 | Task Dependent | Controls Installation | 2020-11-20 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 43 | 43 |  |  |  |  | MDC1.C1.C4200: FS | MDC1.C1.Cx2050: FS, MDC1.C1.C4490: FS | VECA Electricians | 720 | 0
MDC1.C1.C4300 | Not Started | MDC1-BL.5.3.1.4.13.3 | Task Dependent | Controls Installation | 2020-12-07 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 43 | 43 |  |  |  |  | MDC1.C1.C4220: FS | MDC1.C1.C4390: FS, MDC1.C1.Cx2050: FS | VECA Electricians | 720 | 0
MDC1.C3.C3080 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C3.C3050: FS, MDC1.C3.E1220: FS, MDC1.C3.E1230: FS | MDC1.C3.C3330: FS, MDC1.C3.C3350: FS, MDC1.C3.C3380: FS, MDC1.C3.C3110: FS, MDC1.C3.C3370: FS | VECA Electricians | 480 | 0
MDC1.C3.C4100 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C3.C4050: FS, MDC1.C3.E1240: FS, MDC1.C3.E1250: FS | MDC1.C3.C4370: FS, MDC1.C3.C4380: FS, MDC1.C3.C4430: FS, MDC1.C3.C4180: FS, MDC1.C3.C4410: FS | VECA Electricians | 480 | 0
MDC1.C4.C1060 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C1020: FS | MDC1.C4.C1070: SS 6, MDC1.C4.C1280: FS, MDC1.C4.C1100: FS, MDC1-C4.P1600: FS, MDC1.C4.E1120: FS 5, MDC1.C4.C1230: FS, MDC1.C4.E1060: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C4.C3020 | Not Started | MDC1-BL.5.3.6.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C1020: FS | MDC1.C4.C3060: FS, MDC1.C4.C3030: FS | VECA Electricians | 960 | 0
MDC1.C4.C2060 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C4.C2020: FS | MDC1.C4.C2070: SS 6, MDC1.C4.C2280: FS, MDC1.C4.C2100: FS, MDC1.C4.E1130: FS 5, MDC1.C4.C2270: FS, MDC1.C4.E1040: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C4.C4020 | Not Started | MDC1-BL.5.3.6.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-12-01 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C4.C2020: FS | MDC1.C4.C4060: FS, MDC1.C4.C4030: FS | VECA Electricians | 960 | 0
MDC1.S.1650 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-2 | 2020-12-03 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 10 | 10 |  |  |  |  | MDC1.S.1550: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 600 | 0
MDC1.S.1660 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -3 WEST UPMS | 2020-12-09 07:00 | 2020-12-15 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 1 | 1 |  |  |  |  | MDC1.S.1560: FS, MDC1.S.1520: FS, MDC1.S.1610: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1700: FS, MDC1.S.1780: FS | VECA Electricians | 360 | 0
MDC1AD-1019 | Not Started | MDC1-BL.5.3.2.4.1 | Task Dependent | Set Electrical Equipment | 2020-10-28 07:00 | 2020-12-14 17:00 |  |  |  |  | 0 | 0 | 36 | 36 | 8 | 8 |  |  |  |  | MDC1AD-1016: FS, MDC1-2505: FS, MDC1-2506: FS, MDC1-2507: FS, MDC1-2508: FS, MDC1-2511: FS, MDC1-2512: FS, MDC1-2514: FS, MDC1-2513: FS | MDC1-1969: FS, MDC1-1968: FS, MDC1-1967: FS, MDC1AD-1023: FS, MDC1.AD.Cx2000: FS | VECA Electricians | 2880 | 0
MDC1AD-1022 | Not Started | MDC1-BL.5.3.2.4.2 | Task Dependent | Plumbing Devices & Trim | 2020-11-19 07:00 | 2020-12-14 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1AD-1020: FS | MDC1.AD.Cx2000: FS | TCM | 360 | 0
MDC1.S.1640 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-3 | 2020-12-10 07:00 | 2020-12-14 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 2 | 2 |  |  |  |  | MDC1.C3.C4040: FS, MDC1.C3.C2040: FS, MDC1.C3.C3040: FS, MDC1.C3.C1040: FS, MDC1.S.1200: FS, MDC1.S.1620: FS, MDC1.S.1460: FS, MDC1.S.1500: FS, MDC1.S.1600: FS, MDC1-1996: FS | MDC1.S.1790: FS, MDC1.S.1770: FS, MDC1.S.1680: FS | VECA Electricians | 240 | 0
MDC1.C1.C3310 | Not Started | MDC1-BL.5.3.1.4.10.3 | Task Dependent | Controls Installation | 2020-12-03 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 41 | 41 |  |  |  |  | MDC1.C1.C3240: FS | MDC1.C1.C3400: FS, MDC1.C1.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C2.C3180 | Not Started | MDC1-BL.5.3.9.4.2.4 | Task Dependent | Fire Alarm Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C2.C3120: FS, MDC1.C2.C3080: FS | MDC1.C2.C3440: FS | VECA Electricians | 240 | 0
MDC1.C2.C2230 | Not Started | MDC1-BL.5.3.9.4.3.4 | Task Dependent | Fire Alarm Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C2.C2170: FS, MDC1.C2.C2060: FS | MDC1.C2.C2430: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0
MDC1.C3.C1160 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C1100: FS, MDC1.C3.E1180: FS, MDC1.C3.E1190: FS, MDC1-C3.P1700: FS | MDC1.C3.C1360: FS, MDC1.C3.C1170: SS 5, MDC1.C3.C1200: FS, MDC1.C3.C1400: FS | TCM | 720 | 0
MDC1.C3.C2160 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C2100: FS, MDC1.C3.E1200: FS, MDC1.C3.E1210: FS | MDC1.C3.C2350: FS, MDC1.C3.C2170: SS 5, MDC1.C3.C2190: FS, MDC1.C3.C2390: FS | TCM | 720 | 0
MDC1.C3.C4090 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-12-09 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 62 | 62 |  |  |  |  | MDC1.C3.C4070: FS | MDC1.C3.C4130: FS, MDC1.C3.E1290: FS | SURE STEEL | 160 | 0
MDC1.C4.C1050 | Not Started | MDC1-BL.5.3.6.4.5.4 | Task Dependent | Fire Riser Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C1010: FS | MDC1.C4.C1090: FS |  | 0 | 0
MDC1.C4.C3010 | Not Started | MDC1-BL.5.3.6.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C1010: FS | MDC1.C4.C3240: FS, MDC1.C4.C3290: FS, MDC1.C4.C3050: FS | PCI | 480 | 0
MDC1.C4.C2050 | Not Started | MDC1-BL.5.3.6.4.7.4 | Task Dependent | Fire Riser Installation | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 100 | 100 |  |  |  |  | MDC1.C4.C2010: FS | MDC1.C4.C2090: FS |  | 0 | 0
MDC1.C4.C4010 | Not Started | MDC1-BL.5.3.6.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-25 07:00 | 2020-12-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 98 | 98 |  |  |  |  | MDC1.C4.CS1090: FS, MDC1.C4.C2010: FS | MDC1.C4.C4230: FS, MDC1.C4.C4270: FS, MDC1.C4.C4050: FS | PCI | 480 | 0
MDC1.C1.C3300 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-11-30 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C3210: FS | MDC1.C1.C3350: FS, MDC1.C1.C3390: FS |  | 0 | 0
MDC1.C2.C1230 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | Cable Tray Installation | 2020-11-24 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C1180: FS | MDC1.C2.C1280: FS, MDC1.C2.C3210: FS, MDC1.C2.C1270: FS, MDC1.C2.C1300: FS, MDC1.C2.C1400: FS, MDC1.C2.C1240: FF 6 | VECA Electricians | 1440 | 0
MDC1.C2.C2220 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | Cable Tray Installation | 2020-11-24 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C1.C4180: FS, MDC1.C2.C2160: FS | MDC1.C2.C4170: FS, MDC1.C2.C2260: FS, MDC1.C2.C2390: FS, MDC1.C2.C2240: FF 6, MDC1.C2.C2270: FS | VECA Electricians | 1440 | 0
MDC1.S.1630 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull- UMS to COLO-3 | 2020-12-03 07:00 | 2020-12-11 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 13 | 13 |  |  |  |  | MDC1.C3.C3040: FS, MDC1.C3.C1040: FS, MDC1.S.1550: FS, MDC1.S.1270: FS, MDC1-1996: FS | MDC1.S.1820: FS | VECA Electricians | 420 | 0
MDC1.C1.C1360 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | GEN & UPM to MER Cable Bus Instal | 2020-11-25 08:00 | 2020-12-11 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C1280: FS, MDC1.C1.C1300: FS | MDC1.C1.C1420: FS | VECA Electricians | 560 | 0
MDC1AD-1021 | Not Started | MDC1-BL.5.3.2.4.4 | Task Dependent | Mechanical Ductwork Installation | 2020-11-16 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 35 | 35 |  |  |  |  | MDC1AD-1016: FS, MDC1AD-1021.1: FS | MDC1AD-1023: FS, MDC1AD-1025: FS | TCM | 360 | 0
MDC1.C4.C1040 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-07 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C1030: FS, MDC1.C4.E1010: FS, MDC1.C4.E1000: FS | MDC1.S.1770: FS, MDC1.S.1740: FS, MDC1.S.1720: FS | VECA Electricians | 80 | 0
MDC1.C4.C2040 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-12-07 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C2030: FS, MDC1.C4.E1020: FS, MDC1.C4.E1030: FS | MDC1.S.1770: FS, MDC1.S.1710: FS, MDC1.S.1750: FS | VECA Electricians | 80 | 0
MDC1.C1.C4270 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Lift & Set MER in Place | 2020-12-04 07:00 | 2020-12-10 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.E1470: FS, MDC1.C1.E1230: FS, MDC1.C1.C4050: FS, MDC1.C1.C3210: FS | MDC1.C1.C4280: FS, MDC1.C1.C4340: FS, MDC1.C2.C1250: FS | VECA Electricians | 120 | 0
MDC1.C3.C1120 | Not Started | MDC1-BL.5.3.8.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C1070: FS | MDC1.C3.C1250: FS, MDC1.C3.C3090: FS | VECA Electricians | 960 | 0
MDC1.C3.C1130 | Not Started | MDC1-BL.5.3.8.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C1070: FS | MDC1.C3.C1330: FS, MDC1.C3.C1190: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C3.C1140 | Not Started | MDC1-BL.5.3.8.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C1070: FS, MDC1.C3.E1140: FS, MDC1.C3.E1160: FS | MDC1.C3.C1180: FS | TCM | 480 | 0
MDC1.C3.C1150 | Not Started | MDC1-BL.5.3.8.4.5.4 | Task Dependent | Fire Alarm System | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C1080: FS | MDC1.C3.C1190: FS, MDC1-C3.P1800: FS | VECA Electricians | 240 | 0
MDC1.C3.C3070 | Not Started | MDC1-BL.5.3.8.4.6.4 | Task Dependent | Fire Riser Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C3030: FS | MDC1.C3.C3100: FS |  | 0 | 0
MDC1.C3.C2120 | Not Started | MDC1-BL.5.3.8.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C2070: FS | MDC1.C3.C4110: FS, MDC1.C3.C2200: FS | VECA Electricians | 960 | 0
MDC1.C3.C2130 | Not Started | MDC1-BL.5.3.8.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C2070: FS | MDC1.C3.C2410: FS, MDC1.C3.C2210: FS, MDC1.C3.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C3.C2140 | Not Started | MDC1-BL.5.3.8.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 97 | 97 |  |  |  |  | MDC1.C3.C2070: FS, MDC1.C3.E1150: FS, MDC1.C3.E1170: FS | MDC1.C3.C2180: FS | TCM | 480 | 0
MDC1.C3.C2150 | Not Started | MDC1-BL.5.3.8.4.7.4 | Task Dependent | Fire Alarm System | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C2080: FS | MDC1.C3.C2210: FS | VECA Electricians | 240 | 0
MDC1.C3.C4080 | Not Started | MDC1-BL.5.3.8.4.8.4 | Task Dependent | Fire Riser Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.C4030: FS | MDC1.C3.C4120: FS |  | 0 | 0
MDC1.C2.C3170 | Not Started | MDC1-BL.5.3.9.4.10.1 | Task Dependent | HAC Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 13 | 13 |  |  |  |  | MDC1.C2.C3110: FS | MDC1.C2.C3210: FS, MDC1.C2.C3260: FS | TCM | 480 | 0
MDC1.C2.C4140 | Not Started | MDC1-BL.5.3.9.4.13.1 | Task Dependent | HAC Installation | 2020-11-21 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 13 | 13 |  |  |  |  | MDC1.C2.C4090: FS | MDC1.C2.C4170: FS | TCM | 480 | 0
MDC1.S.1620 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Vault to COLO-3 UPM | 2020-12-04 07:00 | 2020-12-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 2 | 2 |  |  |  |  | MDC1.S.1580: FS, MDC1.S.1460: FS, MDC1.C3.C3010: FS | MDC1.S.1640: FS, MDC1.S.1670: FS |  | 0 | 0
MDC1.C1.C3270 | Not Started | MDC1-BL.5.3.1.3.6.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C1.C3200: FS | MDC1.C1.C3370: FS | VECA Electricians | 960 | 0
MDC1.C1.C3280 | Not Started | MDC1-BL.5.3.1.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 88 | 88 |  |  |  |  | MDC1.C1.C3200: FS | MDC1.C1.C3420: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C1.C3290 | Not Started | MDC1-BL.5.3.1.4.6.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C3200: FS, MDC1.C1.E1390: FS, MDC1.C1.E1410: FS | MDC1.C1.C3340: FS | TCM | 480 | 0
MDC1.C1.C4230 | Not Started | MDC1-BL.5.3.1.3.8.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 77 | 77 |  |  |  |  | MDC1.C1.C4190: FS, MDC1.C1.C4190: SS 5 | MDC1.C1.C4350: FS | VECA Electricians | 960 | 0
MDC1.C1.C4240 | Not Started | MDC1-BL.5.3.1.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 89 | 89 |  |  |  |  | MDC1.C1.C4190: FS | MDC1.C1.C4480: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C1.C4250 | Not Started | MDC1-BL.5.3.1.4.8.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C4190: FS, MDC1.C1.E1400: FS, MDC1.C1.E1420: FS | MDC1.C1.C4320: FS | TCM | 480 | 0
MDC1.C2.C1200 | Not Started | MDC1-BL.5.3.9.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1160: FS, MDC1.C2.C1160: SS 5 | MDC1.C2.C3190: FS, MDC1.C2.C1310: FS | VECA Electricians | 960 | 0
MDC1.C2.C1210 | Not Started | MDC1-BL.5.3.9.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C1090: FS, MDC1.C2.E1260: FS, MDC1.C2.E1280: FS | MDC1.C2.C1260: FS | TCM | 480 | 0
MDC1.C2.C1220 | Not Started | MDC1-BL.5.3.9.4.5.4 | Task Dependent | Fire Alarm System | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1170: FS | MDC1.C2.C1320: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0
MDC1.C2.C3160 | Not Started | MDC1-BL.5.3.9.4.6.4 | Task Dependent | Fire Riser Installation | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C2.C3100: FS | MDC1.C2.C3200: FS |  | 0 | 0
MDC1.C2.C2190 | Not Started | MDC1-BL.5.3.9.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2140: FS, MDC1.C2.C2140: SS 5 | MDC1.C2.C4150: FS, MDC1.C2.C2300: FS | VECA Electricians | 960 | 0
MDC1.C2.C2200 | Not Started | MDC1-BL.5.3.9.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 66 | 66 |  |  |  |  | MDC1.C2.C2070: FS, MDC1.C2.E1270: FS, MDC1.C2.E1290: FS | MDC1.C2.C2250: FS | TCM | 480 | 0
MDC1.C2.C2210 | Not Started | MDC1-BL.5.3.9.4.7.4 | Task Dependent | Fire Alarm System | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C2150: FS | MDC1.C2.C2320: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0
MDC1.C2.C4130 | Not Started | MDC1-BL.5.3.9.4.8.4 | Task Dependent | Fire Riser Installation | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C2.C4080: FS | MDC1.C2.C4160: FS |  | 0 | 0
MDC1.C3.C4070 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C3.C4050: SS 6, MDC1.C3.C4020: FS | MDC1.C3.C4090: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C4.C4000 | Not Started | MDC1-BL.5.3.6.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-11-20 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 87 | 87 |  |  |  |  | MDC1.C4.C2000: FS | MDC1.C4.C4070: FS | TCM | 720 | 0
MDC1.S.1590 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - COLO-4 UPM to UMS | 2020-12-03 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 14 | 14 |  |  |  |  | MDC1.S.1550: FS | MDC1.S.1740: FS | VECA Electricians | 240 | 0
MDC1.S.1600 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull - JAZ to URS | 2020-12-03 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.S.1250: FS, MDC1.S.1410: FS, MDC1-2189: FS, MDC1-2132: FS, MDC1.S.1560: FS, MDC1-1996: FS | MDC1.S.1700: FS, MDC1.S.1760: FS, MDC1.S.1640: FS | VECA Electricians | 240 | 0
MDC1.S.1610 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -3 East UPMS | 2020-12-01 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 1 | 1 |  |  |  |  | MDC1.S.1510: FS, MDC1.S.1520: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1660: FS | VECA Electricians | 360 | 0
MDC1.C1.C4260 | Not Started | MDC1-BL.5.3.1.4.13.2 | Task Dependent | IDF Backbone Install | 2020-11-17 07:00 | 2020-12-08 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 25 | 25 |  |  |  |  | MDC1.C1.C4180: FS, MDC1.C1.C2230: FS | MDC1.C1.C4330: FS | LINX- TELECOM | 1440 | 0
MDC1.C3.E1260 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-3 |  | 2020-12-07 17:00 |  |  | 2020-12-07 17:00 |  | 0 | 0 | 0 | 0 | 51 | 51 |  |  |  |  | MDC1.C3.C3050: FS 5 | MDC1.C3.C3200: FS |  | 0 | 0
MDC1.C3.E1270 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-4 |  | 2020-12-07 17:00 |  |  | 2020-12-07 17:00 |  | 0 | 0 | 0 | 0 | 56 | 56 |  |  |  |  | MDC1.C3.C4050: FS 5 | MDC1.C3.C4270: FS |  | 0 | 0
MDC1-P1050 | Not Started | MDC1-BL.3.1 | Finish Milestone | Grant County Permanent Power Required for CX |  | 2020-12-07 08:00 |  |  | 2020-12-07 08:00 |  | 0 | 0 | 0 | 0 | 30 | 30 | Finish On or After | 2020-12-07 08:00 |  |  | MDC1.C1.C1300: FS | MDC1.AD.Cx2000: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1.S.1840: FS, MDC1.S.1850: FS |  | 0 | 0
MDC1.C1.C2340 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-11-20 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C2270: FS | MDC1.C1.C2390: FS, MDC1.C1.C2420: FS, MDC1.C1.C4340: FS |  | 0 | 0
MDC1.C1.C4220 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | PDU's Installation | 2020-12-02 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 30 | 30 |  |  |  |  | MDC1.C1.C4210: FS, MDC1.C1.C4130: FS, MDC1.C1.E1450: FS, MDC1.C1.E1460: FS | MDC1.C1.C4390: FS, MDC1.C1.C4360: FS, MDC1.C1.C4310: FS, MDC1.C1.C4300: FS | VECA Electricians | 180 | 0
MDC1.C4.C1030 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-01 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C1020: FS | MDC1.C4.C1040: FS, MDC1.C4.E1000: FS | CSI, VECA Electricians | 480 | 0
MDC1.C4.C2030 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-12-01 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 12 | 12 |  |  |  |  | MDC1.C4.C2020: FS | MDC1.C4.C2040: FS, MDC1.C4.E1030: FS | CSI, VECA Electricians | 480 | 0
MDC1.C1.C3260 | Not Started | MDC1-BL.5.3.1.4.10.2 | Task Dependent | IDF Backbone Install | 2020-11-13 07:00 | 2020-12-04 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 23 | 23 |  |  |  |  | MDC1.C1.C3190: FS, MDC1.C1.C1240: FS | MDC1.C1.C3330: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C3250 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-11-30 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C1.C3050: FS, MDC1.C1.C3080: FS, MDC1.C1.C3210: FS, MDC1.C1.C1280: FS | MDC1.C1.C3350: FS, MDC1.C1.C3410: FS, MDC1.C1.C3390: FS | SURE STEEL | 160 | 0
MDC1.C2.C3130 | Not Started | MDC1-BL.5.3.9.3.2.2 | Task Dependent | Datahall Finishes | 2020-11-19 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C3110: SS 6 | MDC1.C2.C3290: FS | PCI | 400 | 0
MDC1.C2.C3140 | Not Started | MDC1-BL.5.3.9.4.6.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 63 | 63 |  |  |  |  | MDC1.C2.C3090: FS | MDC1.C2.C3300: FS, MDC1.C2.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C2.C3150 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C2.C3120: SS 5 | MDC1.C2.Cx3030: FS, MDC1.C2.Cx3040: FS, MDC1.M2010: FS, MDC1.C2.Cx2050: FS | TCM | 720 | 0
MDC1.C2.C2180 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 71 | 71 |  |  |  |  | MDC1.C2.C2170: SS 5 | MDC1.C2.Cx2000: FS | TCM | 720 | 0
MDC1.C2.C4110 | Not Started | MDC1-BL.5.3.9.3.4.2 | Task Dependent | Datahall Finishes | 2020-11-19 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 41 | 41 |  |  |  |  | MDC1.C2.C4090: SS 6 | MDC1.C2.C4240: FS | PCI | 400 | 0
MDC1.C2.C4120 | Not Started | MDC1-BL.5.3.9.4.8.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-17 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C2.C4070: FS | MDC1.C2.C4410: FS, MDC1.C2.Cx3020: FS, MDC1.C2.Cx2030: FS | VECA Electricians | 240 | 0
MDC1.S.1580 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault - Set South Vault along UPM to Vault | 2020-12-01 07:00 | 2020-12-03 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 2 | 2 |  |  |  |  | MDC1.S.1340: FS, MDC1.C3.C4050: FS | MDC1.S.1770: FS, MDC1.S.1620: FS | VECA Electricians | 180 | 0
MDC1.C1.C1350 | Not Started | MDC1-BL.5.3.1.4.9.3 | Task Dependent | Fire Alarm System | 2020-11-18 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 111 | 111 |  |  |  |  | MDC1.C1.C1270: FS | MDC1.M1010: FS, MDC1-C1.P1900: FS | VECA Electricians | 600 | 0
MDC1.C1.C3240 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | PDU's Installation | 2020-11-30 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 28 | 28 |  |  |  |  | MDC1.C1.C3220: FS, MDC1.C1.C3120: FS, MDC1.C1.E1430: FS, MDC1.C1.E1440: FS | MDC1.C1.C3360: FS, MDC1.C1.C3400: FS, MDC1.C1.C3320: FS, MDC1.C1.C3310: FS | VECA Electricians | 180 | 0
MDC1.C1.C2330 | Not Started | MDC1-BL.5.3.1.4.11.3 | Task Dependent | Fire Alarm System | 2020-11-18 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 111 | 111 |  |  |  |  | MDC1.C1.C2250: FS, MDC1.C1.C2250: FF | MDC1.M1010: FS, MDC1-C1.P1900: FS | VECA Electricians | 600 | 0
MDC1.S.1550 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - south vault (along UMS duct run) to UMS | 2020-11-18 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.S.1470: FS | MDC1.S.1730: FS, MDC1.S.1650: FS, MDC1.S.1630: FS, MDC1.S.1590: FS | VECA Electricians | 600 | 0
MDC1.S.1560 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-3 Cell 2- Cell - 4 | 2020-12-01 07:00 | 2020-12-02 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 3 | 3 |  |  |  |  | MDC1.S.1220: FS, MDC1.S.1440: FF, MDC1.S.1440: FS, MDC1.C3.C2040: FS, MDC1.C3.C4040: FS, MDC1.S.1520: FS, MDC1-1996: FS | MDC1.S.1660: FS, MDC1.S.1750: FF, MDC1.S.1750: FS, MDC1.S.1600: FS | VECA Electricians | 120 | 0
MDC1.C3.C3060 | Not Started | MDC1-BL.5.3.8.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-23 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C3.C1090: FS | MDC1.C3.C1210: FS, MDC1.C4.C1140: FS, MDC1.C3.C3180: FS | TCM, VECA Electricians | 800 | 0
MDC1.C3.C4060 | Not Started | MDC1-BL.5.3.8.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-23 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C3.C2090: FF, MDC1.C3.C2090: FS | MDC1.C3.C2240: FS, MDC1.C4.C2140: FS, MDC1.C3.C4220: FS | TCM, VECA Electricians | 800 | 0
MDC1.C1.C4210 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Power Bus Installation | 2020-11-17 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 30 | 30 |  |  |  |  | MDC1.C1.C4180: FS | MDC1.C1.C4220: FS, MDC1.C1.Cx2050: FS, MDC1.C1.E1450: FS | VECA Electricians | 1200 | 0
MDC1.S.1540 | Not Started | MDC1-BL.5.1.9 | Task Dependent | Telecom-RNG Fiber underground installation | 2020-09-28 07:00 | 2020-12-01 17:00 |  |  |  |  | 0 | 0 | 50 | 50 | 79 | 79 |  |  |  |  | MDC1.S.1160: FS | MDC1.S.1830: FS | LINX- TELECOM | 5000 | 0
MDC1.C1.C1310 | Not Started | MDC1-BL.5.3.1.3.5.2 | Task Dependent | Mechanical Corridor Finishes | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 118 | 118 |  |  |  |  | MDC1.C1.C1210: FS, MDC1.C1.C1120: FS | MDC1.C1.C1470: FS, MDC1.C1.C1380: FS, MDC1.C1.C1370: FS | PCI | 180 | 0
MDC1.C1.C1320 | Not Started | MDC1-BL.5.3.1.4.5.4 | Task Dependent | Controls Installation | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 40 | 40 |  |  |  |  | MDC1.C1.C1220: FS, MDC1.C1.C1190: FS | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1-C1.P1800: SS | VECA Electricians | 720 | 0
MDC1.C1.C1330 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 28 | 28 |  |  |  |  | MDC1.C1.C1240: FS, MDC1.C1.C1200: FS | MDC1.C1.C1390: FS, MDC1.C1.C1430: SS 6, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C1340 | Not Started | MDC1-BL.5.3.1.4.9.3 | Task Dependent | Controls Installation | 2020-11-18 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 40 | 40 |  |  |  |  | MDC1.C1.C1270: FS | MDC1.C1.C1450: FF, MDC1.C1.C1450: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | VECA Electricians | 720 | 0
MDC1.C1.C3230 | Not Started | MDC1-BL.5.3.1.4.6.4 | Task Dependent | Controls Installation | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 51 | 51 |  |  |  |  | MDC1.C1.C3170: FS | MDC1.C1.Cx2030: FS | VECA Electricians | 720 | 0
MDC1.C1.C2290 | Not Started | MDC1-BL.5.3.1.3.7.2 | Task Dependent | Mechanical Corridor Finishes | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 106 | 106 |  |  |  |  | MDC1.C1.C2190: FS, MDC1.C1.C2110: SS | MDC1.C1.C2470: FS, MDC1.C1.C2360: FS, MDC1.C1.C2350: FS | PCI | 180 | 0
MDC1.C1.C2300 | Not Started | MDC1-BL.5.3.1.4.7.4 | Task Dependent | Controls Installation | 2020-11-05 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 45 | 45 |  |  |  |  | MDC1.C1.C2200: FS, MDC1.C1.C2220: FS | MDC1.C1.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C1.C2310 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | EPMS Pull Wire / Term / Test | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2230: FS, MDC1.C1.C2180: FS | MDC1.C1.Cx2010: FF 6, MDC1.C1.C2370: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C2320 | Not Started | MDC1-BL.5.3.1.4.11.3 | Task Dependent | Controls Installation | 2020-11-18 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 45 | 45 |  |  |  |  | MDC1.C1.C2250: FS | MDC1.C1.C2400: FS, MDC1.C1.Cx2010: FS | VECA Electricians | 720 | 0
MDC1.C2.C4100 | Not Started | MDC1-BL.5.3.9.4.4.4 | Task Dependent | Fire Alarm Installation | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 72 | 72 |  |  |  |  | MDC1.C2.C4060: FS, MDC1.C2.C4040: FS, MDC1.C2.C4050: FS, MDC1-2527: FS | MDC1.C2.C4400: FS, MDC1-C2.P1900: FS | VECA Electricians | 240 | 0
MDC1.C3.C1110 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C3.C1050: FS, MDC1.C3.E1040: FS, MDC1.C3.E1050: FS | MDC1.C3.C1380: FS, MDC1.C3.C1360: FS, MDC1.C3.C1420: FS, MDC1.C3.C1200: FS, MDC1.C3.C1400: FS | VECA Electricians | 480 | 0
MDC1.C3.C3050 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 51 | 51 |  |  |  |  | MDC1.C3.C3010: FS | MDC1.C3.C3230: FS, MDC1.C3.C3080: FS, MDC1.C3.E1260: FS 5, MDC1.C3.C3200: FS, MDC1.C3.E1220: FS, MDC1.C3.C3350: SS, MDC1.C3.C3110: SS, MDC1.C3.C3370: SS, MDC1.C3.Cx2030: SS | CSI, VECA Electricians | 1440 | 0
MDC1.C3.C2110 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C3.C2050: FS, MDC1.C3.E1060: FS, MDC1.C3.E1070: FS | MDC1.C3.C2380: FS, MDC1.C3.C2350: FS, MDC1.C3.C2440: FS, MDC1.C3.C2190: FS, MDC1.C3.C2390: FS | VECA Electricians | 480 | 0
MDC1.C3.C4050 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 2 | 2 |  |  |  |  | MDC1.C3.C4000: FS | MDC1.C3.C4070: SS 6, MDC1.C3.C4290: FS, MDC1.C3.C4100: FS, MDC1.C3.E1270: FS 5, MDC1.C3.C4270: FS, MDC1.C3.E1240: FS, MDC1.S.1580: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C4.C1020 | Not Started | MDC1-BL.5.3.6.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C3010: FS, MDC1.C4.CS1060: FS | MDC1.C4.C3020: FS, MDC1-1958: SS, MDC1.C4.C1030: FS, MDC1.C4.C1060: FS | VECA Electricians | 960 | 0
MDC1.C4.C2020 | Not Started | MDC1-BL.5.3.6.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-11-12 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C4000: FS, MDC1.C4.CS1060: FS | MDC1.C4.C2060: FS, MDC1.C4.C4020: FS, MDC1.C4.C2030: FS, MDC1.S.1670: FS | VECA Electricians | 960 | 0
MDC1.S.1520 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | 2020-11-25 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 1 | 1 |  |  |  |  | MDC1.S.1220: FS, MDC1.S.1420: FS, MDC1.C3.C3040: FS, MDC1.C3.C4040: FS, MDC1.S.1510: FS, MDC1-1996: FS | MDC1.S.1660: FS, MDC1.S.1610: FS, MDC1.S.1710: FS, MDC1.S.1560: FS | VECA Electricians | 120 | 0
MDC1.S.1530 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -2 WEST UPMS | 2020-11-20 07:00 | 2020-11-30 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 34 | 34 |  |  |  |  | MDC1.S.1440: FS, MDC1.S.1360: FS, MDC1.S.1420: FS, MDC1.S.1490: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0
MDC1AD-1018 | Not Started | MDC1-BL.5.3.2.3.2 | Task Dependent | Finishes | 2020-10-28 07:00 | 2020-11-25 17:00 |  |  |  |  | 0 | 0 | 24 | 24 | 44 | 44 |  |  |  |  | MDC1AD-1016: FS, MDC1AD-1024: FS | MDC1AD-1027: FS, MDC1AD-1025: FS, MDC1AD-1026: FS | TCM, PCI | 2160 | 0
MDC1.C1.C3210 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Lift & Set MER in Place | 2020-11-20 07:00 | 2020-11-25 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.E1380: FS, MDC1.C1.E1220: FS, MDC1.C1.C3050: FS, MDC1.C1.C2270: FS | MDC1.C1.C3300: FS, MDC1.C1.C3250: FS, MDC1.C1.C4270: FS | VECA Electricians | 120 | 0
MDC1.C1.C3220 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Power Bus Installation | 2020-11-13 07:00 | 2020-11-25 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 28 | 28 |  |  |  |  | MDC1.C1.C3190: FS, MDC1.C1.C1260: FS | MDC1.C1.C3240: FS, MDC1.C1.E1430: FS | VECA Electricians | 1200 | 0
MDC1.C1.C1300 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Assemble MER & Complete Shipping Split (SE) | 2020-11-12 08:00 | 2020-11-25 08:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.C1250: FS | MDC1-P1050: FS, MDC1.C1.C1360: FS, MDC1.C1.C1410: FS |  | 0 | 0
MDC1.C1.C2280 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-11-20 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 6 | 6 |  |  |  |  | MDC1.C1.C2050: FS, MDC1.C1.C2270: FS | MDC1.C1.C2390: FS, MDC1.C1.C2430: FS, MDC1.C1.C2420: FS, MDC1.C1.C4280: FS | SURE STEEL | 160 | 0
MDC1.C2.C1190 | Not Started | MDC1-BL.5.3.9.4.1.4 | Task Dependent | Fire Alarm Installation | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C2.C1120: FS, MDC1.C2.C1080: FS | MDC1.C2.C1450: FS | VECA Electricians | 240 | 0
MDC1.C2.C3120 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C2.C3070: FS, MDC1.C2.E1220: FS, MDC1.C2.E1230: FS | MDC1.C2.C3430: FS, MDC1.C2.C3150: SS 5, MDC1.C2.C3180: FS, MDC1.C2.C3440: FS | TCM | 720 | 0
MDC1.C2.C2170 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C2110: FS, MDC1.C2.E1240: FS, MDC1.C2.E1250: FS | MDC1.C2.C2410: FS, MDC1.C2.C2180: SS 5, MDC1.C2.C2230: FS, MDC1.C2.C2430: FS | TCM | 720 | 0
MDC1.C3.C1100 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-20 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 54 | 54 |  |  |  |  | MDC1.C3.C1060: FS | MDC1.C3.C1160: FS, MDC1.C3.E1180: FS | SURE STEEL | 160 | 0
MDC1.C3.C2100 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-20 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 54 | 54 |  |  |  |  | MDC1.C3.C2060: FS | MDC1.C3.C2160: FS, MDC1.C3.E1200: FS | SURE STEEL | 160 | 0
MDC1.C4.C1010 | Not Started | MDC1-BL.5.3.6.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 86 | 86 |  |  |  |  | MDC1.C4.CS1090: FS | MDC1.C4.C1130: FS, MDC1.C4.C3010: FS, MDC1.C4.C1200: FS, MDC1.C4.C1240: FS, MDC1.C4.C1050: FS | PCI | 480 | 0
MDC1.C4.C2010 | Not Started | MDC1-BL.5.3.6.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-11-10 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 86 | 86 |  |  |  |  | MDC1.C4.CS1090: FS | MDC1.C4.C2130: FS, MDC1.C4.C4010: FS, MDC1.C4.C2200: FS, MDC1.C4.C2230: FS, MDC1.C4.C2050: FS | PCI | 480 | 0
MDC1.S.1510 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-3 - CELL-1 to Cell-3 | 2020-11-23 07:00 | 2020-11-24 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 1 | 1 |  |  |  |  | MDC1.C3.C3040: FS, MDC1.C3.C1040: FS, MDC1-1996: FS | MDC1.S.1610: FS, MDC1.S.1520: FS | VECA Electricians | 120 | 0
MDC1-1975 | Not Started | MDC1-BL.5.3.2.4.5.4 | Task Dependent | Fire Alarm Installation | 2020-11-09 07:00 | 2020-11-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 42 | 42 |  |  |  |  | MDC1-1964: FS, MDC1-1963: FS | MDC1-1976: FS | VECA Electricians | 240 | 0
MDC1.C2.C1180 | Not Started | MDC1-BL.5.3.9.4.9.1 | Task Dependent | HAC Installation | 2020-11-09 07:00 | 2020-11-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C1110: FS | MDC1.C2.C1230: FS, MDC1.C2.C1270: FS | TCM | 480 | 0
MDC1.C2.C2160 | Not Started | MDC1-BL.5.3.9.4.11.1 | Task Dependent | HAC Installation | 2020-11-09 07:00 | 2020-11-23 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C2.C2100: FS | MDC1.C2.C2220: FS | TCM | 480 | 0
MDC1.C3.C1090 | Not Started | MDC1-BL.5.3.8.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-17 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C2.C3090: FS, MDC1.C2.C3030: FS, MDC1.C3.CS1090: FS, MDC1-C3.P1500: FS | MDC1.C3.C3060: FS, MDC1.C3.C1210: FS | TCM, VECA Electricians | 800 | 0
MDC1.C3.C2090 | Not Started | MDC1-BL.5.3.8.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-11-17 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 29 | 29 |  |  |  |  | MDC1.C2.C4070: FS, MDC1.C2.C4020: FS | MDC1.C3.C4060: FF, MDC1.C3.C2240: FS, MDC1.C3.C4060: FS | TCM, VECA Electricians | 800 | 0
MDC1.C3.C3040 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-18 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C3.C3020: FS, MDC1.C3.E1080: FS, MDC1.C3.E1090: FS | MDC1.S.1640: FS, MDC1.S.1630: FS, MDC1.S.1510: FS, MDC1.S.1520: FS | VECA Electricians | 80 | 0
MDC1.C3.C4040 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-18 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.C3.C4010: FS, MDC1.C3.E1100: FS, MDC1.C3.E1110: FS | MDC1.S.1640: FS, MDC1.S.1520: FS, MDC1.S.1560: FS | VECA Electricians | 80 | 0
MDC1.S.1500 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-2 | 2020-11-18 07:00 | 2020-11-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C2.C4030: FS, MDC1.C2.C2020: FS, MDC1.C2.C3040: FS, MDC1.C2.C1030: FS, MDC1.S.1390: FS, MDC1.S.1280: FS, MDC1.S.1110: FS, MDC1.S.1480: FS, MDC1.S.1480: FF, MDC1-1996: FS | MDC1.S.1790: FS, MDC1.S.1640: FS | VECA Electricians | 240 | 0
MDC1.C2.C3110 | Not Started | MDC1-BL.5.3.9.3.2.1 | Task Dependent | Hang Wall Partitions | 2020-11-11 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 13 | 13 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C3090: SS 6 | MDC1.C2.C3130: SS 6, MDC1.C2.C3170: FS | PCI | 600 | 0
MDC1.C2.C4090 | Not Started | MDC1-BL.5.3.9.3.4.1 | Task Dependent | Hang Wall Partitions | 2020-11-11 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 13 | 13 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C4070: SS 6 | MDC1.C2.C4110: SS 6, MDC1.C2.C4140: FS | PCI | 600 | 0
MDC1.C3.C1070 | Not Started | MDC1-BL.5.3.8.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C1030: FS | MDC1.C3.C1140: FS, MDC1.C3.C1130: FS, MDC1.C3.C3090: FS, MDC1.C3.C1120: FS, MDC1.C3.E1140: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C3.C1080 | Not Started | MDC1-BL.5.3.8.4.5.4 | Task Dependent | Fire Riser Installation | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C1030: FS | MDC1.C3.C1150: FS |  | 0 | 0
MDC1.C3.C3030 | Not Started | MDC1-BL.5.3.8.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C1030: FS | MDC1.C3.C3070: FS, MDC1.C3.C3160: FS, MDC1.C3.C3210: FS | PCI | 480 | 0
MDC1.C3.C2070 | Not Started | MDC1-BL.5.3.8.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.C2030: FS | MDC1.C3.C2140: FS, MDC1.C3.C2130: FS, MDC1.C3.C4110: FS, MDC1.C3.C2120: FS, MDC1.C3.E1150: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C3.C2080 | Not Started | MDC1-BL.5.3.8.4.7.4 | Task Dependent | Fire Riser Installation | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 81 | 81 |  |  |  |  | MDC1.C3.C2030: FS | MDC1.C3.C2150: FS |  | 0 | 0
MDC1.C3.C4030 | Not Started | MDC1-BL.5.3.8.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-06 07:00 | 2020-11-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C3.CS1090: FS, MDC1.C3.C2030: FS | MDC1.C3.C4200: FS, MDC1.C3.C4240: FS, MDC1.C3.C4080: FS | PCI | 480 | 0
MDC1.C1.C1290 | Not Started | MDC1-BL.5.3.1.4.5.2 | Task Dependent | Hydronic Piping Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C1230: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0
MDC1.C1.C3200 | Not Started | MDC1-BL.5.3.1.3.6.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C1210: FS, MDC1.C1.CS1110: FS, MDC1.C1.C1170: FS, MDC1-2105: FS | MDC1.C1.C3290: FS, MDC1.C1.C3280: FS, MDC1.C1.C3270: FS, MDC1.C1.E1390: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C1.C2260 | Not Started | MDC1-BL.5.3.1.4.7.2 | Task Dependent | Hydronic Piping Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C2210: FS | MDC1.C1.Cx2000: FF, MDC1-C1.P1800: FS | TCM | 480 | 0
MDC1.C1.C4190 | Not Started | MDC1-BL.5.3.1.3.8.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2190: FS, MDC1.C1.CS1110: FS, MDC1.C1.C2160: FS, MDC1-2105: FS | MDC1.C1.C4250: FS, MDC1.C1.C4240: FS, MDC1.C1.C4230: FS, MDC1.C1.C4230: SS 5, MDC1.C1.E1400: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C1.C4200 | Not Started | MDC1-BL.5.3.1.4.8.4 | Task Dependent | Fire Alarm System | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C1.C4160: FS | MDC1.C1.C4290: FS | VECA Electricians | 240 | 0
MDC1.C2.C1160 | Not Started | MDC1-BL.5.3.9.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1100: FS | MDC1.C2.C1200: FS, MDC1.C2.C3190: FS, MDC1.C2.C1200: SS 5, MDC1.C2.E1260: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C2.C1170 | Not Started | MDC1-BL.5.3.9.4.5.4 | Task Dependent | Fire Riser Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1100: FS | MDC1.C2.C1220: FS |  | 0 | 0
MDC1.C2.C3100 | Not Started | MDC1-BL.5.3.9.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C1100: FS | MDC1.C2.C3350: FS, MDC1.C2.C3400: FS, MDC1.C2.C3160: FS | PCI | 480 | 0
MDC1.C2.C2140 | Not Started | MDC1-BL.5.3.9.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C2080: FS | MDC1.C2.C2190: FS, MDC1.C2.C4150: FS, MDC1.C2.C2190: SS 5, MDC1.C2.E1270: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C2.C2150 | Not Started | MDC1-BL.5.3.9.4.7.4 | Task Dependent | Fire Riser Installation | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C2080: FS | MDC1.C2.C2210: FS |  | 0 | 0
MDC1.C2.C4080 | Not Started | MDC1-BL.5.3.9.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C2080: FS | MDC1.C2.C4300: FS, MDC1.C2.C4340: FS, MDC1.C2.C4130: FS | PCI | 480 | 0
MDC1.C3.C1060 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C1050: SS 6, MDC1.C3.C1000: FS, MDC1.C2.C1060: FS | MDC1.C3.C1100: FS, MDC1.C4.C1070: FS, MDC1.C4.C1070: FF, MDC1-C3.P1700: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C3.C2060 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C2050: SS 6, MDC1.C3.C2020: FS | MDC1.C3.C2100: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C3.C4020 | Not Started | MDC1-BL.5.3.8.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 62 | 62 |  |  |  |  | MDC1.C3.C2020: FS | MDC1.C3.C4070: FS | TCM | 720 | 0
MDC1.C4.C2000 | Not Started | MDC1-BL.5.3.6.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-11-05 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 74 | 74 |  |  |  |  | MDC1.C4.C3000: FS | MDC1.C4.C2070: FS, MDC1.C4.C4000: FS | TCM | 720 | 0
MDC1.C1.C2270 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Lift & Set MER in Place | 2020-11-13 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.C2050: FS, MDC1.C1.E1150: FS, MDC1.C1.E1330: FS, MDC1.C1.C1250: FS | MDC1.C1.C2340: FS, MDC1.C1.C2280: FS, MDC1.C1.C3210: FS | VECA Electricians | 120 | 0
MDC1.S.1490 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -2 East UPMS | 2020-11-12 07:00 | 2020-11-19 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 34 | 34 |  |  |  |  | MDC1.S.1400: FS, MDC1.S.1420: FS, MDC1.S.1450: FS | MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1530: FS | VECA Electricians | 360 | 0
MDC1.C1.C1280 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Steel Support for OH Conductors & Cable Tray Installation | 2020-11-12 08:00 | 2020-11-19 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 5 | 5 |  |  |  |  | MDC1.C1.C1250: FS | MDC1.C1.C1360: FS, MDC1.C1.C1420: FS, MDC1.C1.C1410: FS, MDC1.C1.C3250: FS | SURE STEEL | 160 | 0
MDC1AD-1020 | Not Started | MDC1-BL.5.3.2.4.2 | Task Dependent | Domestic Water Piping | 2020-10-28 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 50 | 50 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1022: FS | TCM | 360 | 0
MDC1.C2.C1140 | Not Started | MDC1-BL.5.3.9.3.1.2 | Task Dependent | Datahall Finishes | 2020-11-06 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 57 | 57 |  |  |  |  | MDC1.C2.C1110: SS 6 | MDC1.C2.C1300: FS | PCI | 400 | 0
MDC1.C2.C1150 | Not Started | MDC1-BL.5.3.9.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-04 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 63 | 63 |  |  |  |  | MDC1.C2.C1090: FS | MDC1.C2.C1350: FS, MDC1.C2.C1320: FS, MDC1.C2.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C2.C2120 | Not Started | MDC1-BL.5.3.9.3.3.2 | Task Dependent | Datahall Finishes | 2020-11-06 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 51 | 51 |  |  |  |  | MDC1.C2.C2100: SS 6 | MDC1.C2.C2280: FS | PCI | 400 | 0
MDC1.C2.C2130 | Not Started | MDC1-BL.5.3.9.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2020-11-04 07:00 | 2020-11-18 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 63 | 63 |  |  |  |  | MDC1.C2.C2070: FS | MDC1.C2.C2440: FS, MDC1.C2.C2320: FS, MDC1.C2.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C3.E1120 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-1 |  | 2020-11-18 17:00 |  |  | 2020-11-18 17:00 |  | 0 | 0 | 0 | 0 | 52 | 52 |  |  |  |  | MDC1.C3.C1050: FS 5 | MDC1.C3.C1230: FS |  | 0 | 0
MDC1.C3.E1130 | Not Started | MDC1-BL.4.10.2.1.3 | Finish Milestone | Pad Ready for MER COLO-3 Cell-2 |  | 2020-11-18 17:00 |  |  | 2020-11-18 17:00 |  | 0 | 0 | 0 | 0 | 57 | 57 |  |  |  |  | MDC1.C3.C2050: FS 5 | MDC1.C3.C2260: FS |  | 0 | 0
MDC1.C1.C1270 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | PDU's Installation | 2020-11-13 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 27 | 27 |  |  |  |  | MDC1.C1.C1260: FS, MDC1.C1.C1140: FS, MDC1.C1.E1340: FS, MDC1.C1.E1350: FS | MDC1.C1.C1450: FS, MDC1.C1.C1350: FS, MDC1.C1.C1340: FS, MDC1.C1.C1400: FS | VECA Electricians | 180 | 0
MDC1.C1.C2250 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | PDU's Installation | 2020-11-13 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 32 | 32 |  |  |  |  | MDC1.C1.C2240: FS, MDC1.C1.C2130: FS, MDC1.C1.E1360: FS, MDC1.C1.E1370: FS | MDC1.C1.C2380: FS, MDC1.C1.C2400: FS, MDC1.C1.C2330: FS, MDC1.C1.C2330: FF, MDC1.C1.C2320: FS | VECA Electricians | 180 | 0
MDC1.C3.C3020 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-11-12 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C3.C3010: FS | MDC1.C3.C3040: FS, MDC1.C3.E1080: FS | CSI, VECA Electricians | 480 | 0
MDC1.C3.C4010 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-11-12 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 3 | 3 |  |  |  |  | MDC1.C3.C4000: FS | MDC1.C3.C4040: FS, MDC1.C3.E1100: FS | CSI, VECA Electricians | 480 | 0
MDC1.S.1470 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - Vault to UMS- UMS to JAZ run | 2020-11-09 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1210: FS, MDC1.S.1410: FS, MDC1-2133: FS, MDC1.S.1170: FS, MDC1.S.1370: FS | MDC1.S.1680: FS, MDC1.S.1550: FS | VECA Electricians | 420 | 0
MDC1.S.1480 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | PULL- URS to COLO-1 | 2020-11-12 07:00 | 2020-11-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C1.C4040: FS, MDC1.C1.C2040: FS, MDC1.C1.C3040: FS, MDC1-1963: FS, MDC1.S.1390: FS, MDC1.S.1110: FS, MDC1.S.1260: FS, MDC1.S.1100: FS, MDC1.S.1310: FS, MDC1.S.1440: FS, MDC1-1996: FS | MDC1.S.1790: FS, MDC1.S.1500: FS, MDC1.S.1500: FF | VECA Electricians | 240 | 0
MDC1.C1.C4180 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | Cable Tray Installation | 2020-11-02 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 17 | 17 |  |  |  |  | MDC1.C1.C2180: FS, MDC1.C1.C4140: FS, MDC1-2106: FS | MDC1.C1.C4260: FS, MDC1.C2.C2220: FS, MDC1.C1.C4210: FS, MDC1.C1.C4330: FS, MDC1.C1.C4380: FS | VECA Electricians | 1440 | 0
MDC1.C2.C1130 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-11-02 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 83 | 83 |  |  |  |  | MDC1.C2.C1120: SS 5 | MDC1.C2.Cx2010: FS | TCM | 720 | 0
MDC1.C2.C3090 | Not Started | MDC1-BL.5.3.9.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-11-04 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C1090: FS, MDC1.C2.C3030: FS | MDC1.C2.C3250: FS, MDC1.C2.C3140: FS, MDC1.C3.C1090: FS, MDC1.C2.C3110: SS 6, MDC1.C2.E1340: FS | VECA Electricians | 1200 | 0
MDC1.C2.C4070 | Not Started | MDC1-BL.5.3.9.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-11-04 07:00 | 2020-11-16 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 13 | 13 |  |  |  |  | MDC1.C2.C2070: FS, MDC1.C2.C4020: FS | MDC1.C2.C4190: FS, MDC1.C2.C4120: FS, MDC1.C3.C2090: FS, MDC1.C2.C4090: SS 6 | VECA Electricians | 1200 | 0
MDC1-1971 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-31 07:00 | 2020-11-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 71 | 71 |  |  |  |  | MDC1-1964: SS 5 | MDC1.AD.Cx2000: FS | TCM | 720 | 0
MDC1AD-1021.1 | Not Started | MDC1-BL.5.3.2.4.4 | Task Dependent | Set Mechanical Equipment | 2020-10-28 07:00 | 2020-11-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 35 | 35 |  |  |  |  | MDC1AD-1016: FS | MDC1AD-1021: FS | TCM | 300 | 0
MDC1.S.1460 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Builing to South Vault- URS Run | 2020-11-06 07:00 | 2020-11-13 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 15 | 15 |  |  |  |  | MDC1.S.1390: FS, MDC1.C3.C1010: FS | MDC1.S.1770: FS, MDC1.S.1640: FS, MDC1.S.1620: FS |  | 0 | 0
MDC1.C1.C3180 | Not Started | MDC1-BL.5.3.1.4.2.4 | Task Dependent | Fire Alarm Installation | 2020-10-30 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 46 | 46 |  |  |  |  | MDC1.C1.C3130: FS, MDC1.C1.C3080: FS | MDC1.C1.C3450: FS | VECA Electricians | 240 | 0
MDC1.C1.C3190 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | Cable Tray Installation | 2020-10-30 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3140: FS, MDC1-2106: FS | MDC1.C1.C3260: FS, MDC1.C1.C3220: FS, MDC1.C1.C3360: FS, MDC1.C1.C3330: FS, MDC1.C1.C3380: FS | VECA Electricians | 1440 | 0
MDC1.C1.C1260 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Power Bus Installation | 2020-11-02 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 27 | 27 |  |  |  |  | MDC1.C1.C1200: FS | MDC1.C1.C1270: FS, MDC1.C1.C3220: FS, MDC1.C1.E1340: FS | VECA Electricians | 1200 | 0
MDC1.C1.C2240 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Power Bus Installation | 2020-11-02 07:00 | 2020-11-12 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 32 | 32 |  |  |  |  | MDC1.C1.C2180: FS | MDC1.C1.C2250: FS, MDC1.C1.E1360: FS | VECA Electricians | 1200 | 0
MDC1.C1.C1250 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Lift & Set MER in Place | 2020-11-06 08:00 | 2020-11-12 08:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.E1320: FS, MDC1.C1.E1140: FS, MDC1.C1.C1050: FS, MDC1-C1.P1600: FS, MDC1.S.1030: FS, MDC1.S.1040: FS, MDC1.S.1120: FS, MDC1.S.1130: FS, MDC1.S.1300: FS | MDC1.C1.C1280: FS, MDC1.C1.C1300: FS, MDC1.C1.C2270: FS | VECA Electricians | 120 | 0
MDC1.C2.C3080 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 59 | 59 |  |  |  |  | MDC1.C2.C3050: FS, MDC1.C2.E1160: FS, MDC1.C2.E1170: FS | MDC1.C2.C3380: FS, MDC1.C2.C3430: FS, MDC1.C2.C3450: FS, MDC1.C2.C3180: FS, MDC1.C2.C3440: FS | VECA Electricians | 480 | 0
MDC1.C2.C4060 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1.C2.C4040: FS, MDC1.C2.E1180: FS, MDC1.C2.E1190: FS | MDC1.C2.C4370: FS, MDC1.C2.C4380: FS, MDC1.C2.C4390: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS | VECA Electricians | 480 | 0
MDC1.C3.C1050 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C3.C1010: FS, MDC1.C2.C1040: FS | MDC1.C3.C1060: SS 6, MDC1.C3.C1110: FS, MDC1-C3.P1600: FS, MDC1.C3.E1120: FS 5, MDC1.C3.C1230: FS, MDC1.C3.E1040: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C3.C3010 | Not Started | MDC1-BL.5.3.8.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C1010: FS | MDC1.C3.C3050: FS, MDC1.C3.C3020: FS, MDC1.C4.C1020: FS, MDC1.S.1620: FS | VECA Electricians | 960 | 0
MDC1.C3.C2050 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C2000: FS | MDC1.C3.C2060: SS 6, MDC1.C3.C2290: FS, MDC1.C3.C2110: FS, MDC1.C3.E1130: FS 5, MDC1.C3.C2260: FS, MDC1.C3.E1060: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C3.C4000 | Not Started | MDC1-BL.5.3.8.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-29 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C3.C2000: FS | MDC1.C3.C4050: FS, MDC1.C3.C4010: FS, MDC1.C4.C2020: FS | VECA Electricians | 960 | 0
MDC1.S.1440 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-2 Cell 2- Cell - 4 | 2020-11-10 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C2.C4030: FS, MDC1.C2.C2020: FS, MDC1.S.1050: FS, MDC1.S.1360: FF, MDC1.S.1360: FS, MDC1.C2.C2020: FF, MDC1.C2.C4030: FF, MDC1.S.1420: FS, MDC1-1996: FS | MDC1.S.1530: FS, MDC1.S.1560: FF, MDC1.S.1560: FS, MDC1.S.1480: FS | VECA Electricians | 120 | 0
MDC1.S.1450 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -1 East UPMS | 2020-11-05 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 34 | 34 |  |  |  |  | MDC1.S.1290: FS, MDC1.S.1380: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS, MDC1.S.1490: FS | VECA Electricians | 360 | 0
MDC1.C1.C1240 | Not Started | MDC1-BL.5.3.1.4.9.2 | Task Dependent | IDF Backbone Install | 2020-10-26 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 24 | 24 |  |  |  |  | MDC1.C1.C1200: SS 6 | MDC1.C1.C1330: FS, MDC1.C1.C3260: FS | LINX- TELECOM | 1440 | 0
MDC1.C1.C2230 | Not Started | MDC1-BL.5.3.1.4.11.2 | Task Dependent | IDF Backbone Install | 2020-10-26 07:00 | 2020-11-11 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 28 | 28 |  |  |  |  | MDC1.C1.C2180: SS 6 | MDC1.C1.C2310: FS, MDC1.C1.C4260: FS | LINX- TELECOM | 1440 | 0
MDC1.C4.CS1090 | Not Started | MDC1-BL.5.7.6.7.1.2 | Task Dependent | Slab on Grade | 2020-10-29 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 68 | 68 |  |  |  |  | MDC1.C4.CS1080: FF, MDC1.C3.CS1090: FS, A1170: FS, MDC1-C4.P1400: FS | MDC1.C4.C4010: FS, MDC1.C4.C2010: FS, MDC1.C4.C3010: FS, MDC1.C4.C1010: FS, MDC1.C4.C4190: FS, MDC1.C4.C2220: FS, MDC1.C4.C3190: FS, MDC1.C4.C1220: FS, MDC1.C4.C1140: FS, MDC1-C4.P1500: FS | CSI | 800 | 0
MDC1.C1.C4170 | Not Started | MDC1-BL.5.3.1.4.4.4 | Task Dependent | Fire Alarm Installation | 2020-10-27 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C1.C4120: FS, MDC1.C1.C4090: FS | MDC1.C1.C4450: FS | VECA Electricians | 240 | 0
MDC1.C2.C1120 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-10-27 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1070: FS, MDC1.C2.E1140: FS, MDC1.C2.E1150: FS, MDC1-C2.P1700: FS | MDC1.C2.C1430: FS, MDC1.C2.C1130: SS 5, MDC1.C2.C1190: FS, MDC1.C2.C1450: FS | TCM | 720 | 0
MDC1.C2.C3070 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-05 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 49 | 49 |  |  |  |  | MDC1.C2.C3060: FS | MDC1.C2.C3120: FS, MDC1.C2.E1220: FS | SURE STEEL | 160 | 0
MDC1.C2.C2110 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-11-05 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 34 | 34 |  |  |  |  | MDC1.C2.C2090: FS | MDC1.C2.C2170: FS, MDC1.C2.E1240: FS | SURE STEEL | 160 | 0
MDC1.S.1420 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | 2020-11-07 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.S.1220: FS, MDC1.S.1050: FS, MDC1.S.1290: FS, MDC1.C2.C2020: FS, MDC1.C2.C4030: FS, MDC1.S.1400: FS, MDC1-1996: FS | MDC1.S.1530: FS, MDC1.S.1490: FS, MDC1.S.1520: FS, MDC1.S.1440: FS | VECA Electricians | 120 | 0
MDC1.S.1430 | Not Started | MDC1-BL.5.1.3.3 | Task Dependent | Term COLO -1 WEST UPMS | 2020-11-03 07:00 | 2020-11-09 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 48 | 48 |  |  |  |  | MDC1.S.1360: FS, MDC1.S.1330: FS, MDC1.S.1290: FS | MDC1.S.1850: FF, MDC1.S.1850: FS, MDC1.S.1840: FS | VECA Electricians | 360 | 0
MDC1.C2.C1110 | Not Started | MDC1-BL.5.3.9.3.1.1 | Task Dependent | Hang Wall Partitions | 2020-10-30 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 11 | 11 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C1090: SS 6 | MDC1.C2.C1140: SS 6, MDC1.C2.C1180: FS | PCI | 600 | 0
MDC1.C2.C2100 | Not Started | MDC1-BL.5.3.9.3.3.1 | Task Dependent | Hang Wall Partitions | 2020-10-30 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 11 | 11 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C2.C2070: SS 6 | MDC1.C2.C2120: SS 6, MDC1.C2.C2160: FS | PCI | 600 | 0
MDC1-1964 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Set Exterior Mechanical CFCI Equipment | 2020-10-26 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 42 | 42 |  |  |  |  | MDC1-1970: FS, MDC1-2016: FS 6 | MDC1-1971: SS 5, MDC1-1975: FS, MDC1-1976: FS | VECA Electricians | 480 | 0
MDC1.S.1570 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Set MV Gear (UMS) | 2020-11-04 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 49 | 49 |  |  |  |  | MDC1.S.1370: FS, MDC1-2503: FS, MDC1-2509: FS, MDC1-1996: FS | MDC1.S.1850: FS | VECA Electricians | 240 | 0
MDC1.S.1410 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - Vault To JAZ - URS to JAZ run | 2020-10-31 07:00 | 2020-11-07 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1320: FS, MDC1.S.1320: FF | MDC1.S.1600: FS, MDC1.S.1470: FS | VECA Electricians | 420 | 0
MDC1.C3.C1040 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-03 07:00 | 2020-11-06 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C3.C1020: FS, MDC1.C3.E1000: FS, MDC1.C3.E1010: FS | MDC1.S.1640: FS, MDC1.S.1630: FS, MDC1.S.1510: FS | VECA Electricians | 80 | 0
MDC1.C3.C2040 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-11-03 07:00 | 2020-11-06 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 19 | 19 |  |  |  |  | MDC1.C3.C2010: FS, MDC1.C3.E1020: FS, MDC1.C3.E1030: FS | MDC1.S.1640: FS, MDC1.S.1560: FS | VECA Electricians | 80 | 0
MDC1.S.1400 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | 2020-11-05 07:00 | 2020-11-06 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C2.C3040: FS, MDC1.C2.C1030: FS, MDC1.C2.C1030: FF, MDC1.C2.C3040: FF, MDC1.S.1380: FS, MDC1-1996: FS | MDC1.S.1490: FS, MDC1.S.1420: FS | VECA Electricians | 120 | 0
MDC1-2016 | In Progress | MDC1-BL.4.14.2 | Task Dependent | Water treatment Skids Procurement | 2020-04-27 08:00 | 2020-11-06 12:00 |  |  |  |  | 42.86 | 83 | 110 | 193 | 56 | 56 |  |  |  |  | MDC1-2002: FS 7 | MDC1-1964: FS 6 |  | 0 | 0
MDC1.C3.C1030 | Not Started | MDC1-BL.5.3.8.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-22 07:00 | 2020-11-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.CS1090: FS | MDC1.C3.C3030: FS, MDC1.C3.C1070: FS, MDC1.C3.C1250: FS, MDC1.C3.C1290: FS, MDC1.C3.C1080: FS | PCI | 480 | 0
MDC1.C3.C2030 | Not Started | MDC1-BL.5.3.8.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-10-22 07:00 | 2020-11-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 53 | 53 |  |  |  |  | MDC1.C3.CS1090: FS | MDC1.C3.C2070: FS, MDC1.C3.C4030: FS, MDC1.C3.C2200: FS, MDC1.C3.C2220: FS, MDC1.C3.C2080: FS | PCI | 480 | 0
MDC1.S.1390 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank - Building to North Vault URS run | 2020-10-29 07:00 | 2020-11-05 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 15 | 15 |  |  |  |  | MDC1.S.1240: FS, MDC1.S.1280: FS, MDC1.C3.C1010: FS | MDC1.S.1480: FS, MDC1.S.1500: FS, MDC1.S.1460: FS |  | 0 | 0
MDC1.C1.C1210 | Not Started | MDC1-BL.5.3.1.3.5.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C1170: FS, MDC1.C1.C1120: FS, MDC1.C1.C1170: SS 5 | MDC1.C1.C1310: FS, MDC1.C1.C3200: FS | VECA Electricians | 960 | 0
MDC1.C1.C1220 | Not Started | MDC1-BL.5.3.1.4.5.1 | Task Dependent | VFD'S Installation & Wiring | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 40 | 40 |  |  |  |  | MDC1.C1.C1170: FS | MDC1.C1.C1320: FS, MDC1.C1.C1470: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C1.C1230 | Not Started | MDC1-BL.5.3.1.4.5.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C1170: FS, MDC1.C1.E1280: FS, MDC1.C1.E1300: FS | MDC1.C1.C1290: FS | TCM | 480 | 0
MDC1.C1.C3150 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 69 | 69 |  |  |  |  | MDC1.C1.C3130: SS 5 | MDC1.C1.Cx2030: FS | TCM | 720 | 0
MDC1.C1.C3160 | Not Started | MDC1-BL.5.3.1.4.6.4 | Task Dependent | Fire Riser Installation | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 51 | 51 |  |  |  |  | MDC1.C1.C3110: FS | MDC1.C1.C3170: SS |  | 0 | 0
MDC1.C1.C3170 | Not Started | MDC1-BL.5.3.1.4.6.4 | Task Dependent | Fire Alarm System | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 51 | 51 |  |  |  |  | MDC1.C1.C3160: SS | MDC1.C1.C3230: FS | VECA Electricians | 240 | 0
MDC1.C1.C2190 | Not Started | MDC1-BL.5.3.1.3.7.1 | Task Dependent | In-Wall MEPFP Rough-In (surface mounted Rough-in) | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2160: FS, MDC1.C1.C2160: SS 5 | MDC1.C1.C2290: FS, MDC1.C1.C4190: FS | VECA Electricians | 960 | 0
MDC1.C1.C2200 | Not Started | MDC1-BL.5.3.1.4.7.1 | Task Dependent | VFD'S Installation & Wiring | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 45 | 45 |  |  |  |  | MDC1.C1.C2160: FS | MDC1.C1.C2300: FS, MDC1.C1.C2470: FS, MDC1.C1.Cx3020: FS | VECA Electricians | 240 | 0
MDC1.C1.C2210 | Not Started | MDC1-BL.5.3.1.4.7.2 | Task Dependent | AHU/DOAS Equipment Setting | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 57 | 57 |  |  |  |  | MDC1.C1.C2160: FS, MDC1.C1.E1290: FS, MDC1.C1.E1310: FS | MDC1.C1.C2260: FS | TCM | 480 | 0
MDC1.C1.C2220 | Not Started | MDC1-BL.5.3.1.4.7.4 | Task Dependent | Fire Alarm System | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 45 | 45 |  |  |  |  | MDC1.C1.C2170: FS | MDC1.C1.C2300: FS | VECA Electricians | 240 | 0
MDC1.C1.C4160 | Not Started | MDC1-BL.5.3.1.4.8.4 | Task Dependent | Fire Riser Installation | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 43 | 43 |  |  |  |  | MDC1.C1.C4110: FS | MDC1.C1.C4200: FS |  | 0 | 0
MDC1.C2.C1100 | Not Started | MDC1-BL.5.3.9.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C1.C3110: FS | MDC1.C2.C1160: FS, MDC1.C2.C3100: FS, MDC1.C2.C1310: FS, MDC1.C2.C1360: FS, MDC1.C2.C1170: FS | PCI | 480 | 0
MDC1.C2.C3060 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C2.C3050: SS 6, MDC1.C2.C3000: FS | MDC1.C2.C3070: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C2080 | Not Started | MDC1-BL.5.3.9.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.CS1090: FS, MDC1.C1.C4110: FS | MDC1.C2.C4080: FS, MDC1.C2.C2140: FS, MDC1.C2.C2300: FS, MDC1.C2.C2360: SS 6, MDC1.C2.C2150: FS | PCI | 480 | 0
MDC1.C2.C2090 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C2030: SS 6, MDC1.C2.C2050: FS | MDC1.C2.C2110: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C4050 | Not Started | MDC1-BL.5.3.9.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 70 | 70 |  |  |  |  | MDC1.C2.C2050: FS | MDC1.C2.C4380: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.Cx3030: FS, MDC1.C2.Cx2030: FS | TCM | 720 | 0
MDC1.C3.C2020 | Not Started | MDC1-BL.5.3.8.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C3000: FS | MDC1.C3.C2060: FS, MDC1.C3.C4020: FS | TCM | 720 | 0
MDC1.C4.C3000 | Not Started | MDC1-BL.5.3.6.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-21 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 74 | 74 |  |  |  |  | MDC1.C4.C1000: FS | MDC1.C4.C3070: FS, MDC1.C4.C2000: FS | TCM | 720 | 0
MDC1.S.1380 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-1 - CELL-1 to Cell-3 | 2020-11-03 07:00 | 2020-11-04 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C2.C1030: FS, MDC1.C2.C3040: FS, MDC1.C1.C3040: FS, MDC1.C1.C1040: FS, MDC1.C1.C3040: FF, MDC1.S.1360: FS, MDC1.S.1310: FS, MDC1-1996: FS | MDC1.S.1450: FS, MDC1.S.1400: FS | VECA Electricians | 120 | 0
MDC1.C2.C1090 | Not Started | MDC1-BL.5.3.9.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-10-22 07:00 | 2020-11-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C2.C3030: FS, MDC1.C2.C1050: FS | MDC1.C2.C1210: FS, MDC1.C2.C1150: FS, MDC1.C2.C3090: FS, MDC1.C2.C1110: SS 6 | VECA Electricians | 1200 | 0
MDC1.C2.C2070 | Not Started | MDC1-BL.5.3.9.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-10-22 07:00 | 2020-11-03 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C2.C4020: FS, MDC1.C2.C2040: FS | MDC1.C2.C2200: FS, MDC1.C2.C2130: FS, MDC1.C2.C4070: FS, MDC1.C2.C2100: SS 6 | VECA Electricians | 1200 | 0
MDC1.C2.E1210 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-3 |  | 2020-11-03 17:00 |  |  | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 41 | 41 |  |  |  |  | MDC1.C2.C3050: FS 5 | MDC1.C2.C3230: FS |  | 0 | 0
MDC1.S.1370 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Set UMS vault | 2020-10-27 08:00 | 2020-11-03 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 5 | 5 |  |  |  |  | MDC1-2133: FS, MDC1.S.1170: FS, MDC1-2190: FS | MDC1.S.1570: FS, MDC1.S.1680: FS, MDC1.S.1470: FS, MDC1-2503: FS | VECA Electricians | 480 | 0
MDC1.C2.E1200 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-4 |  | 2020-11-03 08:00 |  |  | 2020-11-03 08:00 |  | 0 | 0 | 0 | 0 | 69 | 69 |  |  |  |  | MDC1.C2.C4040: FS 4 | MDC1.C2.C4220: FS |  | 0 | 0
MDC1.C3.C1020 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-29 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 13 | 13 |  |  |  |  | MDC1.C3.C1010: FS | MDC1.C3.C1040: FS, MDC1.C3.E1000: FS | CSI, VECA Electricians | 480 | 0
MDC1.C3.C2010 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-29 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 19 | 19 |  |  |  |  | MDC1.C3.C2000: FS | MDC1.C3.C2040: FS, MDC1.C3.E1020: FS | CSI, VECA Electricians | 480 | 0
MDC1.S.1350 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO-4 UPM to UPM | 2020-10-29 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 40 | 40 |  |  |  |  | MDC1.S.1220: FS, MDC1.C4.CS1030: FS, MDC1.C4.CS1050: FS, MDC1.C4.CS1070: FS | MDC1.S.1750: FS, MDC1.S.1710: FS |  | 0 | 0
MDC1.S.1360 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM COLO-1 Cell 2- Cell - 4 | 2020-10-31 07:00 | 2020-11-02 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C1.C2040: FS, MDC1.C1.C4040: FS, MDC1.S.1020: FS, MDC1.S.1330: FS, MDC1.S.1330: FF, MDC1-1996: FS | MDC1.S.1530: FS, MDC1.S.1430: FS, MDC1.S.1440: FF, MDC1.S.1440: FS, MDC1.S.1380: FS | VECA Electricians | 120 | 0
MDC1.C1.C1200 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | Cable Tray Installation | 2020-10-17 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 24 | 24 |  |  |  |  | MDC1.C1.C1150: FS, MDC1-2105: FS, MDC1-2106: FS | MDC1.C1.C1240: SS 6, MDC1.C1.C1260: FS, MDC1.C1.C1330: FS | VECA Electricians | 1440 | 0
MDC1.C1.C2180 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | Cable Tray Installation | 2020-10-17 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 17 | 17 |  |  |  |  | MDC1.C1.C2150: FS, MDC1.C1.C2130: FS, MDC1-2106: FS | MDC1.C1.C2230: SS 6, MDC1.C1.C4180: FS, MDC1.C1.C2310: FS, MDC1.C1.C2240: FS, MDC1.C1.C2380: FS | VECA Electricians | 1440 | 0
MDC1.C1.C4150 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-17 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 76 | 76 |  |  |  |  | MDC1.C1.C4120: SS 5 | MDC1.C1.Cx2050: FS | TCM | 720 | 0
MDC1.S.1340 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault - Set South Vault Along Vault to URS run | 2020-10-29 07:00 | 2020-10-31 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 23 | 23 |  |  |  |  | MDC1.S.1240: FS, MDC1.C3.C2000: FS | MDC1.S.1580: FS | VECA Electricians | 180 | 0
MDC1.S.1300 | Not Started | MDC1-BL.5.1.4 | Task Dependent | Aggregate Road Base | 2020-09-24 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 30 | 30 | 5 | 5 | Finish On or Before | 2020-11-23 17:00 |  |  | MDC1.S.1130: FS, MDC1.C4.CS1050: FS | MDC1.S.1880: FS, MDC1.S.1900: FS, MDC1.S.1870: FS, MDC1.C1.C1250: FS, MDC1.S.1860: FS | Advantage | 4000 | 0
MDC1.S.1310 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Set MV Gear (URS) | 2020-10-27 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 15 | 15 |  |  |  |  | MDC1-2004: FS, MDC1.S.1170: FS, MDC1-2504: FS, MDC1-2510: FS, MDC1-1996: FS | MDC1.S.1840: FS, MDC1.S.1480: FS, MDC1.S.1380: FS | VECA Electricians | 240 | 0
MDC1.S.1320 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - URS to vault - URS to JAZ run | 2020-10-22 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1270: FS, MDC1.S.1230: FS, MDC1.S.1270: FF | MDC1.S.1410: FS, MDC1.S.1410: FF | VECA Electricians | 420 | 0
MDC1.S.1330 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pul UPM to UPM Admin to COLO-1 Cell -2 | 2020-10-29 07:00 | 2020-10-30 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.S.1290: FS, MDC1.C1.C3040: FS, MDC1-1963: FS, MDC1.S.1100: FS, MDC1.S.1290: FF, MDC1-1996: FS | MDC1.S.1430: FS, MDC1.S.1360: FS, MDC1.S.1360: FF | VECA Electricians | 120 | 0
MDC1.C1.C3130 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-10-15 07:00 | 2020-10-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.C3100: FS, MDC1.C1.E1260: FS, MDC1.C1.E1270: FS | MDC1.C1.C3390: FS, MDC1.C1.C3150: SS 5, MDC1.C1.C3180: FS, MDC1.C1.C3450: FS | TCM | 720 | 0
MDC1.C1.C3140 | Not Started | MDC1-BL.5.3.1.4.10.1 | Task Dependent | HAC Installation | 2020-10-15 07:00 | 2020-10-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 23 | 23 |  |  |  |  | MDC1.C1.C3090: FS | MDC1.C1.C3190: FS | TCM | 480 | 0
MDC1.C1.C4140 | Not Started | MDC1-BL.5.3.1.4.13.1 | Task Dependent | HAC Installation | 2020-10-15 07:00 | 2020-10-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 19 | 19 |  |  |  |  | MDC1.C1.C4100: FS | MDC1.C1.C4180: FS | TCM | 480 | 0
MDC1.C4.CS1070 | Not Started | MDC1-BL.5.7.6.7.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-10-10 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 40 | 40 |  |  |  |  | MDC1.C3.CS1070: FF, MDC1.C4.CS1010: FS, MDC1.C3.CS1070: FS, MDC1.C4.CS1050: FS | MDC1.C4.CS1080: FF, MDC1-C4.P1400: FS, MDC1.S.1350: FS | TCM, VECA Electricians | 2100 | 0
MDC1.C4.CS1080 | Not Started | MDC1-BL.5.7.6.7.1.2 | Task Dependent | Aggregate Base Course | 2020-10-21 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 78 | 78 |  |  |  |  | MDC1.C4.CS1070: FF, MDC1.C4.CS1050: FS | MDC1.C4.CS1090: FF | CSI | 600 | 0
MDC1.C2.C1080 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 60 | 60 |  |  |  |  | MDC1.C2.C1040: FS, MDC1.C2.E1040: FS, MDC1.C2.E1050: FS | MDC1.C2.C1410: FS, MDC1.C2.C1430: FS, MDC1.C2.C1460: FS, MDC1.C2.C1190: FS, MDC1.C2.C1450: FS | VECA Electricians | 480 | 0
MDC1.C2.C3050 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 41 | 41 |  |  |  |  | MDC1.C2.C3010: FS | MDC1.C2.C3060: SS 6, MDC1.C2.C3270: FS, MDC1.C2.C3080: FS, MDC1.C2.E1210: FS 5, MDC1.C2.C3230: FS, MDC1.C2.E1160: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C2060 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 56 | 56 |  |  |  |  | MDC1.C2.C2030: FS, MDC1.C2.E1060: FS, MDC1.C2.E1070: FS | MDC1.C2.C2420: FS, MDC1.C2.C2410: FS, MDC1.C2.C2460: FS, MDC1.C2.C2230: FS, MDC1.C2.C2430: FS | VECA Electricians | 480 | 0
MDC1.C2.C4040 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C2.C4000: FS | MDC1.C2.C4250: FS, MDC1.C2.C4060: FS, MDC1.C2.E1200: FS 4, MDC1.C2.C4220: FS, MDC1.C2.E1180: FS, MDC1.C2.C4380: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.Cx3030: FS, MDC1.C2.Cx2030: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C3.C1010 | Not Started | MDC1-BL.5.3.8.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3010: FS, MDC1.C3.CS1060: FS | MDC1.C3.C1050: FS, MDC1.C3.C3010: FS, MDC1-1957: SS, MDC1.C3.C1020: FS, MDC1.S.1390: FS, MDC1.S.1460: FS | VECA Electricians | 960 | 0
MDC1.C3.C2000 | Not Started | MDC1-BL.5.3.8.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-10-14 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C4000: FS, MDC1.C3.CS1060: FS | MDC1.C3.C2050: FS, MDC1.C3.C2010: FS, MDC1.C3.C4000: FS, MDC1.S.1340: FS | VECA Electricians | 960 | 0
MDC1.S.1290 | Not Started | MDC1-BL.5.1.3.2 | Task Dependent | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | 2020-10-27 07:00 | 2020-10-28 17:00 |  |  |  |  | 0 | 0 | 2 | 2 | 13 | 13 |  |  |  |  | MDC1.C1.C4040: FS, MDC1.C1.C3040: FS, MDC1.S.1020: FS, MDC1-1996: FS | MDC1.S.1330: FS, MDC1.S.1430: FS, MDC1.S.1450: FS, MDC1.S.1420: FS, MDC1.S.1330: FF | VECA Electricians | 120 | 0
MDC1AD-1016 | Not Started | MDC1-BL.5.3.2.3.1 | Task Dependent | Hang Wall Partitions | 2020-10-06 07:00 | 2020-10-27 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 8 | 8 |  |  |  |  | MDC1.AD.CS1100: FS, MDC1-2101: FS, MDC1AD-1017: FS | MDC1AD-1018: FS, MDC1AD-1019: FS, MDC1AD-1020: FS, MDC1AD-1021: FS, MDC1AD-1021.1: FS, MDC1-2505: FS, MDC1-2506: FS, MDC1-2507: FS, MDC1-2508: FS | PCI | 900 | 0
MDC1.C1.C3120 | Not Started | MDC1-BL.5.3.1.3.2.2 | Task Dependent | Datahall Finishes | 2020-10-15 07:00 | 2020-10-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 52 | 52 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C3090: FS | MDC1.C1.C3240: FS | PCI | 400 | 0
MDC1.C1.C4130 | Not Started | MDC1-BL.5.3.1.3.4.2 | Task Dependent | Datahall Finishes | 2020-10-15 07:00 | 2020-10-27 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 56 | 56 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C4100: FS | MDC1.C1.C4220: FS | PCI | 400 | 0
MDC1.C1.C4120 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-10-12 07:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C4080: FS, MDC1.C1.E1240: FS, MDC1.C1.E1250: FS | MDC1.C1.C4410: FS, MDC1.C1.C4150: SS 5, MDC1.C1.C4170: FS, MDC1.C1.C4450: FS | TCM | 720 | 0
MDC1.C2.C1070 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-10-21 07:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 50 | 50 |  |  |  |  | MDC1.C2.C1060: FS | MDC1.C2.C1120: FS, MDC1.C2.E1140: FS | SURE STEEL | 160 | 0
MDC1-1996 | Not Started | MDC1-BL.4.11.5.1 | Task Dependent | MV Wire Procurement | 2020-08-04 08:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 15 | 15 |  |  |  |  | MDC1-2002: FS, MDC1-2134: FS | MDC1.C2.Cx2010: FS, MDC1.S.1290: FS, MDC1.S.1330: FS, MDC1.S.1360: FS, MDC1.S.1310: FS, MDC1.S.1380: FS, MDC1.S.1400: FS, MDC1.S.1420: FS, MDC1.S.1440: FS, MDC1.S.1480: FS, MDC1.S.1500: FS, MDC1.S.1510: FS, MDC1.S.1520: FS, MDC1.S.1570: FS, MDC1.S.1560: FS, MDC1.S.1730: FS, MDC1.S.1650: FS, MDC1.S.1630: FS, MDC1.S.1600: FS, MDC1.S.1640: FS, MDC1.S.1680: FS, MDC1.S.1710: FS, MDC1.S.1720: FS, MDC1.S.1740: FS, MDC1.S.1750: FS, MDC1.S.1770: FS |  | 0 | 0
MDC1-2132 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-08-04 08:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 42 | 42 |  |  |  |  | MDC1-2134: FS | MDC1.S.1600: FS |  | 0 | 0
MDC1-2133 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | UMS Vault Procurement DRB#1 | 2020-08-04 08:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 5 | 5 |  |  |  |  | MDC1-2134: FS, MDC1-2527: FS | MDC1.S.1370: FS, MDC1.S.1680: FS, MDC1.S.1470: FS |  | 0 | 0
MDC1.S.1280 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank COLO-2 UPM to Vault | 2020-10-21 07:00 | 2020-10-26 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 17 | 17 |  |  |  |  | MDC1.S.1240: FS, MDC1.S.1260: FS | MDC1.S.1500: FS, MDC1.S.1390: FS |  | 0 | 0
MDC1.C2.C3040 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-19 07:00 | 2020-10-22 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 21 | 21 |  |  |  |  | MDC1.C2.C3020: FS, MDC1.C2.E1080: FS, MDC1.C2.E1090: FS | MDC1.S.1500: FS, MDC1.S.1380: FS, MDC1.S.1400: FS, MDC1.S.1400: FF | VECA Electricians | 80 | 0
MDC1.C2.C4030 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-19 07:00 | 2020-10-22 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 25 | 25 |  |  |  |  | MDC1.C2.C4010: FS, MDC1.C2.E1100: FS, MDC1.C2.E1110: FS | MDC1.S.1500: FS, MDC1.S.1440: FS, MDC1.S.1420: FS, MDC1.S.1440: FF | VECA Electricians | 80 | 0
MDC1.C3.CS1090 | Not Started | MDC1-BL.5.7.5.7.1.2 | Task Dependent | Slab on Grade | 2020-10-10 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 49 | 49 |  |  |  |  | MDC1.C3.CS1080: FF, MDC1.C2.CS1090: FS, MDC1-C3.P1400: FS | MDC1.C3.C4030: FS, MDC1.C3.C2030: FS, MDC1.C3.C3030: FS, MDC1.C3.C1030: FS, MDC1.C3.C4230: FS, MDC1.C3.C2250: FS, MDC1.C3.C3190: FS, MDC1.C3.C1220: FS, MDC1.C4.CS1090: FS, MDC1.C3.C1090: FS, MDC1-C3.P1500: FS | CSI | 800 | 0
MDC1.C2.C3030 | Not Started | MDC1-BL.5.3.9.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-16 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C2.C1050: FS | MDC1.C2.C1090: FS, MDC1.C3.C1090: FS, MDC1.C2.C3090: FS | TCM, VECA Electricians | 800 | 0
MDC1.C2.C4020 | Not Started | MDC1-BL.5.3.9.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-16 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C2.C2040: FS | MDC1.C2.C2070: FS, MDC1.C3.C2090: FS, MDC1.C2.C4070: FS | TCM, VECA Electricians | 800 | 0
MDC1.S.1270 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - COLO-3 UPM to Vault UMS Run | 2020-10-17 07:00 | 2020-10-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.S.1230: FS | MDC1.S.1630: FS, MDC1.S.1320: FS, MDC1.S.1320: FF | VECA Electricians | 240 | 0
MDC1.C1.C1170 | Not Started | MDC1-BL.5.3.1.3.5.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C1120: FS, MDC1.C1.CS1110: FS, MDC1-C1.P1500: FS | MDC1.C1.C1230: FS, MDC1.C1.C1220: FS, MDC1.C1.C1210: FS, MDC1.C1.C1210: SS 5, MDC1.C1.C3200: FS, MDC1.C1.E1280: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C1.C1180 | Not Started | MDC1-BL.5.3.1.4.5.4 | Task Dependent | Fire Riser Installation | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C1.C1120: FS | MDC1.C1.C1190: SS |  | 0 | 0
MDC1.C1.C1190 | Not Started | MDC1-BL.5.3.1.4.5.4 | Task Dependent | Fire Alarm System | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C1.C1180: SS | MDC1.C1.C1320: FS | VECA Electricians | 240 | 0
MDC1.C1.C3110 | Not Started | MDC1-BL.5.3.1.3.6.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C1120: FS | MDC1.C2.C1100: FS, MDC1.C1.C3370: SS, MDC1.C1.C3430: FS, MDC1.C1.C3160: FS | PCI | 480 | 0
MDC1.C1.C2160 | Not Started | MDC1-BL.5.3.1.3.7.1 | Task Dependent | OverHead MEPFP Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 33 | 33 |  |  |  |  | MDC1.C1.C2110: FS, MDC1.C1.CS1110: FS | MDC1.C1.C2210: FS, MDC1.C1.C2200: FS, MDC1.C1.C2190: FS, MDC1.C1.C2190: SS 5, MDC1.C1.C4190: FS, MDC1.C1.E1290: FS | TCM, VECA Electricians | 1360 | 0
MDC1.C1.C2170 | Not Started | MDC1-BL.5.3.1.4.7.4 | Task Dependent | Fire Riser Installation | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 45 | 45 |  |  |  |  | MDC1.C1.C2110: FS | MDC1.C1.C2220: FS |  | 0 | 0
MDC1.C1.C4110 | Not Started | MDC1-BL.5.3.1.3.8.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C2110: FS | MDC1.C2.C2080: FS, MDC1.C1.C4350: SS, MDC1.C1.C4420: FS, MDC1.C1.C4160: FS | PCI | 480 | 0
MDC1.C2.C1060 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 50 | 50 |  |  |  |  | MDC1.C2.C1040: SS 6, MDC1.C2.C1000: FS, MDC1.C1.C1060: FS | MDC1.C2.C1070: FS, MDC1.C3.C1060: FS, MDC1-C2.P1700: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C2050 | Not Started | MDC1-BL.5.3.9.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C3000: FS | MDC1.C2.C2090: FS, MDC1.C2.C4050: FS | TCM | 720 | 0
MDC1.C3.C3000 | Not Started | MDC1-BL.5.3.8.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C3.C1000: FS | MDC1.C3.C2020: FS, MDC1.C3.C3350: FS, MDC1.C3.C3110: FS, MDC1.C3.C3370: FS, MDC1.C3.Cx2030: FS | TCM | 720 | 0
MDC1.C4.C1000 | Not Started | MDC1-BL.5.3.6.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-10-07 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 74 | 74 |  |  |  |  | MDC1.C3.C1000: FS | MDC1.C4.C1070: FS, MDC1.C4.C3000: FS | TCM | 720 | 0
MDC1.S.1260 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Back- Admin UPM to Vault | 2020-10-14 07:00 | 2020-10-20 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 17 | 17 |  |  |  |  | MDC1.S.1190: FS, MDC1.S.1100: FS, MDC1.S.1100: FF, MDC1.C2.C2000: FS, MDC1.C2.C4000: FS | MDC1.S.1480: FS, MDC1.S.1280: FS |  | 0 | 0
MDC1AD-1024 | Not Started | MDC1-BL.5.3.2.3.3 | Task Dependent | MEP Overhead | 2020-09-21 07:00 | 2020-10-19 17:00 |  |  |  |  | 0 | 0 | 24 | 24 | 50 | 50 |  |  |  |  | MDC1-2008: FS, MDC1.AD.CS1100: FS, MDC1-2102: FS, MDC1-2103: FS, MDC1-2104: FS, MDC1-2109: FS 21 | MDC1AD-1025: FS, MDC1AD-1018: FS | VECA Electricians | 2400 | 0
MDC1.C2.E1120 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-1 |  | 2020-10-19 17:00 |  |  | 2020-10-19 17:00 |  | 0 | 0 | 0 | 0 | 42 | 42 |  |  |  |  | MDC1.C2.C1040: FS 5 | MDC1.C2.C1250: FS |  | 0 | 0
MDC1.C2.E1130 | Not Started | MDC1-BL.4.10.2.1.2 | Finish Milestone | Pad Ready for MER COLO-2 Cell-2 |  | 2020-10-19 17:00 |  |  | 2020-10-19 17:00 |  | 0 | 0 | 0 | 0 | 48 | 48 |  |  |  |  | MDC1.C2.C2030: FS 5 | MDC1.C2.C2290: FS |  | 0 | 0
MDC1.C1.C1160 | Not Started | MDC1-BL.5.3.1.4.1.4 | Task Dependent | Fire Alarm Installation | 2020-10-05 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 56 | 56 |  |  |  |  | MDC1.C1.C1110: FS, MDC1.C1.C1090: FS | MDC1.C1.C1440: FS | VECA Electricians | 240 | 0
MDC1.C2.C3020 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-14 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 21 | 21 |  |  |  |  | MDC1.C2.C3010: FS | MDC1.C2.C3040: FS, MDC1.C2.E1080: FS | CSI, VECA Electricians | 480 | 0
MDC1.C2.C4010 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-10-14 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 25 | 25 |  |  |  |  | MDC1.C2.C4000: FS | MDC1.C2.C4030: FS, MDC1.C2.E1100: FS | CSI, VECA Electricians | 480 | 0
MDC1.S.1250 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Set URS Vault | 2020-10-09 07:00 | 2020-10-17 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 21 | 21 |  |  |  |  | MDC1-2004: FS | MDC1.S.1600: FS, MDC1-2504: FS | VECA Electricians | 480 | 0
MDC1.C3.CS1080 | Not Started | MDC1-BL.5.7.5.7.1.2 | Task Dependent | Aggregate Base Course | 2020-10-10 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 53 | 53 |  |  |  |  | MDC1.C3.CS1070: FF, MDC1.C3.CS1050: FS, MDC1-C3.P1400: FS | MDC1.C3.CS1090: FF | CSI | 600 | 0
MDC1.C1.C2140 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 78 | 78 |  |  |  |  | MDC1.C1.C2120: SS 5 | MDC1.C1.Cx2010: FS | TCM | 720 | 0
MDC1.C1.C1150 | Not Started | MDC1-BL.5.3.1.4.9.1 | Task Dependent | HAC Installation | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 24 | 24 |  |  |  |  | MDC1.C1.C1100: FS | MDC1.C1.C1200: FS | TCM | 480 | 0
MDC1.C1.C2150 | Not Started | MDC1-BL.5.3.1.4.11.1 | Task Dependent | HAC Installation | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 17 | 17 |  |  |  |  | MDC1.C1.C2100: FS | MDC1.C1.C2180: FS | TCM | 480 | 0
MDC1.S.1230 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | 2020-10-02 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.S.1070: FS, MDC1.S.1140: FS, MDC1.S.1180: FS | MDC1.S.1270: FS, MDC1.S.1320: FS | VECA Electricians | 720 | 0
MDC1.S.1240 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault - Set North Vault Along Vault to URS run | 2020-10-14 07:00 | 2020-10-16 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 20 | 20 |  |  |  |  | MDC1.S.1190: FS, MDC1.C2.C4000: FS | MDC1.S.1390: FS, MDC1.S.1280: FS, MDC1.S.1340: FS | VECA Electricians | 180 | 0
MDC1-2106 | Not Started | MDC1-BL.4.11.1.1 | Task Dependent | Design / Lead Time for Busway (OFCI Starline BOM Materials) | 2020-10-12 08:00 | 2020-10-16 16:00 |  |  |  |  | 0 | 0 | 5 | 5 | 21 | 21 | As Late As Possible |  |  |  | MDC1-2008: FS, MDC1-2003: FS | MDC1.C1.C1200: FS, MDC1.C1.C3190: FS, MDC1.C1.C2180: FS, MDC1.C1.C4180: FS |  | 0 | 0
MDC1.C2.C1050 | Not Started | MDC1-BL.5.3.9.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-10 07:00 | 2020-10-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C3070: FS, MDC1.C1.C3010: FS, MDC1.C2.CS1090: FS, MDC1-C2.P1500: FS | MDC1.C2.C1090: FS, MDC1.C2.C3030: FS | TCM, VECA Electricians | 800 | 0
MDC1.C2.C2040 | Not Started | MDC1-BL.5.3.9.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-10-10 07:00 | 2020-10-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C4070: FS, MDC1.C1.C4010: FS | MDC1.C2.C2070: FS, MDC1.C2.C4020: FS | TCM, VECA Electricians | 800 | 0
MDC1.C1.C1140 | Not Started | MDC1-BL.5.3.1.3.1.2 | Task Dependent | Datahall Finishes | 2020-10-02 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 51 | 51 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C1100: FS, MDC1-2529: FS | MDC1.C1.C1270: FS | PCI | 400 | 0
MDC1.C1.C3090 | Not Started | MDC1-BL.5.3.1.3.2.1 | Task Dependent | Hang Wall Partitions | 2020-10-06 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 23 | 23 |  |  |  |  | MDC1.C1.C3070: SS 6 | MDC1.C1.C3120: FS, MDC1.C1.C3140: FS | PCI | 600 | 0
MDC1.C1.C3100 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-10-10 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 38 | 38 |  |  |  |  | MDC1.C1.C3060: FS | MDC1.C1.C3130: FS, MDC1.C1.E1260: FS | SURE STEEL | 160 | 0
MDC1.C1.C2130 | Not Started | MDC1-BL.5.3.1.3.3.2 | Task Dependent | Datahall Finishes | 2020-10-02 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 19 | 19 |  |  |  |  | MDC1.C1.CS1120: FS, MDC1.C1.C2100: FS | MDC1.C1.C2180: FS, MDC1.C1.C2250: FS | PCI | 400 | 0
MDC1.C1.C4100 | Not Started | MDC1-BL.5.3.1.3.4.1 | Task Dependent | Hang Wall Partitions | 2020-10-06 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 19 | 19 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C4070: SS 6 | MDC1.C1.C4130: FS, MDC1.C1.C4140: FS | PCI | 600 | 0
MDC1.S.1220 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO-3 UPM to UPM | 2020-10-10 07:00 | 2020-10-14 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 32 | 32 |  |  |  |  | MDC1.S.1200: FS, MDC1.C3.CS1050: FS, MDC1.C4.CS1030: FS, MDC1.C3.CS1070: FS | MDC1.S.1560: FS, MDC1.S.1520: FS, MDC1.S.1420: FS, MDC1.S.1350: FS |  | 0 | 0
MDC1.C4.CS1060 | Not Started | MDC1-BL.5.7.6.7.2 | Task Dependent | Downspouts & Gutters | 2020-09-25 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 24 | 24 |  |  |  |  | MDC1.C4.CS1050: FS, MDC1.C3.CS1060: FS, MDC1.C4.CS1040: SS, MDC1.C3.CS1040: SS, MDC1-C3.P1200: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS, MDC1.C3.CS1040: FS, MDC1.C4.CS1030: FS, MDC1.C4.CS1040: FS | MDC1.C4.C1020: FS, MDC1.C4.C2020: FS, MDC1.S.1900: FS, MDC1.S.1870: FS | SURE STEEL | 900 | 0
MDC1.C1.C3080 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 41 | 41 |  |  |  |  | MDC1.C1.C3050: FS, MDC1.C1.E1180: FS, MDC1.C1.E1190: FS | MDC1.C1.C3410: FS, MDC1.C1.C3390: FS, MDC1.C1.C3470: FS, MDC1.C1.C3180: FS, MDC1.C1.C3450: FS, MDC1.C1.C3250: FS | VECA Electricians | 480 | 0
MDC1.C1.C4090 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 58 | 58 |  |  |  |  | MDC1.C1.C4050: FS, MDC1.C1.E1200: FS, MDC1.C1.E1210: FS | MDC1.C1.C4440: FS, MDC1.C1.C4410: FS, MDC1.C1.C4470: FS, MDC1.C1.C4170: FS, MDC1.C1.C4450: FS | VECA Electricians | 480 | 0
MDC1.C2.C1040 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 42 | 42 |  |  |  |  | MDC1.C2.C1010: FS | MDC1.C2.C1060: SS 6, MDC1.C2.C1290: FS, MDC1.C3.C1050: FS, MDC1.C2.C1080: FS, MDC1-C2.P1600: FS, MDC1.C2.E1120: FS 5, MDC1.C2.C1250: FS, MDC1.C2.E1050: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C3010 | Not Started | MDC1-BL.5.3.9.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C1010: FS | MDC1.C2.C4000: SS, MDC1.C2.C3050: FS, MDC1.C2.C3020: FS, MDC1.C3.C1010: FS | VECA Electricians | 960 | 0
MDC1.C2.C2030 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 46 | 46 |  |  |  |  | MDC1.C2.C2000: FS | MDC1.C2.C2090: SS 6, MDC1.C2.C2330: FS, MDC1.C2.C2060: FS, MDC1.C2.E1130: FS 5, MDC1.C2.C2290: FS, MDC1.C2.E1060: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C4000 | Not Started | MDC1-BL.5.3.9.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-29 07:00 | 2020-10-13 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C2.C3010: SS | MDC1.C2.C4040: FS, MDC1.C2.C4010: FS, MDC1.C3.C2000: FS, MDC1.S.1260: FS, MDC1.S.1240: FS | VECA Electricians | 960 | 0
MDC1.C1.C2120 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-09-26 07:00 | 2020-10-10 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C1.C2070: FS, MDC1.C1.E1160: FS, MDC1.C1.E1170: FS | MDC1.C1.C2420: FS, MDC1.C1.C2140: SS 5, MDC1.C1.C2410: FS, MDC1.C1.C2450: FS | TCM | 720 | 0
MDC1.C1.C4080 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-10-07 07:00 | 2020-10-10 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 48 | 48 |  |  |  |  | MDC1.C1.C4060: FS | MDC1.C1.C4120: FS, MDC1.C1.E1240: FS | SURE STEEL | 160 | 0
MDC1.S.1210 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank - JAZ to vault- UMS to JAZ run | 2020-10-02 07:00 | 2020-10-10 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 23 | 23 |  |  |  |  | MDC1.S.1170: FS, MDC1.S.1180: FS, MDC1-2131: FS, MDC1.S.1150: FS | MDC1.S.1680: FS, MDC1.S.1470: FS | VECA Electricians | 420 | 0
MDC1.C1.C1130 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Mechanical Equipment Piping Connections | 2020-09-25 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 79 | 79 |  |  |  |  | MDC1.C1.C1110: SS 5 | MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS | TCM | 720 | 0
MDC1.C3.CS1070 | Not Started | MDC1-BL.5.7.5.7.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-09-22 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 32 | 32 |  |  |  |  | MDC1.C2.CS1070: FS, MDC1.C3.CS1000: FS, MDC1.C3.CS1050: FS | MDC1.C4.CS1070: FF, MDC1.C3.CS1080: FF, MDC1.C4.CS1070: FS, MDC1-C3.P1400: FS, MDC1.S.1220: FS | TCM, VECA Electricians | 2100 | 0
MDC1.C1.C3060 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-25 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.C3050: SS 6, MDC1.C1.C3030: SS 15 | MDC1.C1.C3100: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C1.C3070 | Not Started | MDC1-BL.5.3.1.3.2.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-28 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C1080: FS, MDC1.C1.C3010: FS | MDC1.C2.C1050: FS, MDC1.C1.C3090: SS 6 | VECA Electricians | 1200 | 0
MDC1.C1.C4070 | Not Started | MDC1-BL.5.3.1.3.4.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-28 07:00 | 2020-10-09 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C2080: FS, MDC1.C1.C4010: FS | MDC1.C2.C2040: FS, MDC1.C1.C4100: SS 6 | VECA Electricians | 1200 | 0
MDC1-2004 | Not Started | MDC1-BL.4.11.5.1 | Task Dependent | URS Vault Procurement | 2020-07-17 08:00 | 2020-10-08 17:00 |  |  |  |  | 0 | 0 | 84 | 84 | 26 | 26 |  |  |  |  | MDC1-1997: FS, MDC1-2527: FS | MDC1.S.1310: FS, MDC1.C2.Cx2010: FS, MDC1.S.1250: FS |  | 0 | 0
MDC1.C2.C1030 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-05 07:00 | 2020-10-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 33 | 33 |  |  |  |  | MDC1.C2.C1020: FS, MDC1.C2.E1000: FS, MDC1.C2.E1010: FS | MDC1.S.1500: FS, MDC1.S.1380: FS, MDC1.S.1400: FS, MDC1.S.1400: FF | VECA Electricians | 80 | 0
MDC1.C2.C2020 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-10-05 07:00 | 2020-10-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 37 | 37 |  |  |  |  | MDC1.C2.C2010: FS, MDC1.C2.E1020: FS, MDC1.C2.E1030: FS | MDC1.S.1500: FS, MDC1.S.1440: FS, MDC1.S.1420: FS, MDC1.S.1440: FF | VECA Electricians | 80 | 0
MDC1.S.1120 | In Progress | MDC1-BL.5.1.10 | Task Dependent | Site Water / Fire Loop | 2020-07-24 07:00 | 2020-10-07 17:00 |  |  |  |  | 0 | 6 | 60 | 60 | 35 | 35 |  |  |  |  | MDC1-1997: FS, MDC1.S.1030: SS 30, MDC1.S.1130: SS 20 | MDC1.S.1910: FS, MDC1.C1.C1250: FS | Advantage | 3000 | 0
MDC1.S.1130 | In Progress | MDC1-BL.5.1.10 | Task Dependent | Site Storm | 2020-06-29 07:00 | 2020-10-07 17:00 |  |  |  |  | 13.75 | 11 | 69 | 80 | 5 | 5 |  |  |  |  | MDC1.S.1040: SS 30 | MDC1.S.1120: SS 20, MDC1.S.1300: FS, MDC1.C1.C1250: FS | Advantage | 4000 | 0
MDC1.C1.C1120 | Not Started | MDC1-BL.5.3.1.3.5.1 | Task Dependent | Frame & Hang Wall Partitions | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1-C1.P1500: FS, MDC1.C1.CS1110: FS | MDC1.C1.C3110: FS, MDC1.C1.C1170: FS, MDC1.C1.C1210: FS, MDC1.C1.C1310: FS, MDC1.C1.C1370: FS, MDC1.C1.C1180: FS | PCI | 480 | 0
MDC1.C1.C2110 | Not Started | MDC1-BL.5.3.1.3.7.1 | Task Dependent | Frame & Hang Wall Partitions - Mechanical Corridor | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1110: FS | MDC1.C1.C4110: FS, MDC1.C1.C2160: FS, MDC1.C1.C2290: SS, MDC1.C1.C2350: FS, MDC1.C1.C2170: FS | PCI | 480 | 0
MDC1.C1.C4060 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C4050: SS 6, MDC1.C1.C4030: FS | MDC1.C1.C4080: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C3000 | Not Started | MDC1-BL.5.3.9.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C2.C1000: FS | MDC1.C2.C3060: FS, MDC1.C2.C2050: FS | TCM | 720 | 0
MDC1.C3.C1000 | Not Started | MDC1-BL.5.3.8.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-22 07:00 | 2020-10-06 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 54 | 54 |  |  |  |  | MDC1.C2.C1000: FS | MDC1.C3.C1060: FS, MDC1.C3.C3000: FS, MDC1.C4.C1000: FS | TCM | 720 | 0
MDC1AD-1017 | Not Started | MDC1-BL.5.3.2.3.1 | Task Dependent | MEP Rough-In / Wall & Ceiling | 2020-09-21 07:00 | 2020-10-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.AD.CS1100: FS, MDC1-C1.P1500: FS, MDC1-2104: FS, MDC1-2109: FS 21 | MDC1AD-1016: FS | PCI, TCM, VECA Electricians | 2880 | 0
MDC1.C1.E1220 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-3 |  | 2020-10-05 17:00 |  |  | 2020-10-05 17:00 |  | 0 | 0 | 0 | 0 | 37 | 37 |  |  |  |  | MDC1.C1.C3050: FS 5 | MDC1.C1.C3210: FS |  | 0 | 0
MDC1.C1.E1230 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-4 |  | 2020-10-05 17:00 |  |  | 2020-10-05 17:00 |  | 0 | 0 | 0 | 0 | 46 | 46 |  |  |  |  | MDC1.C1.C4050: FS 5 | MDC1.C1.C4270: FS |  | 0 | 0
MDC1.S.1200 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - South Cross over (URS to west Vault Run) | 2020-09-21 07:00 | 2020-10-05 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1.S.1110: FF, MDC1.S.1110: FS | MDC1.S.1770: FS, MDC1.S.1640: FS, MDC1.S.1220: FS |  | 0 | 0
MDC1.C1.C1110 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 2020-09-19 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C1070: FS, MDC1-C1.P1700: FS, MDC1.C1.E1120: FS, MDC1.C1.E1130: FS | MDC1.C1.C1130: SS 5, MDC1.C1.C1160: FS, MDC1.C1.C1440: FS, MDC1.C1.C1410: FS | TCM | 720 | 0
MDC1.C2.CS1090 | Not Started | MDC1-BL.5.7.4.7.1.2 | Task Dependent | Slab on Grade | 2020-09-22 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 14 | 14 |  |  |  |  | MDC1.C2.CS1080: FF, MDC1.C1.CS1110: FS, A1170: FS, MDC1-C2.P1400: FS | MDC1.C2.C4080: FS, MDC1.C2.C2080: FS, MDC1.C2.C3100: FS, MDC1.C2.C1100: FS, MDC1.C2.C4090: FS, MDC1.C2.C2100: FS, MDC1.C2.C3110: FS, MDC1.C2.C1110: FS, MDC1.C3.CS1090: FS, MDC1.C2.C1050: FS, MDC1-C2.P1500: FS | CSI | 800 | 0
MDC1.C2.C1020 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-29 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 33 | 33 |  |  |  |  | MDC1.C2.C1010: FS | MDC1.C2.C1030: FS, MDC1.C2.E1000: FS | CSI, VECA Electricians | 480 | 0
MDC1.C2.C2010 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-29 07:00 | 2020-10-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 37 | 37 |  |  |  |  | MDC1.C2.C2000: FS | MDC1.C2.C2020: FS, MDC1.C2.E1030: FS | CSI, VECA Electricians | 480 | 0
MDC1.C1.C1100 | Not Started | MDC1-BL.5.3.1.3.1.1 | Task Dependent | Hang Wall Partitions | 2020-09-23 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 24 | 24 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C1080: SS 6 | MDC1.C1.C1140: FS, MDC1.C1.C1150: FS | PCI | 600 | 0
MDC1.C1.C2100 | Not Started | MDC1-BL.5.3.1.3.3.1 | Task Dependent | Hang Wall Partitions | 2020-09-23 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 8 | 8 | 17 | 17 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1.C1.C2080: SS 6 | MDC1.C1.C2130: FS, MDC1.C1.C2150: FS | PCI | 600 | 0
MDC1.S.1180 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank- Building to URS - 2nd Half | 2020-09-24 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1140: FS, MDC1.S.1140: FF, MDC1.C1.C3040: FS | MDC1.S.1770: FS, MDC1.S.1230: FS, MDC1.S.1210: FS | VECA Electricians | 420 | 0
MDC1.S.1190 | Not Started | MDC1-BL.5.1.3.1.1.2 | Task Dependent | Vault- Set North vault- Along UPM to Vault | 2020-09-29 07:00 | 2020-10-01 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 26 | 26 |  |  |  |  | MDC1.C2.C2000: FS, MDC1-2190: FS | MDC1.S.1240: FS, MDC1.S.1260: FS | VECA Electricians | 180 | 0
MDC1.S.1160 | In Progress | MDC1-BL.5.1.9 | Task Dependent | Telecom-Communications Site Loop/Ductbank | 2020-06-29 08:00 | 2020-10-01 08:00 |  |  |  |  | 4 | 3 | 72 | 75 | 79 | 79 |  |  |  |  | MDC1-1994: FS | MDC1.S.1540: FS, MDC1.S.1910: FS | VECA Electricians | 2500 | 0
MDC1-2008 | In Progress | MDC1-BL.4.11.1 | Task Dependent | BIM Modeling (Above ground) | 2020-08-02 08:00 | 2020-09-30 17:00 |  |  |  |  | 0 | 14 | 60 | 60 | 10 | 10 |  |  |  |  | MDC1-2003: FS, MDC1-1999: FS | MDC1AD-1024: FS, MDC1-2106: FS, MDC1-2109: FF |  | 0 | 0
MDC1-1963 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Set Exterior Electrical OFCI Equipment | 2020-09-16 07:00 | 2020-09-29 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1-1961: FS, MDC1-2000: FS | MDC1.S.1480: FS, MDC1.S.1330: FS, MDC1-1967: FS, MDC1-1968: FS, MDC1-1969: FS, MDC1-1975: FS, MDC1-1976: FS | VECA Electricians | 720 | 0
MDC1.C1.C1090 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 52 | 52 |  |  |  |  | MDC1.C1.C1050: FS, MDC1.C1.E1040: FS, MDC1.C1.E1050: FS | MDC1.C1.C1420: FS, MDC1.C1.C1410: FS, MDC1.C1.C1460: FS, MDC1.C1.C1160: FS, MDC1.C1.C1440: FS | VECA Electricians | 480 | 0
MDC1.C2.CS1080 | Not Started | MDC1-BL.5.7.4.7.1.2 | Task Dependent | Aggregate Base Course | 2020-09-22 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 18 | 18 |  |  |  |  | MDC1.C2.CS1070: FF, MDC1.C2.CS1050: FS, MDC1-C2.P1400: FS, MDC1.C2.CS1020: FS | MDC1.C2.CS1090: FF | CSI | 600 | 0
MDC1.C1.C3050 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 37 | 37 |  |  |  |  | MDC1.C1.C3000: FS | MDC1.C1.C3060: SS 6, MDC1.C1.C3250: FS, MDC1.C1.C3080: FS, MDC1.C1.E1220: FS 5, MDC1.C1.C3210: FS, MDC1.C1.E1180: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C1.C2090 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Set Exterior Electrical OFCI Equipment - GEN | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 59 | 59 |  |  |  |  | MDC1.C1.C2050: FS, MDC1.C1.E1060: FS, MDC1.C1.E1070: FS | MDC1.C1.C2430: FS, MDC1.C1.C2420: FS, MDC1.C1.C2460: FS, MDC1.C1.C2410: FS, MDC1.C1.C2450: FS | VECA Electricians | 480 | 0
MDC1.C1.C4050 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 46 | 46 |  |  |  |  | MDC1.C1.C4000: FS | MDC1.C1.C4060: SS 6, MDC1.C1.C4280: FS, MDC1.C1.C4090: FS, MDC1.C1.E1230: FS 5, MDC1.C1.C4270: FS, MDC1.C1.E1200: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C2.C1010 | Not Started | MDC1-BL.5.3.9.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS, MDC1.C1.C3000: FS, MDC1.C2.CS1060: FS | MDC1.C2.C1040: FS, MDC1.C2.C3010: FS, MDC1-1956: SS, MDC1.C2.C1020: FS | VECA Electricians | 960 | 0
MDC1.C2.C2000 | Not Started | MDC1-BL.5.3.9.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-09-15 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 26 | 26 |  |  |  |  | MDC1.C1.C4000: FS | MDC1.C2.C2030: FS, MDC1.C2.C2010: FS, MDC1.S.1260: FS, MDC1.S.1190: FS | VECA Electricians | 960 | 0
MDC1.S.1170 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- Set vault along UMS to Jaz run | 2020-09-25 07:00 | 2020-09-28 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 26 | 26 |  |  |  |  | MDC1.S.1150: FS, MDC1-2190: FS | MDC1.S.1210: FS, MDC1.S.1310: FS, MDC1.S.1370: FS, MDC1.S.1680: FS, MDC1.S.1470: FS | VECA Electricians | 180 | 0
MDC1-2189 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | JAZ Riser Support DRB#1 Procurement | 2020-07-21 08:00 | 2020-09-28 16:00 |  |  |  |  | 0 | 0 | 70 | 70 | 70 | 70 |  |  |  |  | MDC1-2140.2: FS | MDC1.S.1600: FS, MDC1.S.1680: FS |  | 0 | 0
MDC1-2105 | Not Started | MDC1-BL.4.11.1.1 | Task Dependent | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | 2020-06-30 08:00 | 2020-09-27 16:00 |  |  |  |  | 0 | 0 | 90 | 90 | 50 | 50 |  |  |  |  | MDC1-2003: FS | MDC1.C1.C3200: FS, MDC1.C1.C4190: FS, MDC1.C1.C1200: FS |  | 0 | 0
MDC1.C1.C1080 | Not Started | MDC1-BL.5.3.1.3.1.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-16 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C3010: FS, MDC1.C1.C1030: FS | MDC1.C1.C3070: FS, MDC1.C1.C1100: SS 6 | VECA Electricians | 1200 | 0
MDC1.C1.C2080 | Not Started | MDC1-BL.5.3.1.3.3.1 | Task Dependent | Overhead MEPFP Rough-In | 2020-09-16 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C1.C4010: FS, MDC1.C1.C2030: FS | MDC1.C1.C4070: FS, MDC1.C1.C2100: SS 6 | VECA Electricians | 1200 | 0
MDC1-1970 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-09-23 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 64 | 64 |  |  |  |  | MDC1-1962: FS, MDC1-2012: FS | MDC1-1964: FS | SURE STEEL | 160 | 0
MDC1.C1.CS1120 | Not Started | MDC1-BL.5.7.1.1.3 | Task Dependent | Erect Interior Structural Steel | 2020-09-22 07:00 | 2020-09-26 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 23 | 23 |  |  |  |  | MDC1.C1.CS1110: FS, MDC1-2010: FS | MDC1.C1.C1140: FS, MDC1.C1.C3120: FS, MDC1.C1.C4130: FS, MDC1.C1.C2130: FS | SURE STEEL | 500 | 0
MDC1.C1.C2070 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-09-22 07:00 | 2020-09-25 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 49 | 49 |  |  |  |  | MDC1.C1.C2060: FS | MDC1.C1.C2120: FS, MDC1.C1.E1160: FS | SURE STEEL | 160 | 0
MDC1.C3.CS1060 | Not Started | MDC1-BL.5.7.5.7.2 | Task Dependent | Downspouts & Gutters | 2020-09-05 07:00 | 2020-09-24 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 15 | 15 |  |  |  |  | MDC1.C3.CS1050: FS, MDC1.C2.CS1060: FS, MDC1.C3.CS1040: SS, MDC1-C3.P1200: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS, MDC1.C3.CS1040: FS | MDC1.C4.CS1060: FS, MDC1.C3.C1010: FS, MDC1.C3.C2000: FS | SURE STEEL | 900 | 0
MDC1.S.1150 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- Set vault along URS to JAX run | 2020-09-22 07:00 | 2020-09-24 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 26 | 26 |  |  |  |  | MDC1.S.1070: FS, MDC1-2190: FS | MDC1.S.1170: FS, MDC1.S.1210: FS | VECA Electricians | 180 | 0
MDC1.C1.C3040 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Set Electrical Equipment-UPM Cell -3 | 2020-09-19 07:00 | 2020-09-23 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C1.C1040: FS, MDC1.C1.C3020: FS, MDC1.C1.E1080: FS, MDC1.C1.E1090: FS | MDC1.S.1480: FS, MDC1.S.1290: FS, MDC1.S.1330: FS, MDC1.S.1380: FS, MDC1.C1.Cx2030: FS, MDC1.S.1380: FF, MDC1.S.1730: FS, MDC1.S.1180: FS | VECA Electricians | 80 | 0
MDC1.C1.C4040 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-09-19 07:00 | 2020-09-23 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 39 | 39 |  |  |  |  | MDC1.C1.C4020: FS, MDC1.C1.E1110: FS, MDC1.C1.E1100: FS | MDC1.S.1480: FS, MDC1.S.1360: FS, MDC1.S.1290: FS, MDC1.C1.Cx2050: FS, MDC1.S.1730: FS | VECA Electricians | 80 | 0
MDC1.S.1140 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct Bank- Building to URS - 1st Half | 2020-09-16 07:00 | 2020-09-23 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.S.1090: FS | MDC1.S.1770: FS, MDC1.S.1180: FS, MDC1.S.1230: FS, MDC1.S.1180: FF | VECA Electricians | 420 | 0
MDC1.C4.CS1050 | Not Started | MDC1-BL.5.7.6.7.2 | Task Dependent | Roof Panels Installation | 2020-09-04 07:00 | 2020-09-22 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 6 | 6 |  |  |  |  | MDC1.C3.CS1050: FS, MDC1-C4.P1300: FS, MDC1.C4.CS1040: SF, MDC1.C3.CS1040: SF, MDC1-C3.P1200: FF, MDC1.C2.CS1040: SF, MDC1.C1.CS1060: FF, MDC1.C2.CS1030: FF, MDC1.C2.CS1040: FF, MDC1.C3.CS1030: FF, MDC1.C3.CS1040: FF, MDC1.C4.CS1030: FF, MDC1.C4.CS1040: FF | MDC1.C4.CS1060: FS, MDC1.C4.CS1080: FS, MDC1.C4.CS1070: FS, MDC1.S.1350: FS, MDC1.S.1300: FS, MDC1.S.1900: FS, MDC1.S.1870: FS, MDC1-2529: FS | SURE STEEL | 1680 | 0
MDC1-1962 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-08 07:00 | 2020-09-22 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 64 | 64 |  |  |  |  | MDC1-1961: SS 6, MDC1-1972: SS 15 | MDC1-1970: FS | CSI, VECA Electricians | 1440 | 0
MDC1-2529 | Not Started | MDC1-BL.3.1 | Finish Milestone | Weather Tight |  | 2020-09-22 17:00 |  |  | 2020-09-22 17:00 |  | 0 | 0 | 0 | 0 | 59 | 59 |  |  |  |  | MDC1.C4.CS1050: FS, MDC1.C4.CS1040: FS | MDC1-C1.P1800: FS, MDC1.C1.C1140: FS |  | 0 | 0
MDC1.C1.CS1110 | Not Started | MDC1-BL.5.7.1.1.2 | Task Dependent | Slab on Grade | 2020-09-09 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 0 | 0 |  |  |  |  | MDC1.C1.CS1100: FS, MDC1.AD.CS1100: FS 4, A1170: FS, MDC1-1995: FS | MDC1.C1.C4110: FS, MDC1.C1.C3110: FS, MDC1.C1.C4100: FS, MDC1.C1.C2100: FS, MDC1.C1.C1100: FS, MDC1.C1.C2110: FS, MDC1.C1.C1120: FS, MDC1.C2.CS1090: FS, MDC1.C1.CS1120: FS, MDC1.C1.C1170: FS, MDC1.C1.C3200: FS, MDC1.C1.C2160: FS, MDC1.C1.C4190: FS, MDC1AD-1010: FS | CSI | 800 | 0
MDC1.C2.CS1070 | Not Started | MDC1-BL.5.7.4.7.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-09-02 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 14 | 14 |  |  |  |  | MDC1.C1.CS1090: FF, MDC1.C1.CS1090: FS, MDC1.C2.CS1020: FF, MDC1.C2.CS1050: FF | MDC1.C3.CS1070: FS, MDC1.C2.CS1080: FF, MDC1-C2.P1400: FS | TCM, VECA Electricians | 2100 | 0
MDC1.C1.C3030 | Not Started | MDC1-BL.5.3.1.4.2.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.C3000: SS 6 | MDC1.C1.C3060: SS 15 | TCM | 720 | 0
MDC1.C1.C2060 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C1.C2050: SS 6, MDC1.C1.C2020: FS | MDC1.C1.C2070: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C1.C4030 | Not Started | MDC1-BL.5.3.1.4.4.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C4000: SS 6, MDC1-2527: FS 10 | MDC1.C1.C4060: FS | TCM | 720 | 0
MDC1.C2.C1000 | Not Started | MDC1-BL.5.3.9.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-09-05 07:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C1.C1020: FS | MDC1.C2.C1060: FS, MDC1.C2.C3000: FS, MDC1.C3.C1000: FS | TCM | 720 | 0
MDC1-2010 | Not Started | MDC1-BL.4.13 | Task Dependent | Lead Time for COLO 1 Structural Interior Steel | 2020-06-30 08:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 83 | 83 | 28 | 28 |  |  |  |  | MDC1-2003: FS | MDC1.C1.CS1120: FS |  | 0 | 0
MDC1-2190 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | UPM to UMS Vaults Procurement DRB#1 | 2020-08-18 08:00 | 2020-09-21 17:00 |  |  |  |  | 0 | 0 | 35 | 35 | 31 | 31 |  |  |  |  | MDC1-2140.2: FS, MDC1-2135: FS, MDC1-2134: FS | MDC1.S.1190: FS, MDC1.S.1150: FS, MDC1.S.1170: FS, MDC1.S.1370: FS |  | 0 | 0
MDC1.C1.E1140 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-1 |  | 2020-09-19 17:00 |  |  | 2020-09-19 17:00 |  | 0 | 0 | 0 | 0 | 38 | 38 |  |  |  |  | MDC1.C1.C1050: FS 5 | MDC1.C1.C1250: FS |  | 0 | 0
MDC1.C1.E1150 | Not Started | MDC1-BL.4.10.2.1.1 | Finish Milestone | Pad Ready for MER COLO-1 Cell-2 |  | 2020-09-19 17:00 |  |  | 2020-09-19 17:00 |  | 0 | 0 | 0 | 0 | 44 | 44 |  |  |  |  | MDC1.C1.C2050: FS 5 | MDC1.C1.C2270: FS |  | 0 | 0
MDC1.S.1110 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - North Crossover (URS to west Vault Run) | 2020-09-04 07:00 | 2020-09-19 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1.S.1050: FS, MDC1.C3.CS1050: FS | MDC1.S.1500: FS, MDC1.S.1480: FS, MDC1.S.1200: FF, MDC1.S.1200: FS |  | 0 | 0
MDC1.C1.C1070 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Steel Supports for Exterior Mechanical Equipment | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 48 | 48 |  |  |  |  | MDC1.C1.C1060: FS | MDC1.C1.C1110: FS, MDC1.C1.E1120: FS | SURE STEEL | 160 | 0
MDC1.C1.C3020 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.C1.C3000: FS | MDC1.C1.C3040: FS, MDC1.C1.E1080: FS | CSI, VECA Electricians | 480 | 0
MDC1.C1.C4020 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 39 | 39 |  |  |  |  | MDC1.C1.C4000: FS | MDC1.C1.C4040: FS, MDC1.C1.E1100: FS | CSI, VECA Electricians | 480 | 0
MDC1.S.1100 | Not Started | MDC1-BL.5.1.3.1.2.5 | Task Dependent | Duct Bank Admin UPM to COLO-1 UPM | 2020-09-15 07:00 | 2020-09-18 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 37 | 37 |  |  |  |  | MDC1.AD.CS1080: FS, MDC1.C1.C4000: FS | MDC1.S.1330: FS, MDC1.S.1480: FS, MDC1.S.1260: FS, MDC1.S.1260: FF |  | 0 | 0
MDC1.C4.CS1040 | Not Started | MDC1-BL.5.7.6.7.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-09-02 07:00 | 2020-09-17 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 10 | 10 |  |  |  |  | MDC1.C4.CS1020: FS, MDC1.C3.CS1040: FS, MDC1.C3.CS1040: FF, MDC1-C4.P1200: FS, MDC1.C4.CS1030: FS | MDC1.C4.CS1060: SS, MDC1.C4.CS1050: SF, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1-2529: FS | SURE STEEL | 840 | 0
MDC1.C1.C3010 | Not Started | MDC1-BL.5.3.1.3.2.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-09 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C1030: FS, MDC1-C1.P1500: FS | MDC1.C1.C1080: FS, MDC1.C2.C1050: FS, MDC1.C1.C3070: FS | TCM, VECA Electricians | 800 | 0
MDC1.C1.C4010 | Not Started | MDC1-BL.5.3.1.3.4.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-09 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1.C1.C2030: FS, MDC1-C1.P1500: FS | MDC1.C1.C2080: FS, MDC1.C2.C2040: FS, MDC1.C1.C4070: FS | TCM, VECA Electricians | 800 | 0
MDC1-1961 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-08-31 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 36 | 36 |  |  |  |  | MDC1-1965: FS | MDC1-1967: FS, MDC1-1962: SS 6, MDC1-1963: FS | CSI, VECA Electricians | 1440 | 0
MDC1.S.1090 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct bank- COLO-2 UPM to north Valut | 2020-09-10 07:00 | 2020-09-15 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 0 | 0 |  |  |  |  | MDC1.S.1080: FS, MDC1.C1.C1010: FS, MDC1.C1.C1040: FS | MDC1.S.1140: FS | VECA Electricians | 240 | 0
MDC1.C1.C1050 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 38 | 38 |  |  |  |  | MDC1.C1.CS1070: SS 7, MDC1.C1.C1000: FS | MDC1.C1.C1060: SS, MDC1.C1.C1090: FS, MDC1-C1.P1600: FS, MDC1.C1.E1140: FS 5, MDC1.C1.C1250: FS, MDC1.C1.E1040: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C1.C1060 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Exterior Equipment Pads - Mechanical | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 48 | 48 |  |  |  |  | MDC1.C1.C1050: SS | MDC1.C1.C1070: FS, MDC1.C2.C1060: FS, MDC1-C1.P1700: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C1.C3000 | Not Started | MDC1-BL.5.3.1.4.2.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS, MDC1-2527: FS 10 | MDC1.C1.C3030: SS 6, MDC1.C1.C3050: FS, MDC1.C1.C3020: FS, MDC1.C2.C1010: FS | VECA Electricians | 960 | 0
MDC1.C1.C2050 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Exterior Equipment Pads - Electrical | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 44 | 44 |  |  |  |  | MDC1.C1.C2000: FS | MDC1.C1.C2060: SS 6, MDC1.C1.C2280: FS, MDC1.C1.C2090: FS, MDC1.C1.E1150: FS 5, MDC1.C1.C2270: FS, MDC1.C1.E1060: FS | CSI, VECA Electricians | 1440 | 0
MDC1.C1.C4000 | Not Started | MDC1-BL.5.3.1.4.4.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-29 07:00 | 2020-09-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 26 | 26 |  |  |  |  | MDC1.C1.C2000: FS, MDC1-2527: FS 10 | MDC1.C1.C4030: SS 6, MDC1.C1.C4050: FS, MDC1.C1.C4020: FS, MDC1.C2.C2000: FS, MDC1.S.1100: FS | VECA Electricians | 960 | 0
MDC1.S.1080 | Not Started | MDC1-BL.5.1.3.1.2.1 | Task Dependent | Duct bank- COLO-1 UPM to north vault | 2020-09-02 07:00 | 2020-09-09 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS, MDC1.S.1060: FS | MDC1.S.1090: FS | VECA Electricians | 360 | 0
MDC1.C1.CS1100 | Not Started | MDC1-BL.5.7.1.1.2 | Task Dependent | Aggregate Base Course | 2020-09-02 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 0 | 0 |  |  |  |  | MDC1.C1.CS1090: FS, MDC1.C1.CS1070: FS | MDC1.C1.CS1110: FS | CSI | 500 | 0
MDC1.C1.C1030 | Not Started | MDC1-BL.5.3.1.3.1.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-02 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1-C1.P1500: FS | MDC1.C1.C3010: FS, MDC1.C1.C1080: FS | TCM, VECA Electricians | 800 | 0
MDC1.C1.C2030 | Not Started | MDC1-BL.5.3.1.3.3.1 | Task Dependent | Frame wall & MEPFP In wall roughin | 2020-09-02 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 11 | 11 |  |  |  |  | MDC1-C1.P1500: FS | MDC1.C1.C2080: FS, MDC1.C1.C4010: FS | TCM, VECA Electricians | 800 | 0
MDC1.C1.C1040 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-09-03 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C1.C1010: FS, MDC1.C1.E1010: FS, MDC1.C1.E1000: FS | MDC1.C1.C3040: FS, MDC1.S.1380: FS, MDC1.C1.Cx2000: FS, MDC1-C1.P1800: FS, MDC1.S.1730: FS, MDC1.S.1090: FS | VECA Electricians | 80 | 0
MDC1.C1.C2040 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Set Electrical Equipment-UPM | 2020-09-03 07:00 | 2020-09-08 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 55 | 55 |  |  |  |  | MDC1.C1.C2010: FS, MDC1.C1.E1020: FS, MDC1.C1.E1030: FS | MDC1.S.1480: FS, MDC1.S.1360: FS, MDC1.C1.Cx2010: FS, MDC1.S.1730: FS | VECA Electricians | 80 | 0
MDC1.C1.C1020 | Not Started | MDC1-BL.5.3.1.4.1.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-08-21 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 34 | 34 |  |  |  |  | MDC1.C1.C1000: SS 6 | MDC1.C2.C1000: FS | TCM | 720 | 0
MDC1.C2.CS1060 | Not Started | MDC1-BL.5.7.4.7.2 | Task Dependent | Downspouts & Gutters | 2020-08-18 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 6 | 6 |  |  |  |  | MDC1.C2.CS1050: FS, MDC1.C1.CS1080: FS, MDC1.C2.CS1040: SS, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS | MDC1.C3.CS1060: FS, MDC1.C2.C1010: FS | SURE STEEL | 900 | 0
MDC1.C1.C2020 | Not Started | MDC1-BL.5.3.1.4.3.2 | Task Dependent | Mechanical/Plumbing Underground Rough-In | 2020-08-21 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 49 | 49 |  |  |  |  | MDC1.C1.C2000: SS 6 | MDC1.C1.C2060: FS | TCM | 720 | 0
MDC1.S.1070 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | 2020-09-02 07:00 | 2020-09-04 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 21 | 21 |  |  |  |  | MDC1.S.1060: FS | MDC1.S.1230: FS, MDC1.S.1150: FS | VECA Electricians | 180 | 0
MDC1.C3.CS1050 | Not Started | MDC1-BL.5.7.5.7.2 | Task Dependent | Roof Panels Installation | 2020-08-18 07:00 | 2020-09-03 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 6 | 6 |  |  |  |  | MDC1.C2.CS1050: FS, MDC1-C3.P1300: FS, MDC1-C3.P1200: FF, MDC1.C1.CS1060: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1040: FS, MDC1.C3.CS1030: FS | MDC1.C3.CS1060: FS, MDC1.C4.CS1050: FS, MDC1.C3.CS1080: FS, MDC1-C4.P1300: FS, MDC1.C3.CS1070: FS, MDC1.S.1110: FS, MDC1.S.1220: FS | SURE STEEL | 1680 | 0
MDC1.C1.C1010 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-08-29 07:00 | 2020-09-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 1 | 1 |  |  |  |  | MDC1.C1.C1000: FS | MDC1.C1.C1040: FS, MDC1.C1.E1000: FS, MDC1.S.1090: FS | CSI, VECA Electricians | 480 | 0
MDC1.C1.C2010 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Exterior Equipment Pads - for UPM's | 2020-08-29 07:00 | 2020-09-02 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 55 | 55 |  |  |  |  | MDC1.C1.C2000: FS | MDC1.C1.C2040: FS, MDC1.C1.E1030: FS | CSI, VECA Electricians | 480 | 0
MDC1.AD.CS1100 | Not Started | MDC1-BL.5.7.3.1.2 | Task Dependent | Slab on Grade | 2020-08-20 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 1 | 1 |  |  |  |  | MDC1.AD.CS1090: FS, MDC1-C1.P1400: FS | MDC1AD-1016: FS, MDC1AD-1017: FS, MDC1.C1.CS1110: FS 4, MDC1AD-1024: FS, MDC1-C1.P1500: FS | CSI | 800 | 0
MDC1.C1.CS1090 | Not Started | MDC1-BL.5.7.1.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-08-14 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 0 | 0 |  |  |  |  | MDC1.AD.CS1080: FS | MDC1.C2.CS1070: FF, MDC1.C1.CS1100: FS, MDC1.C2.CS1070: FS | TCM, VECA Electricians | 2100 | 0
MDC1.C4.CS1030 | Not Started | MDC1-BL.5.7.6.7.1.3 | Task Dependent | Secondary Steel | 2020-08-25 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 10 | 10 |  |  |  |  | MDC1.C4.CS1020: FS | MDC1.C4.CS1040: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1.S.1220: FS, MDC1.S.1350: FS | SURE STEEL | 210 | 0
MDC1.S.1060 | Not Started | MDC1-BL.5.1.3.1.1.1 | Task Dependent | Vault- set 1st Vault Along UMS Duct bank run | 2020-08-29 07:00 | 2020-09-01 17:00 |  |  |  |  | 0 | 0 | 3 | 3 | 0 | 0 |  |  |  |  | MDC1.C1.C1000: FS | MDC1.S.1070: FS, MDC1.S.1080: FS | VECA Electricians | 180 | 0
MDC1.C3.CS1040 | Not Started | MDC1-BL.5.7.5.7.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-08-17 07:00 | 2020-08-31 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 11 | 11 |  |  |  |  | MDC1.C3.CS1020: FS, MDC1.C2.CS1040: FS, MDC1-C3.P1200: FS, MDC1.C3.CS1030: FS | MDC1.C4.CS1040: FS, MDC1.C4.CS1040: FF, MDC1-C4.P1200: FS, MDC1.C3.CS1060: SS, MDC1-C4.P1200: SS, MDC1.C3.CS1060: FS, MDC1.C4.CS1060: SS, MDC1.C4.CS1050: SF, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF | SURE STEEL | 840 | 0
MDC1-1995 | In Progress | MDC1-BL.4.11.5.3 | Task Dependent | Site Temp Power Procurement & Infrastructure | 2020-06-29 08:00 | 2020-08-31 08:00 |  |  |  |  | 44.2 | 11 | 28 | 50 | 9 | 9 |  |  |  |  | MDC1-2003: FS | MDC1.C1.CS1110: FS, MDC1.AD.CS1090: FS |  | 0 | 0
MDC1-2109 | Not Started | MDC1-BL.4.11.1 | Finish Milestone | Admin/COLO-1 BIM Signoff |  | 2020-08-30 17:00 |  |  | 2020-08-30 17:00 |  | 0 | 0 | 0 | 0 | 9 | 9 | As Late As Possible |  |  |  | MDC1-2008: FF | MDC1AD-1017: FS 21, MDC1AD-1024: FS 21 |  | 0 | 0
MDC1-1965 | Not Started | MDC1-BL.5.3.2.4.5.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-08 07:00 | 2020-08-29 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 36 | 36 |  |  |  |  | MDC1-1999: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1-C1.P1200: FS, MDC1.AD.CS1070: FS, MDC1-2527: FS, MDC1-1993: FS | MDC1-1961: FS | VECA Electricians | 960 | 0
MDC1-1972 | Not Started | MDC1-BL.5.3.2.4.5.2 | Task Dependent | Mechanical Underground Rough-In | 2020-08-08 07:00 | 2020-08-29 17:00 |  |  |  |  | 0 | 0 | 18 | 18 | 73 | 73 |  |  |  |  | MDC1-1999: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1-C1.P1200: FS, MDC1.AD.CS1070: FS, MDC1-2527: FS | MDC1-1962: SS 15 | TCM | 720 | 0
MDC1.C1.C1000 | Not Started | MDC1-BL.5.3.1.4.1.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-14 07:00 | 2020-08-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 0 | 0 |  |  |  |  | MDC1.C1.CS1080: FS, MDC1.C1.CS1060: FS 4, MDC1.C1.CS1070: FS 2, MDC1-2527: FS 20 | MDC1.C1.C1050: FS, MDC1.C2.C1010: FS, MDC1-1955: SS, MDC1.C1.C1020: SS 6, MDC1.C1.C3000: FS, MDC1.C1.C1010: FS, MDC1.S.1060: FS, MDC1.S.1080: FS | VECA Electricians | 960 | 0
MDC1.C1.C2000 | Not Started | MDC1-BL.5.3.1.4.3.1 | Task Dependent | Electrical Underground Rough-In | 2020-08-14 07:00 | 2020-08-28 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 26 | 26 |  |  |  |  | MDC1.C1.CS1080: FS, MDC1.C1.CS1070: FS, MDC1-2527: FS 10 | MDC1.C1.C2020: SS 6, MDC1.C1.C2050: FS, MDC1.C1.C4000: FS, MDC1.C1.C2010: FS | VECA Electricians | 960 | 0
MDC1-2104 | In Progress | MDC1-BL.4.14.2 | Task Dependent | Design / Lead Time for Fire Alarm | 2020-06-29 08:00 | 2020-08-27 16:00 |  |  |  |  | 0 | 7 | 60 | 60 | 32 | 32 |  |  |  |  | MDC1-2003: FS | MDC1AD-1017: FS, MDC1AD-1024: FS |  | 0 | 0
MDC1.C4.CS1020 | Not Started | MDC1-BL.5.7.6.7.1.3 | Task Dependent | Erect PEMB Steel | 2020-08-08 07:00 | 2020-08-24 17:00 |  |  |  |  | 0 | 0 | 13 | 13 | 10 | 10 |  |  |  |  | MDC1.C4.CS1010: FS, MDC1.C3.CS1020: FS, MDC1-C4.P1100: FS | MDC1.C4.CS1040: FS, MDC1.C4.CS1030: FS | SURE STEEL | 910 | 0
MDC1-2131 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-08-18 08:00 | 2020-08-24 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 67 | 67 |  |  |  |  | MDC1-2134: FS, MDC1-2135: FS | MDC1.S.1210: FS |  | 0 | 0
MDC1.S.1050 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO2- UPM to UPM | 2020-08-18 07:00 | 2020-08-21 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 46 | 46 |  |  |  |  | MDC1.S.1020: FS, MDC1.C3.CS1030: FS, MDC1.C2.CS1050: FS | MDC1.S.1440: FS, MDC1.S.1420: FS, MDC1.S.1110: FS |  | 0 | 0
MDC1.AD.CS1090 | Not Started | MDC1-BL.5.7.3.1.2 | Task Dependent | Aggregate Base Course | 2020-08-14 07:00 | 2020-08-19 17:00 |  |  |  |  | 0 | 0 | 5 | 5 | 1 | 1 |  |  |  |  | MDC1.AD.CS1080: FS, MDC1.AD.CS1060: FS, MDC1-2003: FS, MDC1-C1.P1400: FS, MDC1-1995: FS, MDC1.AD.CS1080: FF | MDC1.AD.CS1100: FS | CSI | 500 | 0
MDC1-2012 | Not Started | MDC1-BL.4.13 | Task Dependent | Lead Time for Admin/COLO 1 Yard Steel | 2020-06-30 08:00 | 2020-08-18 17:00 |  |  |  |  | 0 | 0 | 49 | 49 | 118 | 118 |  |  |  |  | MDC1-2003: FS | MDC1-1967: FS, MDC1-1970: FS |  | 0 | 0
MDC1.C2.CS1050 | Not Started | MDC1-BL.5.7.4.7.2 | Task Dependent | Roof Panels Installation | 2020-07-31 07:00 | 2020-08-17 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 6 | 6 |  |  |  |  | MDC1.C1.CS1070: FS, MDC1-C2.P1300: FS, MDC1.C2.CS1030: FS | MDC1.C2.CS1060: FS, MDC1.C2.CS1080: FS, MDC1.C3.CS1050: FS, MDC1-C2.P1400: FS, MDC1-C3.P1300: FS, MDC1.C2.CS1070: FF, MDC1.S.1050: FS | SURE STEEL | 1680 | 0
MDC1-2135 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-08-04 08:00 | 2020-08-17 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 31 | 31 |  |  |  |  | MDC1-2134: FS | MDC1-2131: FS, MDC1-2190: FS |  | 0 | 0
MDC1.C3.CS1030 | Not Started | MDC1-BL.5.7.5.7.1.3 | Task Dependent | Secondary Steel | 2020-08-08 07:00 | 2020-08-15 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 7 | 7 |  |  |  |  | MDC1.C3.CS1020: FS | MDC1.C3.CS1040: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1.S.1050: FS | SURE STEEL | 210 | 0
MDC1.C2.CS1040 | Not Started | MDC1-BL.5.7.4.7.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-07-31 07:00 | 2020-08-14 17:00 |  |  |  |  | 0 | 0 | 12 | 12 | 8 | 8 |  |  |  |  | MDC1.C2.CS1020: FS, MDC1.C1.CS1050: FS, MDC1-C2.P1200: FS, MDC1.C2.CS1030: FS | MDC1.C3.CS1040: FS, MDC1-C3.P1200: FS, MDC1.C2.CS1060: SS, MDC1-C3.P1200: SS, MDC1.C2.CS1060: FS, MDC1.C3.CS1060: SS, MDC1-C4.P1200: SS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: SS, MDC1.C4.CS1050: SF, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF | SURE STEEL | 840 | 0
MDC1.AD.CS1080 | Not Started | MDC1-BL.5.7.3.1.2 | Task Dependent | MEP Undeground Rough-In (Interior) | 2020-07-27 07:00 | 2020-08-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 0 | 0 |  |  |  |  | MDC1-1999: FS, MDC1.AD.CS1060: FS | MDC1.S.1100: FS, MDC1.AD.CS1090: FS, MDC1.C1.CS1090: FS, MDC1-C1.P1400: FS, MDC1.AD.CS1090: FF | TCM, VECA Electricians | 1330 | 0
MDC1.C1.CS1080 | Not Started | MDC1-BL.5.7.1.2.5 | Task Dependent | Downspouts & Gutters | 2020-07-27 07:00 | 2020-08-13 17:00 |  |  |  |  | 0 | 0 | 15 | 15 | 0 | 0 |  |  |  |  | MDC1.C1.CS1060: FS, MDC1.C1.CS1070: FS, MDC1.AD.CS1070: FF 2 | MDC1.C1.C2000: FS, MDC1.C1.C1000: FS, MDC1.C2.CS1060: FS | SURE STEEL | 900 | 0
MDC1.S.1040 | In Progress | MDC1-BL.5.1.10 | Task Dependent | IWW System | 2020-05-26 07:00 | 2020-08-08 17:00 |  |  |  |  | 43.33 | 33 | 34 | 60 | 5 | 5 |  |  |  |  | MDC1-1997: FS | MDC1.S.1130: SS 30, MDC1.C1.C1250: FS, MDC1.S.1900: FS, MDC1.S.1870: FS |  | 0 | 0
MDC1.AD.CS1070 | Not Started | MDC1-BL.5.7.3.2 | Task Dependent | Downspouts & Gutters | 2020-07-27 07:00 | 2020-08-07 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 3 | 3 |  |  |  |  | MDC1.AD.CS1060: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: FS, MDC1-C1.P1200: FS | MDC1.C1.CS1080: FF 2, MDC1-1965: FS, MDC1-1972: FS | SURE STEEL | 900 | 0
MDC1.C3.CS1020 | Not Started | MDC1-BL.5.7.5.7.1.3 | Task Dependent | Erect PEMB Steel | 2020-07-23 07:00 | 2020-08-07 17:00 |  |  |  |  | 0 | 0 | 13 | 13 | 7 | 7 |  |  |  |  | MDC1.C3.CS1000: FS, MDC1.C2.CS1020: FS, MDC1-C3.P1100: FS | MDC1.C3.CS1040: FS, MDC1.C4.CS1020: FS, MDC1-C4.P1100: FS, MDC1.C3.CS1030: FS | SURE STEEL | 910 | 0
MDC1.C4.CS1010 | Not Started | MDC1-BL.5.7.6.7.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-07-25 07:00 | 2020-08-06 17:00 |  |  |  |  | 0 | 0 | 10 | 10 | 11 | 11 |  |  |  |  | MDC1.C4.CS1000: SS 10, MDC1-C4.P1000: FS | MDC1.C4.CS1020: FS, MDC1.C4.CS1070: FS | CSI, Advantage | 2000 | 0
MDC1-1997.1 | In Progress | MDC1-BL.4.11.5.1 | Task Dependent | Neher Mcgrath Study | 2020-07-02 08:00 | 2020-08-06 17:00 |  |  |  |  | 28.57 | 7 | 25 | 35 | 51 | 51 |  |  |  |  | MDC1-1999: FS 3 | MDC1-1993: FS, MDC1.S.1020: FS |  | 0 | 0
MDC1.S.1020 | Not Started | MDC1-BL.5.1.3.1.2.4 | Task Dependent | Duct Bank - COLO1- UPM to UPM | 2020-07-31 07:00 | 2020-08-05 17:00 |  |  |  |  | 0 | 0 | 4 | 4 | 56 | 56 |  |  |  |  | MDC1-1997.1: FS, MDC1.AD.CS1060: FS, MDC1.C2.CS1030: FS | MDC1.S.1360: FS, MDC1.S.1290: FS, MDC1.S.1050: FS |  | 0 | 0
MDC1-2103 | Not Started | MDC1-BL.4.14.2 | Task Dependent | Design / Lead Time for Fire Protection | 2020-07-06 08:00 | 2020-08-04 16:00 |  |  |  |  | 0 | 0 | 30 | 30 | 108 | 108 | Start On or After |  |  |  | MDC1-2003: FS | MDC1AD-1024: FS |  | 0 | 0
MDC1-2134 | Not Started | MDC1-BL.4.11.5.4 | Task Dependent | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | 2020-07-21 08:00 | 2020-08-03 17:00 |  |  |  |  | 0 | 0 | 14 | 14 | 5 | 5 | Start On or After |  |  |  | MDC1-2140.2: FS | MDC1-2133: FS, MDC1-2131: FS, MDC1-2135: FS, MDC1-2132: FS, MDC1-2190: FS, MDC1-1996: FS |  | 0 | 0
MDC1-1993 | Not Started | MDC1-BL.4.11.5.1 | Task Dependent | MV Ductbanks Procurement | 2020-07-25 08:00 | 2020-08-02 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 51 | 51 |  |  |  |  | MDC1-1997.1: FS | MDC1.C2.Cx2010: FS, MDC1-1965: FS |  | 0 | 0
MDC1.C2.CS1030 | Not Started | MDC1-BL.5.7.4.7.1.3 | Task Dependent | Secondary Steel | 2020-07-23 07:00 | 2020-07-30 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 6 | 6 |  |  |  |  | MDC1.C2.CS1020: FS | MDC1.C2.CS1040: FS, MDC1.C2.CS1060: FS, MDC1-C3.P1200: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF, MDC1.C2.CS1050: FS, MDC1.S.1020: FS | SURE STEEL | 210 | 0
MDC1-2102 | In Progress | MDC1-BL.4.14.2 | Task Dependent | Design / Lead Time for M&P overhead | 2020-06-29 08:00 | 2020-07-28 16:00 |  |  |  |  | 0 | 7 | 58 | 30 | 86 | 86 |  |  |  |  | MDC1-2003: FS | MDC1AD-1024: FS |  | 0 | 0
MDC1-2101 | Not Started | MDC1-BL.4.13 | Task Dependent | Lead time for Drywall/Framing | 2020-06-30 08:00 | 2020-07-26 16:00 |  |  |  |  | 0 | 0 | 27 | 27 | 80 | 80 |  |  |  |  | MDC1-2003: FS | MDC1AD-1016: FS |  | 0 | 0
MDC1.AD.CS1060 | Not Started | MDC1-BL.5.7.3.2 | Task Dependent | Roof Panels Installation | 2020-07-18 07:00 | 2020-07-25 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1-C1.P1300: FS, MDC1.AD.CS1040: FF, MDC1.AD.CS1050: SS 5, MDC1-C1.P1200: FF | MDC1.AD.CS1070: FS, MDC1.AD.CS1090: FS, MDC1.C1.CS1070: SS, MDC1-C1.P1400: FS, MDC1.AD.CS1080: FS, MDC1.S.1020: FS | SURE STEEL | 0 | 0
MDC1.C1.CS1070 | Not Started | MDC1-BL.5.7.1.2.5 | Task Dependent | Roof Panels Installation | 2020-07-18 07:00 | 2020-07-25 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.C1.CS1060: SS, MDC1.AD.CS1060: SS | MDC1.C1.C2000: FS, MDC1.C1.C1050: SS 7, MDC1.C1.CS1080: FS, MDC1.C1.CS1100: FS, MDC1.C2.CS1050: FS, MDC1-C2.P1300: FS, MDC1.C1.C1000: FS 2 | SURE STEEL | 0 | 0
MDC1.S.1030 | In Progress | MDC1-BL.5.1.10 | Task Dependent | Site Sanitary | 2020-05-11 07:00 | 2020-07-24 17:00 |  |  |  |  | 43.33 | 43 | 34 | 60 | 44 | 44 |  |  |  |  | MDC1-1997: FS | MDC1.S.1120: SS 30, MDC1.C1.C1250: FS | Advantage | 3000 | 0
MDC1.C4.CS1000 | In Progress | MDC1-BL.5.7.6.7.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP/Backfill | 2020-07-06 07:00 | 2020-07-23 17:00 |  |  |  |  | 33.33 | 5 | 10 | 15 | 11 | 11 |  |  |  |  | MDC1.C3.CS1010: FS, MDC1-C4.P1000: FS | MDC1.C4.CS1010: SS 10 | CSI, Advantage | 3000 | 0
MDC1.AD.CS1050 | Not Started | MDC1-BL.5.7.3.2 | Task Dependent | Exterior Insulated Metal Panels Installation | 2020-07-13 07:00 | 2020-07-22 17:00 |  |  |  |  | 0 | 0 | 9 | 9 | 0 | 0 |  |  |  |  | MDC1.AD.CS1030: SS 9, MDC1-2011: FS, MDC1-2013: SS 4, MDC1-2003: FS, MDC1-2003: FF, MDC1.AD.CS1040: FS | MDC1AD-1010: FS, MDC1.C1.CS1050: SS, MDC1.AD.CS1060: SS 5, MDC1.AD.CS1070: FS, MDC1.C1.CS1060: SS, MDC1-1965: FS, MDC1-1972: FS, MDC1-C1.P1300: SS 2 | SURE STEEL | 0 | 0
MDC1.C2.CS1020 | Not Started | MDC1-BL.5.7.4.7.1.3 | Task Dependent | Erect PEMB Steel | 2020-07-07 07:00 | 2020-07-22 17:00 |  |  |  |  | 0 | 0 | 13 | 13 | 6 | 6 |  |  |  |  | MDC1.C2.CS1010: FS, MDC1.C1.CS1030: FS, MDC1-C2.P1100: FS | MDC1.C2.CS1040: FS, MDC1.C3.CS1020: FS, MDC1-C3.P1100: FS, MDC1.C2.CS1030: FS, MDC1.C2.CS1070: FF, MDC1.C2.CS1080: FS, MDC1-C2.P1400: FS | SURE STEEL | 0 | 0
MDC1.C2.CS1010 | Completed | MDC1-BL.5.7.4.7.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-07-08 07:00 | 2020-07-20 17:00 |  |  |  |  | 100 | 10 | 0 | 10 | [6 empty] | MDC1.C2.CS1000: SS 10, MDC1.C1.CS1010: FS 20, MDC1-C2.P1000: FS | MDC1.C2.CS1020: FS, MDC1.C3.CS1000: FS | CSI, Advantage | 2000 | 0
MDC1.C3.CS1000 | In Progress | MDC1-BL.5.7.5.7.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-07-08 07:00 | 2020-07-20 17:00 |  |  |  |  | 10 | 4 | 9 | 10 | 17 | 17 |  |  |  |  | MDC1.C3.CS1010: SS 10, MDC1-C3.P1000: FS, MDC1.C2.CS1010: FS | MDC1.C3.CS1020: FS, MDC1.C3.CS1070: FS | CSI | 1000 | 0
MDC1-2140.2 | Not Started | MDC1-BL.4.9.2 | Finish Milestone | CO- DRB# 1 - Approved |  | 2020-07-20 17:00 |  |  | 2020-07-20 17:00 |  | 0 | 0 | 0 | 0 | 5 | 5 |  |  |  |  | MDC1-2140.1: FS | MDC1-2134: FS, MDC1-2189: FS, MDC1-2190: FS |  | 0 | 0
MDC1.C1.CS1050 | Not Started | MDC1-BL.5.7.1.2.2 | Task Dependent | Exterior Insulated Metal Panels Installation - East Elevation | 2020-07-13 07:00 | 2020-07-18 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 5 | 5 |  |  |  |  | MDC1.C1.CS1030: FS, MDC1-C1.P1200: FS, MDC1-2003: FS, MDC1.C1.CS1040: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: SS | MDC1.C1.CS1060: SS, MDC1.C2.CS1040: FS, MDC1-C2.P1200: FS | SURE STEEL | 0 | 0
MDC1.C1.CS1060 | Not Started | MDC1-BL.5.7.1.2.4 | Task Dependent | Exterior Insulated Metal Panels Installation - West Elevation | 2020-07-13 07:00 | 2020-07-18 17:00 |  |  |  |  | 0 | 0 | 6 | 6 | 5 | 5 |  |  |  |  | MDC1.C1.CS1050: SS, MDC1.C1.CS1040: FS, MDC1.AD.CS1040: FS, MDC1.AD.CS1050: SS, MDC1-C1.P1200: FS | MDC1.C1.CS1080: FS, MDC1.C1.CS1070: SS, MDC1.C1.C1000: FS 4, MDC1.C2.CS1060: FS, MDC1-C3.P1200: FS, MDC1.C3.CS1060: FS, MDC1.C3.CS1050: FS, MDC1-C4.P1200: FS, MDC1.C4.CS1060: FS, MDC1.C4.CS1050: FF | SURE STEEL | 0 | 0
MDC1-2527 | Not Started | MDC1-BL.4.10.3 | Finish Milestone | MDC1 Deliery -OFCI release submittal release |  | 2020-07-17 07:00 |  |  | 2020-07-17 07:00 |  | 0 | 0 | 0 | 0 | 3 | 3 | Finish On or After | 2020-07-17 07:00 |  |  | MDC1.M1000: FS, MDC1-1999: FS | MDC1.C1.E1320: FS, MDC1.C1.E1330: FS, MDC1.C1.E1380: FS, MDC1.C1.E1470: FS, MDC1.C2.E1300: FS, MDC1.C2.E1310: FS, MDC1.C2.E1360: FS, MDC1.C2.E1410: FS, MDC1.C3.E1340: FS, MDC1.C3.E1350: FS, MDC1.C3.E1360: FS, MDC1.C3.E1370: FS, MDC1.C4.E1360: FS, MDC1.C4.E1370: FS, MDC1.C4.E1380: FS, MDC1.C4.E1390: FS, MDC1-2511: FS, MDC1.C1.E1300: FS, MDC1.C1.E1310: FS, MDC1.C1.E1410: FS, MDC1.C1.E1420: FS, MDC1.C2.E1280: FS, MDC1.C2.E1290: FS, MDC1.C2.E1320: FS, MDC1.C2.E1350: FS, MDC1.C3.E1160: FS, MDC1.C3.E1170: FS, MDC1.C3.E1320: FS, MDC1.C3.E1330: FS, MDC1.C4.E1280: FS, MDC1.C4.E1310: FS, MDC1.C4.E1340: FS, MDC1.C4.E1350: FS, MDC1.C1.E1010: FS, MDC1.C1.E1020: FS, MDC1.C1.E1090: FS, MDC1.C1.E1110: FS, MDC1.C2.E1010: FS, MDC1.C2.E1020: FS, MDC1.C2.E1090: FS, MDC1.C2.E1110: FS, MDC1.C3.E1010: FS, MDC1.C3.E1030: FS, MDC1.C3.E1090: FS, MDC1.C3.E1110: FS, MDC1.C4.E1010: FS, MDC1.C4.E1020: FS, MDC1.C4.E1090: FS, MDC1.C4.E1110: FS, MDC1.C1.E1130: FS, MDC1.C1.E1170: FS, MDC1.C1.E1250: FS, MDC1.C1.E1270: FS, MDC1.C2.E1150: FS, MDC1.C2.E1230: FS, MDC1.C2.E1250: FS, MDC1.C3.E1190: FS, MDC1.C3.E1210: FS, MDC1.C3.E1280: FS, MDC1.C4.E1150: FS, MDC1.C4.E1170: FS, MDC1.C4.E1250: FS, MDC1.C4.E1270: FS, MDC1.C1.E1050: FS, MDC1.C1.E1070: FS, MDC1.C1.E1190: FS, MDC1.C1.E1210: FS, MDC1.C2.E1040: FS, MDC1.C2.E1070: FS, MDC1.C2.E1170: FS, MDC1.C2.E1190: FS, MDC1.C3.E1050: FS, MDC1.C3.E1070: FS, MDC1.C3.E1230: FS, MDC1.C3.E1250: FS, MDC1.C4.E1050: FS, MDC1.C4.E1070: FS, MDC1.C4.E1190: FS, MDC1.C4.E1210: FS, MDC1.C1.E1350: FS, MDC1.C1.E1370: FS, MDC1.C1.E1440: FS, MDC1.C1.E1460: FS, MDC1.C2.E1380: FS, MDC1.C2.E1400: FS, MDC1.C2.E1430: FS, MDC1.C2.E1450: FS, MDC1.C3.E1390: FS, MDC1.C3.E1410: FS, MDC1.C3.E1430: FS, MDC1.C3.E1450: FS, MDC1.C4.E1410: FS, MDC1.C4.E1430: FS, MDC1.C4.E1450: FS, MDC1.C4.E1470: FS, MDC1-2511: SS, MDC1-2509: FS, MDC1-2510: FS, MDC1-2512: FS, MDC1-2513: FS, MDC1-2514: FS, MDC1-1965: FS, MDC1-1972: FS, MDC1.C1.C1000: FS 20, MDC1.C1.C3000: FS 10, MDC1.C1.C2000: FS 10, MDC1.C1.C4000: FS 10, MDC1.C1.C4030: FS 10, MDC1-2133: FS, MDC1-2004: FS, MDC1.C3.C3350: FS, MDC1.C3.C3110: FS, MDC1.C3.C3370: FS, MDC1.C3.Cx2030: FS, MDC1.C2.C4380: FS, MDC1.C2.C4100: FS, MDC1.C2.C4400: FS, MDC1.C2.Cx3030: FS, MDC1.C2.Cx2030: FS |  | 0 | 0
MDC1.AD.CS1040 | Not Started | MDC1-BL.5.7.3.1.3 | Task Dependent | Secondary Steel | 2020-07-02 07:00 | 2020-07-10 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 0 | 0 |  |  |  |  | MDC1.AD.CS1030: FS | MDC1.AD.CS1050: FS, MDC1AD-1010: FS, MDC1.C1.CS1050: FS, MDC1.AD.CS1060: FF, MDC1.AD.CS1070: FS, MDC1.C1.CS1060: FS, MDC1-1965: FS, MDC1-1972: FS, MDC1-C1.P1300: FS | SURE STEEL | 0 | 0
MDC1.AD.CS1030 | In Progress | MDC1-BL.5.7.3.1.3 | Task Dependent | Erect PEMB Steel | 2020-06-29 07:00 | 2020-07-09 17:00 |  |  |  |  | 66.67 | 6 | 3 | 9 | 0 | 0 |  |  |  |  | MDC1-1383: FS 1, MDC1-2002: FS, MDC1.S.1010: FS, MDC1-2111: FS | MDC1.AD.CS1050: SS 9, MDC1.C1.CS1030: SS 5, MDC1-C1.P1200: SS 12, MDC1-C1.P1100: SS, MDC1.AD.CS1040: FS | SURE STEEL | 910 | 0
MDC1.C1.CS1030 | In Progress | MDC1-BL.5.7.1.1.3 | Task Dependent | Erect PEMB Steel | 2020-06-29 07:00 | 2020-07-09 17:00 |  |  |  |  | 33.33 | 2 | 6 | 9 | 6 | 6 |  |  |  |  | MDC1.C1.CS1010: FS, MDC1.AD.CS1030: SS 5, MDC1-C1.P1100: FS | MDC1.C1.CS1050: FS, MDC1.C2.CS1020: FS, MDC1-C2.P1100: FS, MDC1.C1.CS1040: SS 4 | SURE STEEL | 0 | 0
MDC1.C2.CS1000 | Completed | MDC1-BL.5.7.4.7.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP/Backfill | 2020-06-22 07:00 | 2020-07-09 17:00 |  |  |  |  | 100 | 29 | 0 | 15 | [6 empty] | MDC1.C1.CS1000: SS 10, MDC1-C2.P1000: FS | MDC1.C2.CS1010: SS 10, MDC1.C3.CS1010: SS 10, MDC1-C3.P1000: FS | CSI, Advantage | 3000 | 0
MDC1.C3.CS1010 | In Progress | MDC1-BL.5.7.5.7.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP/Backfill | 2020-06-22 07:00 | 2020-07-09 17:00 |  |  |  |  | 0 | 10 | 16 | 15 | 11 | 11 |  |  |  |  | MDC1.C2.CS1000: SS 10 | MDC1.C3.CS1000: SS 10, MDC1.C4.CS1000: FS, MDC1-C4.P1000: FS | CSI, Advantage | 3000 | 0
MDC1.C1.CS1040 | Not Started | MDC1-BL.5.7.1.1.3 | Task Dependent | Secondary Steel | 2020-07-01 07:00 | 2020-07-09 17:00 |  |  |  |  | 0 | 0 | 7 | 7 | 6 | 6 |  |  |  |  | MDC1.C1.CS1030: SS 4 | MDC1.C1.CS1050: FS, MDC1.C1.CS1060: FS | SURE STEEL | 0 | 0
MDC1-2111 | Completed | MDC1-BL.4.9.2 | Finish Milestone | Phase 1C1- MDC1 Commitment for steel crew |  | 2020-06-29 07:00 |  |  | 2020-06-29 07:00 |  | 100 | 0 | 0 | 0 |  |  | Finish On | 2020-06-04 17:00 |  |  | MDC1-2002: FS | MDC1.AD.CS1030: FS |  | 0 | 0
MDC1.C1.CS1010 | Completed | MDC1-BL.5.7.1.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-06-13 07:00 | 2020-06-25 17:00 |  |  |  |  | 100 | 9 | 0 | 10 | [6 empty] | MDC1.AD.CS1020: FF, MDC1-C1.P1000: FS | MDC1.C1.CS1030: FS, MDC1.C2.CS1010: FS 20 | CSI, Advantage | 2500 | 0
MDC1-2000 | In Progress | MDC1-BL.4.11.1 | Task Dependent | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | 2020-04-27 08:00 | 2020-06-21 17:00 | 2020-04-27 08:00 |  |  |  | 55.36 | 63 | 25 | 56 | 97 | 97 |  |  |  |  | MDC1-2002: FS | MDC1-1963: FS |  | 0 | 0
MDC1-2011 | In Progress | MDC1-BL.4.13 | Task Dependent | Lead Time for Wall & Roof Metal Panels | 2020-04-27 08:00 | 2020-06-21 17:00 |  |  |  |  | 98.21 | 83 | 1 | 56 | 12 | 12 |  |  |  |  | MDC1-2002: FS 7 | MDC1.AD.CS1050: FS |  | 0 | 0
MDC1-2013 | In Progress | MDC1-BL.4.13 | Task Dependent | Lead Time for HM Ext. frames | 2020-04-27 08:00 | 2020-06-21 17:00 |  |  |  |  | 80.36 | 83 | 11 | 56 | 13 | 13 |  |  |  |  | MDC1-2002: FS 7 | MDC1.AD.CS1050: SS 4 |  | 0 | 0
MDC1.S.1010 | Completed | MDC1-BL.5.1.1 | Task Dependent | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | 2020-05-14 07:00 | 2020-06-19 17:00 |  |  |  |  | 100 | 24 | 0 | 30 | [6 empty] | MDC1.S.1000: SS 15 | MDC1-C1.P1100: FS, MDC1.AD.CS1030: FS |  | 0 | 0
MDC1-1383 | Completed | MDC1-BL.4.13 | Task Dependent | Lead Time for PEMB | 2020-02-19 08:00 | 2020-06-18 17:00 |  |  |  |  | 100 | 115 | 0 | 121 | [6 empty] | A1170: FS, MDC1-2001: FS | MDC1.AD.CS1030: FS 1 |  | 0 | 0
MDC1.AD.CS1020 | Completed | MDC1-BL.5.7.3.1.1 | Task Dependent | Interior Footings - Excavate/FRP/Backfill | 2020-06-05 07:00 | 2020-06-16 17:00 |  |  |  |  | 100 | 9 | 0 | 10 | [6 empty] | MDC1-1998: FF 10, MDC1-2002: FS, MDC1-1977: FS, MDC1.AD.CS1010: FS, MDC1.AD.CS1010: FF | MDC1.C1.CS1010: FF | CSI, Advantage | 2000 | 0
MDC1-1999 | Completed | MDC1-BL.4.11.1 | Task Dependent | BIM Modeling (Under ground) | 2020-05-05 08:00 | 2020-06-08 17:00 | 2020-05-05 08:00 |  |  |  | 100 | 34 | 0 | 35 | [6 empty] | MDC1-1997: FS | MDC1-1965: FS, MDC1-1972: FS, MDC1.AD.CS1080: FS, MDC1-2008: FS, MDC1-1997.1: FS 3, MDC1-2527: FS |  | 0 | 0
MDC1.C1.CS1020 | Completed | MDC1-BL.5.7.1.1.1 | Task Dependent | Perimeter Foundations - Waterproof Backfill | 2020-05-26 07:00 | 2020-06-06 17:00 | 2020-05-26 07:00 |  |  |  | 100 | 18 | 0 | 10 | [6 empty] | MDC1.C1.CS1000: FS | MDC1-C2.P1000: FS | CSI | 100 | 0
MDC1.AD.CS1010 | Completed | MDC1-BL.5.7.3.1.1 | Task Dependent | Perimeter Foundations - Waterproof/Backfill | 2020-06-01 07:00 | 2020-06-04 17:00 |  |  |  |  | 100 | 7 | 0 | 4 | [6 empty] | MDC1.AD.CS1000: FS | MDC1.AD.CS1020: FS, MDC1.AD.CS1020: FF | CSI | 40 | 0
MDC1.C1.CS1000 | Completed | MDC1-BL.5.7.1.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP | 2020-05-15 07:00 | 2020-06-03 17:00 |  |  |  |  | 100 | 9 | 0 | 15 | [6 empty] | MDC1.AD.CS1000: FS | MDC1.C2.CS1000: SS 10, MDC1-C2.P1000: FS, MDC1.C1.CS1020: FS | CSI, Advantage | 3000 | 0
MDC1-2140.1 | In Progress | MDC1-BL.4.9.2 | Task Dependent | MDC1 Issue DRB #1 for Review | 2020-05-26 07:00 | 2020-06-01 17:00 |  |  |  |  | 0 | 32 | 17 | 5 | 5 | 5 |  |  |  |  | MDC1-2002: FS | MDC1-2140.2: FS |  | 0 | 0
MDC1-1977 | Completed | MDC1-BL.4.13 | Task Dependent | Lead Time for Rebar (Footings & Walls) | 2020-04-27 08:00 | 2020-05-31 17:00 |  |  |  |  | 100 | 22 | 0 | 35 | [6 empty] | A1170: FS, MDC1-2002: FS | MDC1.AD.CS1000: FS, MDC1.AD.CS1020: FS |  | 0 | 0
MDC1-1997 | Completed | MDC1-BL.4.11.5.1 | Task Dependent | Off-Site BIM Modeling & Coordination | 2020-04-27 08:00 | 2020-05-24 17:00 |  |  |  |  | 100 | 21 | 0 | 28 | [6 empty] | MDC1-2002: FS 7 | MDC1.S.1030: FS, MDC1.S.1120: FS, MDC1.S.1040: FS, MDC1-1999: FS, MDC1-2004: FS, MDC1-1994: FS |  | 0 | 0
MDC1.S.1000 | Completed | MDC1-BL.5.1.2 | Task Dependent | Mobilization | 2020-04-27 07:00 | 2020-05-20 17:00 |  |  |  |  | 100 | 23 | 0 | 20 | [6 empty] | MDC1-2002: FS | MDC1.S.1010: SS 15, MDC1.P1010: SS -1 |  | 0 | 0
MDC1-1994 | Completed | MDC1-BL.4.11.5.1 | Task Dependent | Telecom DuctBank / Vaults Procurement | 2020-05-14 08:00 | 2020-05-18 17:00 |  |  |  |  | 100 | 45 | 0 | 5 | [6 empty] | MDC1-2002: FS, MDC1-1997: FS | MDC1.S.1160: FS |  | 0 | 0
MDC1-1998 | Completed | MDC1-BL.4.11.1 | Task Dependent | Underground Grounding Procurement | 2020-04-27 08:00 | 2020-05-17 17:00 |  |  |  |  | 100 | 21 | 0 | 21 | [6 empty] | MDC1-2002: FS 7 | MDC1.AD.CS1020: FF 10 |  | 0 | 0
MDC1.AD.CS1000 | Completed | MDC1-BL.5.7.3.1.1 | Task Dependent | Perimeter Foundations - Excavate/FRP | 2020-04-27 07:00 | 2020-05-14 17:00 |  |  |  |  | 100 | 23 | 0 | 15 | [6 empty] | MDC1-1977: FS, MDC1-2002: FS, MDC1-P1020: FS, MDC1-C1.P1000: FS | MDC1.C1.CS1000: FS, MDC1.AD.CS1010: FS | CSI, Advantage | 3000 | 0